## Sheet2
Sum of Actual work | Column Labels
Row Labels | CM | PM | Grand Total
43AT69002 | 55.5 | 130.2 | 185.7
2021 | 55.5 | 130.2 | 185.7
44AT69002 | 58 | 150.2 | 208.2
2021 | 58 | 150.2 | 208.2
Grand Total | 113.5 | 280.4 | 393.9

## Sheet1
Main WorkCtr | Oper.WorkCenter | Order | ABC indic. | Functional loc. | Order Type | Description | Opr. short text | Actual work | System status | Bas. start date | Basic fin. date | Normal duration | Number | Work | User status | TotSum (actual) | Total act.costs | Actual Finish
SH_DCS | SH_DCS | 70040874 | A | 43AT69002 | SM02 | (43) NOX Analysers - Envirosoft Health C | Envirosoft Health Checks | 8 | TECO CNF PRT NMAT PRC SETC | 2018-03-15 | 2018-05-06 | 8 | 1 | 8 |  | 0 | 0 | 2018-05-21
SH_DCS | SH_VEND | 70040874 | A | 43AT69002 | SM02 | (43) NOX Analysers - Envirosoft Health C | Envirosoft Health Checks | 8 | TECO CNF PRT NMAT PRC SETC | 2018-03-15 | 2018-05-06 | 8 | 1 | 8 |  | 0 | 0 | 2018-05-21
SH_ELECT | SH_ELECT | 60001327 |  | 43AT69002 | SM01 | SCVH-Nox Analyser sample line deficiency | SCV H - Nox Analyser deficiency sample l | 10 | TECO CNF PRT NMAT PRC SETC | 2010-04-22 | 2010-04-29 | 2 | 1 | 2 |  | 0 | 0 | 2010-04-23
SH_ENG | SH_ENG | 60008165 |  | 43AT69002 | SPRJ | Process Combustion Nox Project | Process Combustion Nox Project | 48 | TECO CNF PRT GMPS MACM PRC SETC | 2014-11-03 | 2014-11-03 | 24 | 2 | 48 |  | 4900.82 | 4900.82 | 2014-12-12
SH_ENG | SH_I&C | 60008165 |  | 43AT69002 | SPRJ | Process Combustion Nox Project | Process Combustion Nox Project | 24 | TECO CNF PRT GMPS MACM PRC SETC | 2014-11-03 | 2014-11-03 | 24 | 1 | 24 |  | 4900.82 | 4900.82 | 2014-12-12
SH_ENG | SH_I&C | 60008165 |  | 43AT69002 | SPRJ | Process Combustion Nox Project | Process Combustion Nox Project | 0 | TECO CNF PRT GMPS MACM PRC SETC | 2014-11-03 | 2014-11-03 | 8 | 1 | 8 |  | 4900.82 | 4900.82 | 2014-12-12
SH_ENG | SH_ENG | 60008167 | A | 44AT69002 | SPRJ | Process Combustion Nox Project | Process Combustion Nox Project | 75 | TECO CNF PRT GMPS MACM PRC SETC | 2014-11-10 | 2014-11-14 | 37.5 | 2 | 75 |  | 9761.08 | 9761.08 | 2014-12-12
SH_ENG | SH_I&C | 60008167 | A | 44AT69002 | SPRJ | Process Combustion Nox Project | Process Combustion Nox Project | 16 | TECO CNF PRT GMPS MACM PRC SETC | 2014-11-10 | 2014-11-14 | 16 | 1 | 16 |  | 9761.08 | 9761.08 | 2014-12-12
SH_ENG | SH_I&C | 60008167 | A | 44AT69002 | SPRJ | Process Combustion Nox Project | Process Combustion Nox Project | 21.5 | TECO CNF PRT GMPS MACM PRC SETC | 2014-11-10 | 2014-11-14 | 21.5 | 1 | 21.5 |  | 9761.08 | 9761.08 | 2014-12-12
SH_I&C | SH_I&C | 60000815 |  | 43AT69002 | SM01 | Nox Analyser on SCV-1H not reading | Nox Analyser on SCH-H not reading | 6 | TECO CNF PRT NMAT PRC SETC | 2010-01-11 | 2010-01-11 | 2 | 1 | 2 |  | 0 | 0 | 2010-01-15
SH_I&C | SH_I&C | 60000822 |  | 43AT69002 | SM01 | SCV-1H Nox Anayser faulty | SCV-1H Nox Anayser faulty | 6 | TECO CNF PRT NMAT PRC SETC | 2010-01-25 | 2010-01-27 | 12 | 1 | 12 |  | 0 | 0 | 2010-01-28
SH_I&C | SH_I&C | 60000860 |  | 43AT69002 | SM01 | Check & replace calibration gas | Check & replace calibration gas | 2 | TECO CNF PRT NMAT PRC SETC | 2010-01-19 |  | 1 | 2 | 2 |  | 0 | 0 | 2010-01-21
SH_I&C | SH_I&C | 60000945 | A | 44AT69002 | SM01 | Flue Gas Flowmeter reading zero | Flue Gas Flowmeter reading zero | 4 | TECO CNF PRT NMAT PRC SETC | 2010-02-04 |  | 3 | 1 | 3 |  | 0 | 0 | 2010-02-08
SH_I&C | SH_I&C | 60000989 | A | 44AT69002 | SM01 | Check out Durag flowmeter | Check out Durag flowmeter | 4 | TECO CNF PRT NMAT PRC SETC | 2010-02-11 | 2010-02-12 | 3 | 1 | 3 |  | 0 | 0 | 2010-02-15
SH_I&C | SH_I&C | 60001209 | A | 44AT69002 | SM01 | Durag flowmeter at fault | Durag flowmeter reporting bad data | 0 | TECO CNF NMAT PPRT PRC SETC | 2010-03-23 | 2010-03-23 | 2 | 1 | 2 |  | 0 | 0 | 2010-04-06
SH_I&C | SH_I&C | 60001209 | A | 44AT69002 | SM01 | Durag flowmeter at fault | Durag flowmeter reporting bad data | 2 | TECO CNF NMAT PPRT PRC SETC | 2010-03-23 | 2010-03-23 | 2 | 1 | 2 |  | 0 | 0 | 2010-04-06
SH_I&C | SH_I&C | 60001220 | A | 44AT69002 | SM01 | Nox analy at top of range | Nox analy at top of range | 2 | TECO CNF PRT NMAT PRC SETC | 2010-03-22 |  | 2 | 1 | 2 |  | 0 | 0 | 2010-03-31
SH_I&C | SH_I&C | 60002305 |  | 43AT69002 | SM01 | NOx analyser suspect reading | *C* NOx analyser suspect reading | 2 | TECO CNF PRT NMAT PRC SETC | 2010-12-25 | 2010-12-25 | 2 | 1 | 2 |  | 100 | 100 | 2010-12-24
SH_I&C | SH_I&C | 60002316 | A | 44AT69002 | SM01 | Error code 40 on Durag Flowmeter | Error code 40 on Durag Flowmeter | 6 | TECO CNF PRT CSER NMAT PRC SETC | 2011-01-05 | 2011-01-05 | 6 | 1 | 6 |  | 300 | 300 | 2011-01-05
SH_I&C | SH_I&C | 60002380 | A | 44AT69002 | SM01 | Re-calibration of Durag Flowmeter | Re-calibration of Durag Flowmeter | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2011-01-25 | 2011-01-25 | 4 | 1 | 4 |  | 275.37 | 275.37 | 2011-01-25
SH_I&C | SH_I&C | 60002404 |  | 43AT69002 | SM01 | Nox analyser U/S | Nox analyser U/S | 8 | TECO CNF PRT NMAT PRC SETC | 2011-01-24 | 2011-01-24 | 2 | 1 | 2 |  | 400 | 400 | 2011-01-26
SH_I&C | SH_I&C | 60002422 |  | 43AT69002 | SM01 | Nox Analyser - flat Lining | Nox Analyser - flat Lining | 4 | TECO CNF PRT NMAT PRC SETC | 2011-01-27 | 2011-01-27 | 3 | 1 | 3 |  | 200 | 200 | 2011-01-27
SH_I&C | SH_I&C | 60003459 |  | 43AT69002 | SM01 | NOx analyser reading very low - below 10 | NOx analyser reading very low - below 10 | 6 | TECO CNF PRT NMAT PRC SETC | 2011-10-21 | 2011-10-21 | 2 | 1 | 2 |  | 700 | 700 | 2011-11-03
SH_I&C | SH_I&C | 60003459 |  | 43AT69002 | SM01 | NOx analyser reading very low - below 10 | Orbital investigation of pump issues | 8 | TECO CNF PRT NMAT PRC SETC | 2011-10-21 | 2011-10-21 | 8 | 1 | 8 |  | 700 | 700 | 2011-11-03
SH_I&C | SH_I&C | 60005194 |  | 43AT69002 | SM01 | 43AI69002C Train 1 NOX Analyser | 43AI69002C Train 1 NOX Analyser | 8 | TECO CNF GMPS MACM PPRT PRC SETC | 2012-11-15 |  | 4 | 1 | 4 |  | 547.3 | 547.3 | 2012-11-15
SH_I&C | SH_I&C | 60005195 | A | 44AT69002 | SM01 | 44AT69002 | 44AT69002 | 4 | TECO CNF PRT NMAT PRC SETC | 2012-11-15 |  | 4 | 1 | 4 |  | 200 | 200 | 2012-11-15
SH_I&C | SH_I&C | 60005217 | A | 44AT69002 | SM01 | SCV 2A NOX analyser failed auto cal | SCV 2A NOX analyser failed auto cal | 8 | TECO CNF PRT NMAT PRC SETC | 2012-11-21 |  | 4 | 1 | 4 |  | 400 | 400 | 2012-11-26
SH_I&C | SH_I&C | 60005235 |  | 43AT69002 | SM01 | Envirosoft Software Upgrade | Envirosoft Software Upgrade (P Jones) | 0 | TECO CNF PRT NMAT PRC SETC | 2013-01-23 | 2013-01-24 | 0 | 0 | 0 |  | 1200 | 1200 | 2013-01-24
SH_I&C | SH_I&C | 60005235 |  | 43AT69002 | SM01 | Envirosoft Software Upgrade | Envirosoft Training (3 techs) | 12 | TECO CNF PRT NMAT PRC SETC | 2013-01-23 | 2013-01-24 | 4 | 3 | 12 |  | 1200 | 1200 | 2013-01-24
SH_I&C | SH_I&C | 60005235 |  | 43AT69002 | SM01 | Envirosoft Software Upgrade | Envirosoft Training (3 techs) | 12 | TECO CNF PRT NMAT PRC SETC | 2013-01-23 | 2013-01-24 | 4 | 3 | 12 |  | 1200 | 1200 | 2013-01-24
SH_I&C | SH_I&C | 60005567 |  | 43AT69002 | SM01 | Calibration check required on NOx analys | Calibration check required on NOx analys | 4 | TECO CNF PRT NMAT PRC SETC | 2013-03-08 |  | 4 | 1 | 4 |  | 200 | 200 | 2013-03-14
SH_I&C | SH_I&C | 60005610 | A | 44AT69002 | SM01 | SCV 2A Nox Analyser U/S | SCV 2A Nox Analyser U/S | 4 | TECO CNF PRT NMAT PRC SETC | 2013-03-21 |  | 4 | 1 | 4 |  | 200 | 200 | 2013-03-21
SH_I&C | SH_I&C | 60005654 | A | 44AT69002 | SM01 | NOx reading trending up to high limit | NOx reading trending up to high limit | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2013-04-07 |  | 4 | 1 | 4 |  | 9586 | 9586 | 2013-04-18
SH_I&C | SH_I&C | 60005654 | A | 44AT69002 | SM01 | NOx reading trending up to high limit | SCV 2A NOx analyser reading trending up | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2013-04-07 |  | 4 | 1 | 4 |  | 9586 | 9586 | 2013-04-18
SH_I&C | SH_I&C | 60005806 | A | 44AT69002 | SM01 | NOx Analyser off-spec completed 7/5/13 | NOx Analyser off-spec completed 7/5/13 | 4 | TECO CNF PRT NMAT PRC SETC | 2013-05-07 |  | 4 | 1 | 4 |  | 200 | 200 | 2013-05-11
SH_I&C | SH_I&C | 60006332 |  | 43AT69002 | SM01 | SCV 1H NOX ANALYSER FLAT LINING | SCV 1H NOX ANALYSER FLAT LINING | 2 | TECO CNF PRT NMAT PRC SETC | 2013-09-05 | 2013-09-05 | 2 | 1 | 2 |  | 100 | 100 | 2013-09-05
SH_I&C | SH_I&C | 60006413 |  | 43AT69002 | SM01 | Nox span check failure | Nox span check failure | 2 | TECO CNF PRT NMAT PRC SETC | 2013-09-27 | 2013-09-27 | 1 | 1 | 1 |  | 100 | 100 | 2013-09-27
SH_I&C | SH_I&C | 60006414 | A | 44AT69002 | SM01 | Nox span check failure | Nox span check failure | 2 | TECO CNF PRT NMAT PRC SETC | 2013-09-27 | 2013-09-27 | 2 | 1 | 2 |  | 100 | 100 | 2013-09-27
SH_I&C | SH_I&C | 60006672 |  | 43AT69002 | SM01 | SCV 1 A nox analyser calibration | SCV 1 A nox analyser calibration | 0 | TECO CNF GMPS MACM PPRT PRC SETC | 2013-11-18 | 2013-11-24 | 2 | 1 | 2 |  | 1468 | 1468 | 2014-02-12
SH_I&C | SH_I&C | 60006766 |  | 43AT69002 | SM01 | 43 AI 69002A SCV 1H NOX reading high | 43 AI 69002A SCV 1H NOX reading high | 2 | TECO CNF PRT NMAT PRC SETC | 2013-11-29 | 2013-12-05 | 0 | 0 | 0 |  | 100 | 100 | 2013-12-02
SH_I&C | SH_I&C | 60006902 |  | 43AT69002 | SM01 | SCV 1H NOx analyser requires calibration | SCV 1H NOx analyser requires calibration | 2 | TECO CNF PRT NMAT PRC SETC | 2014-01-13 | 2014-01-19 | 2 | 1 | 2 |  | 110 | 110 | 2014-01-16
SH_I&C | SH_I&C | 60006984 |  | 43AT69002 | SM01 | SCV 1H NOX req cal check | SCV 1H NOX req cal check | 2 | TECO CNF PRT NMAT PRC SETC | 2014-02-03 | 2014-02-09 | 2 | 1 | 2 |  | 110 | 110 | 2014-02-07
SH_I&C | SH_I&C | 60007020 |  | 43AT69002 | SM01 | SCV 1H NOx analyser requires calibration | SCV 1H NOx analyser requires calibration | 1 | TECO CNF PRT NMAT PRC SETC | 2014-02-10 |  | 1 | 1 | 1 |  | 55 | 55 | 2014-02-10
SH_I&C | SH_I&C | 60007045 |  | 43AT69002 | SM01 | Filter blocked move & repl JNOx analyser | Filter blocked move & repl JNOx analyser | 2 | TECO CNF PRT NMAT PRC SETC | 2014-02-13 |  | 2 | 1 | 2 |  | 110 | 110 | 2014-02-27
SH_I&C | SH_I&C | 60007096 |  | 43AT69002 | SM01 | SCV 1H NOX analyser fault | SCV 1H NOX analyser fault | 2 | TECO CNF GMPS MACM PPRT PRC SETC | 2014-02-25 | 2014-03-03 | 2 | 1 | 2 |  | 1136.29 | 1136.29 | 2014-02-27
SH_I&C | SH_I&C | 60007329 |  | 43AT69002 | SM01 | SCV 2A Nox ANALYSER READING LOW | SCV 2A Nox ANALYSER READING LOW | 1 | TECO CNF PRT NMAT PRC SETC | 2014-03-13 |  | 1 | 1 | 1 |  | 55 | 55 | 2014-03-17
SH_I&C | SH_I&C | 60007582 |  | 43AT69002 | SM01 | Nox ANALYSERS REQUIRE SPAN CALIBRATION | Nox ANALYSERS REQUIRE SPAN CALIBRATION | 2 | TECO CNF PRT MSCP NMAT PRC SETC | 2014-05-06 | 2014-05-06 | 2 | 1 | 2 |  | 110 | 110 | 2014-05-06
SH_I&C | SH_I&C | 60007734 |  | 43AT69002 | SM01 | SCV1H nox analyser flatlining | SCV1H nox analyser flatlining | 2 | TECO CNF PRT NMAT PRC SETC | 2014-06-16 | 2014-06-16 | 2 | 1 | 2 |  | 110 | 110 | 2014-06-17
SH_I&C | SH_I&C | 60007986 |  | 43AT69002 | SM01 | SCV 1H CEMS calibration | SCV 1H CEMS calibration | 2 | TECO CNF PRT NMAT PRC SETC | 2014-08-01 | 2014-08-07 | 2 | 1 | 2 |  | 110 | 110 | 2014-08-01
SH_I&C | SH_I&C | 60008701 | A | 44AT69002 | SM01 | (91) SCV 2A NOx analyser checks | (91) SCV 2A NOx analyser checks | 0 | TECO CNF PRT MSCP NMAT PRC SETC | 2014-12-09 | 2014-12-09 | 0 | 1 | 0 |  | 0 | 0 | 2014-12-09
SH_I&C | SH_I&C | 60008813 | A | 44AT69002 | SM01 | NOx analyser flow Tx failed | NOx analyser flow Tx failed | 2 | TECO CNF PRT MSCP NMAT PRC SETC | 2014-12-29 | 2014-12-29 | 2 | 1 | 2 |  | 110 | 110 | 2014-12-29
SH_I&C | SH_I&C | 60008995 | A | 44AT69002 | SM01 | (91) SCV 2A NOX flow analyser IOP | (91) SCV 2A NOX flow analyser IOP | 2 | TECO CNF PRT NMAT PRC SETC | 2015-01-27 | 2015-02-02 | 2 | 1 | 2 |  | 110 | 110 | 2015-01-27
SH_I&C | SH_I&C | 60009131 | A | 44AT69002 | SM01 | (65) Train 2 Nox analyser Flow off scale | (65) Train 2 Nox analyser Flow off scale | 2 | TECO CNF PRT NMAT PRC SETC | 2015-03-02 | 2015-03-02 | 2 | 1 | 2 |  | 110 | 110 | 2015-03-02
SH_I&C | SH_I&C | 60009430 | A | 44AT69002 | SM01 | Train 2 Nox Flow IOP High | Train 2 Nox Flow IOP High | 1 | TECO CNF PRT NMAT PRC SETC | 2015-05-03 |  | 1 | 1 | 1 |  | 55 | 55 | 2015-05-05
SH_I&C | SH_I&C | 60009447 | A | 44AT69002 | SM01 | (91) SCV 2A NOX ANALYSER BAD FLOW | (91) SCV 2A NOX ANALYSER BAD FLOW | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2015-05-09 | 2015-05-14 | 4 | 1 | 4 |  | 1489.53 | 1489.53 | 2015-05-08
SH_I&C | SH_I&C | 60010331 | A | 43AT69002 | SM01 | (44) SCV 1H NOX analyser failed | (44) SCV 1H NOX analyser failed | 2 | TECO CNF PRT NMAT PRC SETC | 2015-12-21 | 2015-12-23 | 2 | 1 | 2 |  | 110 | 110 | 2015-12-18
SH_I&C | SH_I&C | 60010338 | A | 44AT69002 | SM01 | SCV 2A Nox Analyser Flow | SCV 2A Nox Analyser Flow | 0 | TECO CNF PRT NMAT PRC SETC | 2015-12-20 | 2015-12-20 | 0 | 0 | 0 |  | 55 | 55 | 2015-12-21
SH_I&C | SH_ELECT | 60010338 | A | 44AT69002 | SM01 | SCV 2A Nox Analyser Flow | InvestigateTrace Heating | 1 | TECO CNF PRT NMAT PRC SETC | 2015-12-20 | 2015-12-20 | 0 | 0 | 0 |  | 55 | 55 | 2015-12-21
SH_I&C | SH_I&C | 60010339 | A | 43AT69002 | SM01 | Total Nox SCV 1H (66) | Total Nox SCV 1H (66) | 0 | TECO CNF PRT NMAT PRC SETC | 2015-12-20 | 2015-12-20 | 0 | 0 | 0 |  | 55 | 55 | 2015-12-21
SH_I&C | SH_ELECT | 60010339 | A | 43AT69002 | SM01 | Total Nox SCV 1H (66) | InvestigateTrace Heating | 1 | TECO CNF PRT NMAT PRC SETC | 2015-12-20 | 2015-12-20 | 0 | 0 | 0 |  | 55 | 55 | 2015-12-21
SH_I&C | SH_I&C | 60010425 | A | 44AT69002 | SM01 | (42) NOX ANALYSER SPURIOUS | (42) NOX ANALYSER SPURIOUS | 0 | TECO CNF PRT NMAT PRC SETC | 2016-01-13 | 2016-01-13 | 0 | 0 | 0 |  | 0 | 0 | 2016-01-13
SH_I&C | SH_I&C | 60010529 | A | 44AT69002 | SM01 | (42) Nox Flow | (42) Nox Flow | 2 | TECO CNF PRT NMAT PRC SETC | 2016-01-29 | 2016-02-05 | 2 | 1 | 2 |  | 110 | 110 | 2016-01-29
SH_I&C | SH_I&C | 60010655 | A | 44AT69002 | SM01 | (66) NOx Analyser failed | (66) NOx Analyser failed | 0 | TECO CNF PRT NMAT PRC SETC | 2016-02-18 | 2016-02-18 | 0 | 0 | 0 |  | 0 | 0 | 2016-02-18
SH_I&C | SH_I&C | 60010712 | A | 44AT69002 | SM01 | SCV 2A NOX Flow | SCV 2A NOX Flow | 0 | TECO CNF PRT NMAT PRC SETC | 2016-02-26 | 2016-03-03 | 0 | 0 | 0 |  | 0 | 0 | 2016-02-26
SH_I&C | SH_I&C | 60011091 | A | 43AT69002 | SM01 | 42 SCV 1H CEMS nox analyser IOP | 42 SCV 1H CEMS nox analyser IOP | 0 | TECO CNF PRT NMAT PRC SETC | 2016-05-08 | 2016-05-13 | 0 | 0 | 0 |  | 0 | 0 | 2016-05-09
SH_I&C | SH_I&C | 60011218 | A | 44AT69002 | SM01 | (66)Ph2 NOX analyser failed | (66)Ph2 NOX analyser failed | 0 | TECO CNF PRT NMAT PRC SETC | 2016-05-23 | 2016-05-30 | 0 | 0 | 0 |  | 0 | 0 | 2016-05-24
SH_I&C | SH_I&C | 60011471 | A | 44AT69002 | SM01 | (66)SCV 2A NOX analyser failed | (66)SCV 2A NOX analyser failed | 0 | TECO CNF PRT NMAT PRC SETC | 2016-07-06 | 2016-07-06 | 0 | 0 | 0 |  | 0 | 0 | 2016-07-06
SH_I&C | SH_I&C | 60011606 | A | 44AT69002 | SM01 | 21 SCV 2A NOX analyser reading 0 | 21 SCV 2A NOX analyser reading 0 | 2 | TECO CNF PRT NMAT PRC SETC | 2016-08-12 | 2016-08-12 | 0 | 0 | 0 |  | 110 | 110 | 2016-08-15
SH_I&C | SH_I&C | 60011630 | A | 44AT69002 | SM01 | (66) Analyser fault | (66) Analyser fault | 0 | TECO CNF PRT NMAT PRC SETC | 2016-08-17 | 2016-08-24 | 0 | 0 | 0 |  | 0 | 0 | 2016-08-17
SH_I&C | SH_I&C | 60011663 | A | 44AT69002 | SM01 | (42) NOX ANALYSER | (42) NOX ANALYSER | 0 | TECO CNF PRT NMAT PRC SETC | 2016-08-25 | 2016-09-05 | 0 | 0 | 0 |  | 0 | 0 | 2016-08-25
SH_I&C | SH_I&C | 60011690 | A | 44AT69002 | SM01 | (66) SCV-2A NOx analyser fault | (66) SCV-2A NOx analyser fault | 4.1 | TECO CNF PRT GMPS MACM PRC SETC | 2016-08-30 | 2016-08-30 | 0 | 0 | 0 |  | 10168.03 | 10168.03 | 2016-09-01
SH_I&C | SH_I&C | 60011696 | A | 43AT69002 | SM01 | (PF2017-05)Damaged Instrument Cable | Repair damaged instrument cable | 2 | TECO CNF PRT GMPS MACM PRC SETC | 2016-09-05 | 2017-05-30 | 8 | 2 | 16 |  | 165 | 165 | 2017-07-20
SH_I&C | SH_I&C | 60011789 | A | 43AT69002 | SM01 | (42) NOX ANALYSER FAULT | (42) NOX ANALYSER FAULT | 0 | TECO CNF PRT NMAT PRC SETC | 2016-09-22 | 2016-09-22 | 0 | 0 | 0 |  | 0 | 0 | 2016-09-23
SH_I&C | SH_I&C | 60011790 | A | 43AT69002 | SM01 | SCV 1H Nox Flow | SCV 1H Nox Flow | 0 | TECO CNF PRT GMPS MACM PRC SETC | 2016-09-22 | 2016-09-29 | 0 | 0 | 0 |  | 1349.34 | 1349.34 | 2016-09-22
SH_I&C | SH_I&C | 60012064 | A | 43AT69002 | SM01 | (72) NOX ANALYSER READING INCORRECTLY | (72) NOX ANALYSER READING INCORRECTLY | 4 | TECO CNF PRT NMAT PRC SETC | 2016-11-28 | 2016-11-28 | 0 | 0 | 0 |  | 220 | 220 | 2016-11-28
SH_I&C | SH_I&C | 60012100 | A | 44AT69002 | SM01 | (44) NOx flow Tx in IOP | (44) NOx flow Tx in IOP | 0 | TECO CNF PRT NMAT PRC SETC | 2016-12-07 | 2016-12-14 | 0 | 0 | 0 |  | 0 | 0 | 2016-12-07
SH_I&C | SH_I&C | 60012259 | A | 44AT69002 | SM01 | (44) NOx flow Tx in IOP | (44) NOx flow Tx in IOP | 2 | TECO CNF PRT NMAT PRC SETC | 2017-01-16 | 2017-01-16 | 0 | 0 | 0 |  | 110 | 110 | 2017-01-16
SH_I&C | SH_I&C | 60012295 | A | 43AT69002 | SM01 | (42) Analyser low flow | (42) Analyser low flow | 4 | TECO CNF PRT NMAT PRC SETC | 2017-01-21 | 2017-01-27 | 0 | 0 | 0 |  | 220 | 220 | 2017-01-23
SH_I&C | SH_I&C | 60012324 | A | 43AT69002 | SM01 | (PF2017-09)SCV 1H NOX Flow TX Moisture | Installation of drop legs | 2 | TECO CNF PRT GMPS MACM PRC SETC | 2017-04-27 | 2017-05-15 | 2 | 1 | 2 |  | 855.54 | 855.54 | 2017-04-27
SH_I&C | SH_I&C | 60012324 | A | 43AT69002 | SM01 | (PF2017-09)SCV 1H NOX Flow TX Moisture | Installation of 1/4 turn v/v on SCV 1H | 3 | TECO CNF PRT GMPS MACM PRC SETC | 2017-04-27 | 2017-05-15 | 1 | 1 | 1 |  | 855.54 | 855.54 | 2017-04-27
SH_I&C | SH_I&C | 60012324 | A | 43AT69002 | SM01 | (PF2017-09)SCV 1H NOX Flow TX Moisture | Installation of 1/4 turn v/v on SCV 2A | 2 | TECO CNF PRT GMPS MACM PRC SETC | 2017-04-27 | 2017-05-15 | 1 | 1 | 1 |  | 855.54 | 855.54 | 2017-04-27
SH_I&C | SH_I&C | 60012469 | A | 44AT69002 | SM01 | (42) JNOX On SCV 2A Poor Performance | Replace JNOX Convertor | 5 | TECO CNF PRT GMPS MACM PRC SETC | 2017-03-08 | 2017-04-23 | 2 | 2 | 4 |  | 5946.2 | 5946.2 | 2017-03-08
SH_I&C | SH_I&C | 60012605 | A | 44AT69002 | SM01 | (55)Low Flow | (55)Low Flow | 2 | TECO CNF PRT NMAT PRC SETC | 2017-03-21 | 2017-03-21 | 0 | 0 | 0 |  | 110 | 110 | 2017-03-21
SH_I&C | SH_I&C | 60012804 | A | 43AT69002 | SM01 | (42) NOX ANALYSER SCV 1H | (42) NOX ANALYSER SCV 1H | 4 | TECO CNF PRT NMAT PRC SETC | 2017-05-03 | 2017-05-03 | 0 | 0 | 0 |  | 220 | 220 | 2017-05-03
SH_I&C | SH_I&C | 60012901 | A | 43AT69002 | SM01 | (11) Install Instrument Air Into AH02 | Run instrument air line into AH02 | 0 | TECO CNF PRT GMPS MACM PRC SETC | 2018-03-05 | 2018-03-05 | 4 | 1 | 4 |  | -2.64 | -2.64 | 2018-02-28
SH_I&C | SH_I&C | 60013958 | A | 44AT69002 | SM01 | SAP SCV 2A Flow Temp Press O2 BAD | SAP SCV 2A Flow Temp Press O2 BAD | 1 | TECO CNF NMAT PRC SETC | 2018-01-22 | 2018-01-23 | 0 | 0 | 0 |  | 55 | 55 | 2018-01-22
SH_I&C | SH_I&C | 60013959 | A | 43AT69002 | SM01 | SCV1H & 2A Flow Temp Press O2 BAD | SCV1H & 2A Flow Temp Press O2 BAD | 1 | TECO CNF NMAT PRC SETC | 2018-01-22 | 2018-01-23 | 0 | 0 | 0 |  | 55 | 55 | 2018-01-22
SH_I&C | SH_I&C | 60014420 | A | 44AT69002 | SM01 | (43) Nox - QAL3 Calibration Failure | (43) Nox - QAL3 Calibration Failure | 2 | TECO CNF PRT NMAT PRC SETC | 2018-04-24 | 2018-06-19 | 2 | 1 | 2 |  | 110 | 110 | 2018-04-24
SH_I&C | SH_I&C | 60014839 | A | 43AT69002 | SM01 | (42) Nox analysers, Readings suspect. | (42) Nox analysers, Readings suspect. | 4 | TECO CNF PRT NMAT PRC SETC | 2018-08-23 | 2018-10-14 | 4 | 1 | 4 |  | 220 | 220 | 2018-08-17
SH_I&C | SH_I&C | 60014874 | A | 43AT69002 | SM01 | (42) Nox analyser auto calibration | (42) Nox analyser auto calibration | 4 | TECO CNF NMAT PRC SETC | 2018-08-30 | 2018-09-03 | 0 | 0 | 0 |  | 220 | 220 | 2018-08-30
SH_I&C | SH_I&C | 60015020 | A | 44AT69002 | SM01 | (66) Failed QAL3 SCV2A | (66) Failed QAL3 SCV2A | 1 | TECO CNF PRT NMAT PRC SETC | 2018-10-05 | 2018-12-01 | 1 | 1 | 1 |  | 55 | 55 | 2018-10-05
SH_I&C | SH_I&C | 60015021 | A | 43AT69002 | SM01 | (66) Failed QAL3 SCV1H | (66) Failed QAL3 SCV1H | 1 | TECO CNF PRT GMPS MACM PRC SETC | 2018-10-05 | 2018-12-01 | 1 | 1 | 1 |  | 423.31 | 423.31 | 2018-10-05
SH_I&C | SH_I&C | 60015158 | A | 44AT69002 | SM01 | (66) Failed QAL3 SCV2A 23.10.2018 | (66) Failed QAL3 SCV2A 23.10.2018 | 4 | TECO CNF PRT NMAT PRC SETC | 2018-10-24 | 2018-10-24 | 2 | 2 | 4 |  | 220 | 220 | 2018-10-27
SH_I&C | SH_I&C | 60015159 | A | 43AT69002 | SM01 | (66) Failed QAL3 SCV1H 22.10.2018 | (66) Failed QAL3 SCV1H 22.10.2018 | 4 | TECO CNF PRT NMAT PRC SETC | 2018-10-24 | 2018-10-24 | 0 | 0 | 0 |  | 220 | 220 | 2018-10-24
SH_I&C | SH_I&C | 60015402 | A | 44AT69002 | SM01 | (66) 44AT69002 - NOX Reading Erratic | 44AT69002 - NOX Reading Erratic | 0 | TECO CNF PRT GMPS MACM PRC SETC | 2018-12-19 | 2018-12-19 | 0 | 0 | 0 |  | 9942.53 | 9942.53 | 2018-12-21
SH_I&C | SH_I&C | 60015438 | A | 44AT69002 | SM01 | (21) SCV 2A NOX Analyser U/S | (21) SCV 2A NOX Analyser U/S | 0 | TECO CNF PRT NMAT PRC SETC | 2018-12-27 | 2019-02-20 | 0 | 0 | 0 |  | 0 | 0 | 2018-12-27
SH_I&C | SH_I&C | 60015765 | A | 44AT69002 | SM01 | (50) fail to operate | (50) fail to operate | 4 | TECO CNF PRT NMAT PRC SETC | 2019-03-03 | 2019-03-03 | 0 | 0 | 0 |  | 220 | 220 | 2019-03-04
SH_I&C | SH_I&C | 60015925 | A | 44AT69002 | SM01 | (PLND)(28) SCV 2A NOX Reading/Flow Low | Investigate Low NOX/Flow Reading | 2 | TECO CNF PRT NMAT PRC SETC | 2019-07-03 | 2019-08-17 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2019-07-03
SH_I&C | SH_I&C | 60016117 | A | 44AT69002 | SM01 | (36) faulty indication | (36) faulty indication on O2 Envirosoft | 2 | TECO CNF PRT NMAT PRC SETC | 2019-05-10 | 2019-05-10 | 2 | 1 | 2 | SCHD | 110 | 110 | 2019-05-14
SH_I&C | SH_I&C | 60016404 | A | 43AT69002 | SM01 | (42) Nox 1H faulty readings | (42) Nox 1H faulty readings | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2019-08-05 | 2019-09-07 | 2 | 2 | 4 | PLND SCHD | 11704 | 11704 | 2019-08-05
SH_I&C | SH_I&C | 60016407 | A | 44AT69002 | SM01 | (7) NOX sample line loose on stack | Position NOX line in cable tray.MEWP | 2 | TECO CNF PRT NMAT PRC SETC | 2019-09-11 | 2020-01-05 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2019-09-11
SH_I&C | SH_I&C | 60016521 | A | 43AT69002 | SM01 | (42) SCV 1H Nox Analyser Flow | Investigate/Repair Stack Flow TX | 1 | TECO CNF NMAT PRC SETC | 2019-08-09 | 2019-08-09 | 1 | 1 | 1 | SCHD | 165 | 165 | 2019-08-10
SH_I&C | SH_I&C | 60016521 | A | 43AT69002 | SM01 | (42) SCV 1H Nox Analyser Flow | Investigate/Repair Ultramat Flow Fault | 2 | TECO CNF NMAT PRC SETC | 2019-08-09 | 2019-08-09 | 2 | 1 | 2 | SCHD | 165 | 165 | 2019-08-10
SH_I&C | SH_I&C | 60016569 | A | 43AT69002 | SM01 | (42) NOx reading failed low | (42) NOx reading failed low | 1 | TECO CNF GMPS NMAT PRC SETC | 2019-08-14 | 2019-08-20 | 0 | 0 | 0 | INIT | 43.65 | 43.65 | 2019-08-14
SH_I&C | SH_I&C | 60016702 | A | 43AT69002 | SM01 | (42) NOX ANALYSER DRIFTING - CAL 3 REPOR | (42) NOX ANALYSER DRIFTING - CAL 3 REPOR | 0.5 | TECO CNF PRT NMAT PRC SETC | 2019-09-16 | 2019-09-20 | 0.5 | 1 | 0.5 | PLND SCHD | 27.5 | 27.5 | 2019-09-16
SH_I&C | SH_I&C | 60016708 | A | 43AT69002 | SM01 | (44) SCV 1H flue gas flow meter | (44) SCV 1H flue gas flow meter | 0 | CLSD CNF NMAT PRC SETC | 2019-09-17 | 2019-11-08 | 0 | 0 | 0 | ABDN | 0 | 0 | 2019-09-19
SH_I&C | SH_I&C | 60016726 | A | 43AT69002 | SM01 | (42) SCV 1H NoX analyser failed | (42) SCV 1H NoX analyser failed Call In | 4 | TECO CNF NMAT PPRT PRC SETC | 2019-09-17 | 2019-09-17 | 4 | 1 | 4 | PLND SCHD | 770 | 770 | 2019-09-19
SH_I&C | SH_I&C | 60016726 | A | 43AT69002 | SM01 | (42) SCV 1H NoX analyser failed | (42) SCV 1H NoX analyser failed | 6 | TECO CNF NMAT PPRT PRC SETC | 2019-09-17 | 2019-09-17 | 2 | 2 | 4 | PLND SCHD | 770 | 770 | 2019-09-19
SH_I&C | SH_I&C | 60016726 | A | 43AT69002 | SM01 | (42) SCV 1H NoX analyser failed | (42) SCV 1H NoX analyser failed | 4 | TECO CNF NMAT PPRT PRC SETC | 2019-09-17 | 2019-09-17 | 2 | 2 | 4 | PLND SCHD | 770 | 770 | 2019-09-19
SH_I&C | SH_I&C | 60016851 | A | 43AT69002 | SM01 | (42) NOX failed Qual 3 | (42) NOX failed Qual 3 | 2 | TECO CNF PRT GMPS MACM PRC SETC | 2019-10-28 | 2019-12-15 | 1 | 2 | 2 | PLND SCHD | 584 | 584 | 2019-10-28
SH_I&C | SH_I&C | 60016851 | A | 43AT69002 | SM01 | (42) NOX failed Qual 3 | (42) NOX failed Qual 3 | 8 | TECO CNF PRT GMPS MACM PRC SETC | 2019-10-28 | 2019-12-15 | 8 | 1 | 8 | PLND SCHD | 584 | 584 | 2019-10-28
SH_I&C | SH_VEND | 60016851 | A | 43AT69002 | SM01 | (42) NOX failed Qual 3 | (42) NOX failed Qual 3 | 8 | TECO CNF PRT GMPS MACM PRC SETC | 2019-10-28 | 2019-12-15 | 8 | 1 | 8 | PLND SCHD | 584 | 584 | 2019-10-28
SH_I&C | SH_I&C | 60017019 | A | 43AT69002 | SM01 | (42) Support NPL in AH02 for QAL2 test | Support NPL in AH02 for QAL2 test | 19.5 | TECO CNF PRT NMAT PRC SETC | 2019-12-09 | 2020-01-24 | 19.5 | 1 | 19.5 | PLND SCHD | 1072.5 | 1072.5 | 2019-12-11
SH_I&C | SH_VEND | 60017019 | A | 43AT69002 | SM01 | (42) Support NPL in AH02 for QAL2 test | NPL QAL2 functional test audit | 39 | TECO CNF PRT NMAT PRC SETC | 2019-12-09 | 2020-01-24 | 19.5 | 2 | 39 | PLND SCHD | 1072.5 | 1072.5 | 2019-12-11
SH_I&C | SH_I&C | 60017182 | A | 43AT69002 | SM01 | (28) nox analyser flow low | (28) nox analyser flow low | 0.5 | TECO CNF PRT NMAT PRC SETC | 2020-01-16 | 2020-03-12 | 0.5 | 1 | 0.5 | PLND SCHD | 27.5 | 27.5 | 2020-01-16
SH_I&C | SH_I&C | 60017227 | A | 43AT69002 | SM01 | (66) SCV1H NOX | (66) SCV1H NOX | 2 | TECO CNF NMAT PRC SETC | 2020-01-23 | 2020-01-23 | 0 | 0 | 0 | SCHD | 110 | 110 | 2020-01-23
SH_I&C | SH_I&C | 60017299 | A | 43AT69002 | SM01 | (66) SCV 1H NOX ANALYSER REGULATORY | (66) SCV 1H NOX ANALYSER REGULATORY | 2 | TECO CNF NMAT PRC SETC | 2020-02-12 | 2020-02-17 | 2 | 2 | 4 | PLND SCHD | 110 | 110 | 2020-02-11
SH_I&C | SH_I&C | 60017330 | A | 44AT69002 | SM01 | (66) NOx analyser drifted SCV 2A | (66) NOx analyser drifted SCV 2A | 0.5 | TECO CNF PRT NMAT PRC SETC | 2020-02-20 | 2020-04-18 | 0.5 | 1 | 0.5 | SCHD | 27.5 | 27.5 | 2020-02-20
SH_I&C | SH_I&C | 60017346 | A | 43AT69002 | SM01 | SCV 1H Flue gas flow erratic | SCV 1H Flue gas flow erratic | 1 | TECO CNF NMAT PRC SETC | 2020-02-24 | 2020-02-28 | 1 | 1 | 1 | SCHD | 55 | 55 | 2020-02-24
SH_I&C | SH_I&C | 60017383 | A | 44AT69002 | SM01 | Nox efficency low-Replace Jnox/Ultramat | Replace 44AT69002 (Jnox/Ultramat) | 4 | TECO CNF PRT GMPS MSPT PRC SETC | 2020-07-13 | 2020-08-31 | 4 | 1 | 4 | PLND SCHD | 15958 | 15958 | 2020-07-13
SH_I&C | SH_I&C | 60017383 | A | 44AT69002 | SM01 | Nox efficency low-Replace Jnox/Ultramat | Replace 44AT69002 JNox converter | 4 | TECO CNF PRT GMPS MSPT PRC SETC | 2020-07-13 | 2020-08-31 | 4 | 1 | 4 | PLND SCHD | 15958 | 15958 | 2020-07-13
SH_I&C | SH_I&C | 60017544 | A | 43AT69002 | SM01 | SCV1H - Nox Analyser failed | SCV1H - Nox Analyser failed | 2 | TECO CNF NMAT PRC SETC | 2020-04-29 | 2020-06-28 | 0 | 0 | 0 | SCHD | 110 | 110 | 2020-04-29
SH_I&C | SH_I&C | 60017565 | A | 43AT69002 | SM01 | P2 SCV 1H NOX analyser | P2 SCV 1H NOX analyser | 3 | TECO CNF NMAT PRC SETC | 2020-05-04 | 2020-05-09 | 0 | 0 | 0 | SCHD | 165 | 165 | 2020-05-04
SH_I&C | SH_I&C | 60017569 | A | 44AT69002 | SM01 | SCV 2A Nox Analyser fault | Investigate/repair Nox Analyser fault | 0 | CLSD CNF NMAT PRC SETC | 2020-06-16 | 2020-07-01 | 2 | 1 | 2 | ABDN | 0 | 0 | 2020-05-15
SH_I&C | SH_I&C | 60017585 | A | 43AT69002 | SM01 | Faulty Nox analsyer one SCV 1H | Change faulty Analyser 43AT69002 | 6.5 | TECO CNF GMPS MACM PRC SETC | 2020-06-02 | 2020-07-05 | 6.5 | 1 | 6.5 | PLND SCHD | 12345.5 | 12345.5 | 2020-05-30
SH_I&C | SH_I&C | 60017986 | A | 43AT69002 | SM01 | SCV1H nox analyser in fault | Investigate & Repair SCV1H nox analyser | 8 | TECO CNF NMAT PRC SETC | 2020-08-23 | 2020-10-14 | 4 | 2 | 8 | PLND SCHD | 440 | 440 | 2020-08-17
SH_I&C | SH_I&C | 60018004 | A | 43AT69002 | SM01 | NOx analyser reading zero | Repair and calibrate analyser | 8 | TECO CNF NMAT PRC SETC | 2020-08-21 | 2020-08-28 | 4 | 2 | 8 | PLND SCHD | 440 | 440 | 2020-08-21
SH_I&C | SH_I&C | 60018027 | A | 43AT69002 | SM01 | SCV 1H NOX ANALYSER 43AI69002A FAILED | Investigate NOX fault | 3.5 | TECO CNF NMAT PRC SETC | 2020-08-26 | 2020-10-25 | 3.5 | 1 | 3.5 | PLND SCHD | 192.5 | 192.5 | 2020-08-26
SH_I&C | SH_I&C | 60018077 | A | 43AT69002 | SM01 | NOX ANALYSER LOW READING / FAILED | Investigate/Repair NOX Fault | 2 | TECO CNF PRT GMPS MACM PRC SETC | 2020-09-10 | 2020-09-16 | 2 | 1 | 2 | PLND SCHD | 12329.23 | 12329.23 | 2020-09-09
SH_I&C | SH_I&C | 60018218 | A | 43AT69002 | SM01 | Request Zero CAL NOx ANALYSER SCV 1H | Recalibrate 43AT69002 | 1 | TECO CNF PRT NMAT PRC SETC | 2020-10-19 | 2020-12-14 | 1 | 1 | 1 | PLND SCHD | 55 | 55 | 2020-10-19
SH_I&C | SH_I&C | 60018361 | A | 43AT69002 | SM01 | O2 analyser did not perform zero check | O2 analyser fault/zero check | 1 | TECO CNF NMAT PRC SETC | 2020-12-10 | 2021-02-07 | 1 | 1 | 1 | SCHD | 55 | 55 | 2020-12-10
SH_I&C | SH_I&C | 60018594 | A | 43AT69002 | SM01 | SCV 1H NOX ANALYSER FAULT | INVESTIGATE SCV 1H NOX ANALYSER | 2 | TECO CNF NMAT PRC SETC | 2021-02-08 | 2021-04-09 | 1 | 2 | 2 | PLND SCHD | 110 | 110 | 2021-02-08
SH_I&C | SH_I&C | 60018606 | A | 43AT69002 | SM01 | SCV 1H envirosoft software U/S | 43AT69002 envirosoft software U/S | 16 | TECO CNF NMAT PRC SETC | 2021-02-10 | 2021-02-17 | 4 | 2 | 8 | PLND SCHD | 880 | 880 | 2021-02-10
SH_I&C | SH_I&C | 60018608 | A | 44AT69002 | SM01 | SCV2A NOX analyser IOP | NOX analyser IOP SCV2A | 16 | TECO CNF PRT GMPS MACM PRC SETC | 2021-02-10 | 2021-02-16 | 4 | 2 | 8 | PLND SCHD | 12868 | 12868 | 2021-02-10
SH_I&C | SH_I&C | 60018648 | A | 43AT69002 | SM01 | SCV 1H NOX erratic high readings | Check NOx At & permeate injection rate | 12 | TECO CNF PRT NMAT PRC SETC | 2021-03-12 | 2021-04-20 | 3 | 1 | 3 | PLND SCHD | 660 | 660 | 2021-03-10
SH_I&C | SH_I&C | 60018986 | A | 44AT69002 | SM01 | SCV 2A nox analyser reading low | Investiagte low reading nox analyser | 1 | TECO CNF NMAT PRC SETC | 2021-05-10 | 2021-07-09 | 1 | 1 | 1 | PLND SCHD | 55 | 55 | 2021-05-10
SH_I&C | SH_I&C | 60018992 | A | 44AT69002 | SM01 | Nox 2A chiller/ pumps & pipework suspect | Replace pump & chiller on Nox 2A | 8 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-07-28 | 2021-09-13 | 4 | 2 | 8 | PLND SCHD | 4945.64 | 4945.64 | 2021-07-29
SH_I&C | SH_I&C | 60019003 | A | 43AT69002 | SM01 | SCV 1H NOX NOT READING | Recalibrate SCV 1H NOX | 1 | TECO CNF NMAT PRC SETC | 2021-05-13 | 2021-07-11 | 1 | 1 | 1 | PLND SCHD | 55 | 55 | 2021-05-13
SH_I&C | SH_I&C | 60019012 | A | 43AT69002 | SM01 | SCV 1H NOX analyser reading zero | Investigate/repair 43AT69002 Analyser | 4 | TECO CNF NMAT PRC SETC | 2021-05-14 | 2021-07-13 | 2 | 2 | 4 | PLND SCHD | 220 | 220 | 2021-05-14
SH_I&C | SH_I&C | 60019028 | A | 43AT69002 | SM01 | Replace pump & chiller on Nox analyser | Carryout Nox 1H Chiller/Pump replacement | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2021-08-24 | 2021-08-24 | 4 | 2 | 8 | PLND SCHD | 5137.72 | 5137.72 | 2021-08-25
SH_I&C | SH_I&C | 60019030 | A | 44AT69002 | SM01 | NOx analyser failed | Investigate/repair Faulty Nox Analyser | 4 | TECO CNF NMAT PRC SETC | 2021-05-20 | 2021-07-18 | 4 | 2 | 8 | PLND SCHD | 220 | 220 | 2021-05-20
SH_I&C | SH_I&C | 60019039 | A | 43AT69002 | SM01 | SCV 1H NOX ANALYSER no readings | Investigate SCV 1H NOX ANALYSER | 1 | TECO CNF NMAT PRC SETC | 2021-05-24 | 2021-07-22 | 1 | 1 | 1 | PLND SCHD | 55 | 55 | 2021-05-24
SH_I&C | SH_I&C | 60019076 | A | 44AT69002 | SM01 | 44AI69002C NOX FLOW ANALYSER | Investigate/repair loss in readings | 8 | TECO CNF PRT NMAT PRC SETC | 2021-06-08 | 2021-07-28 | 4 | 2 | 8 | PLND SCHD | 440 | 440 | 2021-06-09
SH_I&C | SH_I&C | 60019096 | A | 43AT69002 | SM01 | SCV 1H NOX value failed to zero | Recalibrate SCV 1H NOX | 2 | TECO CNF NMAT PRC SETC | 2021-06-09 | 2021-08-06 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-09
SH_I&C | SH_I&C | 60019201 | A | 43AT69002 | SM01 | SCV 1-H & 2A Common SW/Control issues | Carry out fault finding on 43AT69002 | 8 | TECO CNF NMAT PRC SETC | 2021-07-19 | 2021-10-17 | 4 | 2 | 8 | PLND SCHD | 440 | 440 | 2021-07-22
SH_I&C | SH_DCS | 60019201 | A | 43AT69002 | SM01 | SCV 1-H & 2A Common SW/Control issues | Assist with common control issues | 4 | TECO CNF NMAT PRC SETC | 2021-07-19 | 2021-10-17 | 4 | 1 | 4 | PLND SCHD | 440 | 440 | 2021-07-22
SH_I&C | SH_I&C | 60019528 | A | 44AT69002 | SM01 | Overhaul and replace JNOX | Replace JNOX & cartridge | 4 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-10-27 | 2022-03-21 | 4 | 1 | 4 | PLND SCHD | 231.07 | 231.07 | 2021-10-26
SH_I&C | SH_I&C | 60019537 | A | 44AT69002 | SM01 | Investigate and repair analyser fault | NOx Investigate & repair analyser fault | 5 | TECO CNF PRT GMPS MACM PRC SETC | 2021-10-04 | 2021-11-28 | 2.5 | 2 | 5 | PLND SCHD | 275 | 275 | 2021-10-04
SH_I&C | SH_I&C | 60019590 | A | 44AT69002 | SM01 | Nox SCV 2A moisture damage | Carry out repairs to Analyser | 8 | TECO CNF GMPS MACM PRC SETC | 2021-11-08 | 2021-12-13 | 8 | 1 | 8 | PLND SCHD | 440 | 440 | 2021-10-27
SH_I&C | SH_I&C | 60019645 | A | 44AT69002 | SM01 | 2A NOX analyser zero check function u/s | Investigate 2A NOX analyser zero | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2021-11-03 | 2021-12-28 | 2 | 2 | 4 | PLND SCHD | 245 | 245 | 2021-11-03
SH_I&C | SH_I&C | 60019673 | A | 43AT69002 | SM01 | Investigate high cal gas usage | Carry out cal gas usage fault | 1 | TECO CNF PRT NMAT PRC SETC | 2021-12-02 | 2022-01-07 | 4 | 1 | 4 | PLND SCHD | 55 | 55 | 2021-12-02
SH_I&C | SH_I&C | 60019722 | A | 43AT69002 | SM01 | SCV 1H NOX analyser u/s | Investigate SCV 1H NOX analyser u/s | 0.5 | TECO CNF NMAT PRC SETC | 2021-11-17 | 2021-11-23 | 0.5 | 1 | 0.5 | PLND SCHD | 27.5 | 27.5 | 2021-11-17
SH_I&C | SH_I&C | 70000815 |  | 43AT69002 | SM02 | NOX Analyser Train 1 calibration |  | 0 | TECO CNF PRT MANC NMAT PRC SETC | 2009-05-13 | 2009-05-13 | 0 | 0 | 0 |  | 0 | 0 | 2009-11-23
SH_I&C | SH_I&C | 70005061 |  | 43AT69002 | SM02 | Calibrations of Nox Analysers | Calibrations of Nox Analysers | 1 | TECO CNF MANC NMAT PRC SETC | 2010-06-04 | 2010-06-04 | 1 | 1 | 1 |  | 0 | 0 | 2010-06-04
SH_I&C | SH_I&C | 70005062 |  | 43AT69002 | SM02 | Calibrations of Nox Analysers | Calibrations of Nox Analysers | 1 | TECO CNF MANC NMAT PRC SETC | 2010-01-26 | 2010-01-26 | 1 | 1 | 1 |  | 0 | 0 | 2010-01-26
SH_I&C | SH_I&C | 70005184 | A | 44AT69002 | SM02 | Nox Analyser Train 2 Calibration | Nox Analyser Train 2 Calibration | 0 | TECO CNF MANC NMAT PRC SETC | 2010-01-26 | 2010-01-26 | 2 | 1 | 2 |  | 0 | 0 | 2010-01-26
SH_I&C | SH_I&C | 70005185 | A | 44AT69002 | SM02 | Nox Analyser Calibration | Nox Analyser Calibration | 0 | TECO CNF MANC NMAT PRC SETC | 2010-06-04 | 2010-06-04 | 2 | 1 | 2 |  | 0 | 0 | 2010-06-04
SH_I&C | SH_I&C | 70010914 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT MANC NMAT PRC SETC | 2012-05-18 | 2012-05-18 | 8 | 1 | 8 |  | 400 | 400 | 2012-05-16
SH_I&C | SH_I&C | 70010914 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 0 | TECO CNF PRT MANC NMAT PRC SETC | 2012-05-18 | 2012-05-18 | 4 | 1 | 4 |  | 400 | 400 | 2012-05-16
SH_I&C | SH_I&C | 70010915 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF GMPS MANC PPRT PRC SETC | 2012-05-14 | 2012-05-14 | 4 | 1 | 4 |  | 9621.8 | 9621.8 | 2012-05-17
SH_I&C | SH_I&C | 70011490 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2012-11-07 | 2012-11-07 | 4 | 1 | 4 |  | 846.98 | 846.98 | 2012-11-07
SH_I&C | SH_I&C | 70011491 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2012-11-08 | 2012-11-08 | 4 | 1 | 4 |  | 846.98 | 846.98 | 2012-11-07
SH_I&C | SH_I&C | 70011566 |  | 43AT69002 | SM02 | Calibrate 43PT69002/43FT69002/43TT69002 | Calibrate 43PT69002/43FT69002/43TT69002 | 4 | TECO CNF PRT NMAT PRC SETC | 2012-05-16 | 2012-05-16 | 4 | 1 | 4 |  | 200 | 200 | 2012-05-17
SH_I&C | SH_I&C | 70011567 | A | 44AT69002 | SM02 | Calibrate 44PT69002/44FT/69002/44TT69002 | Calibrate 44PT69002/44FT/69002/44TT69002 | 4 | TECO CNF PRT NMAT PRC SETC | 2012-05-16 | 2012-05-16 | 4 | 1 | 4 |  | 200 | 200 | 2012-05-17
SH_I&C | SH_I&C | 70013763 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF GMPS MSPT PPRT PRC SETC | 2013-05-01 | 2013-05-01 | 8 | 1 | 8 |  | 3906 | 3906 | 2013-05-01
SH_I&C | SH_I&C | 70013763 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | Replace jnox convertors | 0 | TECO CNF GMPS MSPT PPRT PRC SETC | 2013-05-01 | 2013-05-01 | 0 | 0 | 0 |  | 3906 | 3906 | 2013-05-01
SH_I&C | SH_I&C | 70013764 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT GMPS MSPT PRC SETC | 2013-05-02 | 2013-05-02 | 8 | 1 | 8 |  | 792.9 | 792.9 | 2013-05-03
SH_I&C | SH_I&C | 70013764 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | Replace Solenoid Valve | 0 | TECO CNF PRT GMPS MSPT PRC SETC | 2013-05-02 | 2013-05-02 | 0 | 0 | 0 |  | 792.9 | 792.9 | 2013-05-03
SH_I&C | SH_I&C | 70016484 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT NMAT PRC SETC | 2013-11-21 | 2013-11-21 | 8 | 1 | 8 |  | 400 | 400 | 2013-11-28
SH_I&C | SH_I&C | 70016484 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | Replace jnox converters | 0 | TECO CNF PRT NMAT PRC SETC | 2013-11-21 | 2013-11-21 | 0 | 0 | 0 |  | 400 | 400 | 2013-11-28
SH_I&C | SH_I&C | 70016485 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT NMAT PRC SETC | 2013-11-22 | 2013-11-22 | 8 | 1 | 8 |  | 440 | 440 | 2013-11-21
SH_I&C | SH_I&C | 70019008 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2014-05-01 | 2014-05-01 | 4 | 1 | 4 |  | 445.93 | 445.93 | 2014-05-20
SH_I&C | SH_I&C | 70019009 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2014-05-01 | 2014-05-01 | 4 | 1 | 4 |  | 5160 | 5160 | 2014-05-21
SH_I&C | SH_I&C | 70021761 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF PRT CSER NMAT PRC SETC | 2015-01-06 | 2015-01-06 | 4 | 1 | 4 |  | 220 | 220 | 2015-01-06
SH_I&C | SH_I&C | 70021762 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 6 | TECO CNF PRT GMPS MACM PRC SETC | 2015-01-07 | 2015-01-07 | 6 | 1 | 6 |  | 4445.58 | 4445.58 | 2015-01-07
SH_I&C | SH_I&C | 70024249 |  | 43AT69002 | SM02 | Train 1 NOX maintenance/calibration | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF NMAT PPRT PRC SETC | 2015-08-18 | 2015-08-18 | 4 | 1 | 4 |  | 220 | 220 | 2015-08-18
SH_I&C | SH_VEND | 70024249 |  | 43AT69002 | SM02 | Train 1 NOX maintenance/calibration | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF NMAT PPRT PRC SETC | 2015-08-18 | 2015-08-18 | 4 | 1 | 4 |  | 220 | 220 | 2015-08-18
SH_I&C | SH_I&C | 70024250 | A | 44AT69002 | SM02 | Train 2 NOX maintenance/calibration | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF NMAT PPRT PRC SETC | 2015-08-19 | 2015-08-19 | 4 | 1 | 4 |  | 220 | 220 | 2015-08-19
SH_I&C | SH_VEND | 70024250 | A | 44AT69002 | SM02 | Train 2 NOX maintenance/calibration | 6 Monthly Nox Analyser Calibration | 4 | TECO CNF NMAT PPRT PRC SETC | 2015-08-19 | 2015-08-19 | 4 | 1 | 4 |  | 220 | 220 | 2015-08-19
SH_I&C | SH_I&C | 70028433 |  | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Vendor) | 4 | TECO CNF PRT NMAT PRC SETC | 2016-03-01 | 2016-03-01 | 4 | 1 | 4 |  | 220 | 220 | 2016-03-02
SH_I&C | SH_I&C | 70028434 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Vendor) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2016-03-02 | 2016-03-02 | 4 | 1 | 4 |  | 934.49 | 934.49 | 2016-03-02
SH_I&C | SH_I&C | 70032382 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT GMPS MACM PRC SETC | 2016-08-25 | 2016-08-25 | 8 | 1 | 8 |  | 783.99 | 783.99 | 2016-08-25
SH_I&C | SH_VEND | 70032382 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT GMPS MACM PRC SETC | 2016-08-25 | 2016-08-25 | 8 | 1 | 8 |  | 783.99 | 783.99 | 2016-08-25
SH_I&C | SH_I&C | 70032383 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 5.5 | TECO CNF PRT GMPS MACM PRC SETC | 2016-08-26 | 2016-08-26 | 8 | 1 | 8 |  | 496.16 | 496.16 | 2016-08-26
SH_I&C | SH_VEND | 70032383 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6 Monthly Nox Analyser Calibration | 8 | TECO CNF PRT GMPS MACM PRC SETC | 2016-08-26 | 2016-08-26 | 8 | 1 | 8 |  | 496.16 | 496.16 | 2016-08-26
SH_I&C | SH_I&C | 70034388 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2017-02-22 | 2017-02-22 | 4 | 1 | 4 |  | 220 | 220 | 2017-02-22
SH_I&C | SH_VEND | 70034388 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2017-02-22 | 2017-02-22 | 4 | 1 | 4 |  | 220 | 220 | 2017-02-22
SH_I&C | SH_I&C | 70034389 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2017-02-22 | 2017-02-23 | 4 | 1 | 4 |  | 220 | 220 | 2017-02-22
SH_I&C | SH_VEND | 70034389 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2017-02-22 | 2017-02-23 | 4 | 1 | 4 |  | 220 | 220 | 2017-02-22
SH_I&C | SH_I&C | 70036592 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2017-08-24 | 2017-08-31 | 4 | 1 | 4 |  | 5064 | 5064 | 2017-08-24
SH_I&C | SH_VEND | 70036592 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2017-08-24 | 2017-08-31 | 4 | 1 | 4 |  | 5064 | 5064 | 2017-08-24
SH_I&C | SH_I&C | 70036593 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT MSCP NMAT PRC SETC | 2017-08-24 | 2017-08-31 | 4 | 1 | 4 |  | 220 | 220 | 2017-08-24
SH_I&C | SH_VEND | 70036593 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT MSCP NMAT PRC SETC | 2017-08-24 | 2017-08-31 | 4 | 1 | 4 |  | 220 | 220 | 2017-08-24
SH_I&C | SH_I&C | 70038911 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 2.5 | TECO CNF PRT GMPS MACM PRC SETC | 2018-02-20 | 2018-03-31 | 4 | 1 | 4 |  | 144 | 144 | 2018-02-21
SH_I&C | SH_VEND | 70038911 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 3 | TECO CNF PRT GMPS MACM PRC SETC | 2018-02-20 | 2018-03-31 | 4 | 1 | 4 |  | 144 | 144 | 2018-02-21
SH_I&C | SH_I&C | 70038912 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 2.5 | TECO CNF PRT NMAT PRC SETC | 2018-02-20 | 2018-03-10 | 4 | 1 | 4 |  | 137.5 | 137.5 | 2018-02-21
SH_I&C | SH_VEND | 70038912 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 3 | TECO CNF PRT NMAT PRC SETC | 2018-02-20 | 2018-03-10 | 4 | 1 | 4 |  | 137.5 | 137.5 | 2018-02-21
SH_I&C | SH_I&C | 70040862 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2018-09-13 | 2018-09-21 | 4 | 1 | 4 |  | 220 | 220 | 2018-09-13
SH_I&C | SH_VEND | 70040862 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2018-09-13 | 2018-09-21 | 4 | 1 | 4 |  | 220 | 220 | 2018-09-13
SH_I&C | SH_I&C | 70040863 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 6 | TECO CNF PRT NMAT PRC SETC | 2018-09-13 | 2018-09-21 | 4 | 1 | 4 |  | 330 | 330 | 2018-09-13
SH_I&C | SH_VEND | 70040863 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2018-09-13 | 2018-09-21 | 4 | 1 | 4 |  | 330 | 330 | 2018-09-13
SH_I&C | SH_I&C | 70043103 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2019-03-05 | 2019-03-13 | 4 | 1 | 4 |  | 220 | 220 | 2019-03-05
SH_I&C | SH_VEND | 70043103 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2019-03-05 | 2019-03-13 | 4 | 1 | 4 |  | 220 | 220 | 2019-03-05
SH_I&C | SH_I&C | 70043104 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2019-03-05 | 2019-03-13 | 4 | 1 | 4 |  | 220 | 220 | 2019-03-05
SH_I&C | SH_VEND | 70043104 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2019-03-05 | 2019-03-13 | 4 | 1 | 4 |  | 220 | 220 | 2019-03-05
SH_I&C | SH_I&C | 70045302 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT NMAT PRC SETC | 2019-09-03 | 2019-09-05 | 4 | 1 | 4 | PLND SCHD | 220 | 220 | 2019-09-03
SH_I&C | SH_VEND | 70045302 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 2.5 | TECO CNF PRT NMAT PRC SETC | 2019-09-03 | 2019-09-05 | 4 | 1 | 4 | PLND SCHD | 220 | 220 | 2019-09-03
SH_I&C | SH_I&C | 70045303 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MSPT PRC SETC | 2019-09-03 | 2019-09-05 | 4 | 1 | 4 | PLND SCHD | 4671.33 | 4671.33 | 2019-09-03
SH_I&C | SH_VEND | 70045303 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 2.5 | TECO CNF PRT GMPS MSPT PRC SETC | 2019-09-03 | 2019-09-05 | 4 | 1 | 4 | PLND SCHD | 4671.33 | 4671.33 | 2019-09-03
SH_I&C | SH_I&C | 70047351 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maint (R) | 6M Nox Analyser Calibration (Orbital) | 3.5 | TECO CNF PRT GMPS MACM PRC SETC | 2020-03-03 | 2020-03-03 | 3.5 | 1 | 3.5 | PLND SCHD | 5185.87 | 5185.87 | 2020-03-03
SH_I&C | SH_VEND | 70047351 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maint (R) | 6M Nox Analyser Calibration (Orbital) | 3.5 | TECO CNF PRT GMPS MACM PRC SETC | 2020-03-03 | 2020-03-03 | 3.5 | 1 | 3.5 | PLND SCHD | 5185.87 | 5185.87 | 2020-03-03
SH_I&C | SH_I&C | 70047352 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Main (R) | 6M Nox Analyser Calibration (Orbital) | 3.5 | TECO CNF PRT NMAT PRC SETC | 2020-03-03 | 2020-03-03 | 3.5 | 1 | 3.5 | PLND SCHD | 192.5 | 192.5 | 2020-03-03
SH_I&C | SH_VEND | 70047352 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Main (R) | 6M Nox Analyser Calibration (Orbital) | 3.5 | TECO CNF PRT NMAT PRC SETC | 2020-03-03 | 2020-03-03 | 3.5 | 1 | 3.5 | PLND SCHD | 192.5 | 192.5 | 2020-03-03
SH_I&C | SH_VEND | 70048956 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | Vendor Assistance | 6.5 | TECO CNF PRT NMAT PRC SETC | 2020-09-14 | 2020-09-30 | 6.5 | 1 | 6.5 | PLND SCHD | 357.5 | 357.5 | 2020-09-14
SH_I&C | SH_I&C | 70048956 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | 5Y QAL2 Function test audit | 6.5 | TECO CNF PRT NMAT PRC SETC | 2020-09-14 | 2020-09-30 | 6.5 | 1 | 6.5 | PLND SCHD | 357.5 | 357.5 | 2020-09-14
SH_I&C | SH_VEND | 70048957 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Vendor Assistance | 6.5 | TECO CNF PRT NMAT PRC SETC | 2020-09-15 | 2020-09-30 | 6.5 | 1 | 6.5 | PLND SCHD | 357.5 | 357.5 | 2020-09-15
SH_I&C | SH_I&C | 70048957 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | 5Y QAL2 Function test audit | 6.5 | TECO CNF PRT NMAT PRC SETC | 2020-09-15 | 2020-09-30 | 6.5 | 1 | 6.5 | PLND SCHD | 357.5 | 357.5 | 2020-09-15
SH_I&C | SH_I&C | 70049965 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | Annual Surveillance Test | 0 | TECO CNF PRT NMAT PRC SETC | 2020-09-14 | 2020-09-14 | 0 | 1 | 0 | PLND SCHD | 0 | 0 | 2020-09-04
SH_I&C | SH_VEND | 70049965 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | Vendor Assistance | 0 | TECO CNF PRT NMAT PRC SETC | 2020-09-14 | 2020-09-14 | 0 | 1 | 0 | PLND SCHD | 0 | 0 | 2020-09-04
SH_I&C | SH_I&C | 70049966 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Annual Surveillance Test | 0 | TECO CNF PRT NMAT PRC SETC | 2020-09-15 | 2020-09-15 | 0 | 1 | 0 | PLND SCHD | 0 | 0 | 2020-09-04
SH_I&C | SH_VEND | 70049966 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Vendor Assistance | 0 | TECO CNF PRT NMAT PRC SETC | 2020-09-15 | 2020-09-15 | 0 | 1 | 0 | PLND SCHD | 0 | 0 | 2020-09-04
SH_I&C | SH_I&C | 70050098 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 8 | TECO CNF PRT NMAT PRC SETC | 2020-09-02 | 2020-09-03 | 3.5 | 1 | 8 | PLND SCHD | 440 | 440 | 2020-09-02
SH_I&C | SH_VEND | 70050098 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 8 | TECO CNF PRT NMAT PRC SETC | 2020-09-02 | 2020-09-03 | 3.5 | 1 | 8 | PLND SCHD | 440 | 440 | 2020-09-02
SH_I&C | SH_I&C | 70050099 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 8 | TECO CNF PRT NMAT PRC SETC | 2020-09-02 | 2020-09-03 | 3.5 | 1 | 8 | PLND SCHD | 440 | 440 | 2020-09-02
SH_I&C | SH_VEND | 70050099 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 8 | TECO CNF PRT NMAT PRC SETC | 2020-09-02 | 2020-09-03 | 3.5 | 1 | 8 | PLND SCHD | 440 | 440 | 2020-09-02
SH_I&C | SH_I&C | 70051357 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2021-03-02 | 2021-03-31 | 4 | 1 | 4 | PLND SCHD | 12089.04 | 12089.04 | 2021-03-02
SH_I&C | SH_VEND | 70051357 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2021-03-02 | 2021-03-31 | 4 | 1 | 4 | PLND SCHD | 12089.04 | 12089.04 | 2021-03-02
SH_I&C | SH_I&C | 70051358 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2021-03-02 | 2021-03-31 | 4 | 1 | 4 | PLND SCHD | 12089.04 | 12089.04 | 2021-03-02
SH_I&C | SH_VEND | 70051358 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF PRT GMPS MACM PRC SETC | 2021-03-02 | 2021-03-31 | 4 | 1 | 4 | PLND SCHD | 12089.04 | 12089.04 | 2021-03-02
SH_I&C | SH_I&C | 70055078 | A | 43AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 0 | CLSD CNF NMAT PRC SETC | 2021-03-01 | 2021-03-28 | 0 | 2 | 0 | ABDN | 0 | 0 | 2021-02-22
SH_I&C | SH_I&C | 70055079 | A | 43AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF PRT NMAT PRC SETC | 2021-03-12 | 2021-03-28 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-03-12
SH_I&C | SH_I&C | 70055080 | A | 43AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3 | TECO CNF NMAT PRC SETC | 2021-03-20 | 2021-03-21 | 1.6 | 2 | 3.2 | PLND SCHD | 165 | 165 | 2021-03-19
SH_I&C | SH_I&C | 70055081 | A | 43AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-03-23 | 2021-03-28 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-03-23
SH_I&C | SH_I&C | 70055082 | A | 43AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-03-31 | 2021-03-31 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-03-31
SH_I&C | SH_I&C | 70055083 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-04-05 | 2021-04-05 | 1.6 | 2 | 3.2 | ABDN | 176 | 176 | 2021-04-14
SH_I&C | SH_I&C | 70055084 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-04-12 | 2021-04-12 | 1.6 | 2 | 3.2 | ABDN | 176 | 176 | 2021-04-14
SH_I&C | SH_I&C | 70055085 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF PRT NMAT PRC SETC | 2021-04-22 | 2021-04-23 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-04-22
SH_I&C | SH_I&C | 70055086 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-04-28 | 2021-04-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-04-28
SH_I&C | SH_I&C | 70055087 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 1 | TECO CNF NMAT PRC SETC | 2021-05-04 | 2021-05-31 | 2 | 1 | 2 | PLND SCHD | 55 | 55 | 2021-05-04
SH_I&C | SH_I&C | 70055088 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-05-10 | 2021-05-16 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-11
SH_I&C | SH_I&C | 70055089 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-05-17 | 2021-05-17 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-17
SH_I&C | SH_I&C | 70055090 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-05-26 | 2021-05-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-26
SH_I&C | SH_I&C | 70055091 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-06-01 | 2021-06-06 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-01
SH_I&C | SH_I&C | 70055092 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-06-09 | 2021-06-13 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-09
SH_I&C | SH_I&C | 70055093 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-06-14 | 2021-06-20 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-15
SH_I&C | SH_I&C | 70055094 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-06-21 | 2021-06-21 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-21
SH_I&C | SH_I&C | 70055095 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-06-28 | 2021-06-28 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-28
SH_I&C | SH_I&C | 70055096 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-07-05 | 2021-07-05 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-05
SH_I&C | SH_I&C | 70055097 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-07-13 | 2021-07-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-13
SH_I&C | SH_I&C | 70055098 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-07-19 | 2021-07-25 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-19
SH_I&C | SH_I&C | 70055099 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-07-26 | 2021-07-26 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-26
SH_I&C | SH_I&C | 70055100 | A | 44AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 0 | CLSD CNF NMAT PRC SETC | 2021-03-01 | 2021-03-30 | 0 | 2 | 0 | ABDN | 0 | 0 | 2021-02-22
SH_I&C | SH_I&C | 70055101 | A | 44AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 4 | TECO CNF PRT NMAT PRC SETC | 2021-03-10 | 2021-03-28 | 1.6 | 2 | 3.2 | PLND SCHD | 220 | 220 | 2021-03-10
SH_I&C | SH_I&C | 70055102 | A | 44AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3 | TECO CNF NMAT PRC SETC | 2021-03-20 | 2021-03-21 | 1.6 | 2 | 3.2 | PLND SCHD | 165 | 165 | 2021-03-19
SH_I&C | SH_I&C | 70055103 | A | 44AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-03-22 | 2021-03-22 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-03-22
SH_I&C | SH_I&C | 70055104 | A | 44AT69002 | SM02 | 1W STACK NOX O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF PRT NMAT PRC SETC | 2021-03-29 | 2021-03-29 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-03-29
SH_I&C | SH_I&C | 70055105 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-04-05 | 2021-04-05 | 1.6 | 2 | 3.2 | ABDN | 176 | 176 | 2021-04-14
SH_I&C | SH_I&C | 70055106 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-04-12 | 2021-04-12 | 1.6 | 2 | 3.2 | ABDN | 176 | 176 | 2021-04-14
SH_I&C | SH_I&C | 70055107 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-04-26 | 2021-04-26 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-04-26
SH_I&C | SH_I&C | 70055108 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 3.2 | TECO CNF NMAT PRC SETC | 2021-04-26 | 2021-04-26 | 1.6 | 2 | 3.2 | PLND SCHD | 176 | 176 | 2021-04-26
SH_I&C | SH_I&C | 70055109 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-05-05 | 2021-05-09 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-05
SH_I&C | SH_I&C | 70055110 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-05-11 | 2021-05-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-11
SH_I&C | SH_I&C | 70055111 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-05-19 | 2021-05-23 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-19
SH_I&C | SH_I&C | 70055112 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-05-24 | 2021-05-24 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-05-24
SH_I&C | SH_I&C | 70055113 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-06-03 | 2021-06-06 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-03
SH_I&C | SH_I&C | 70055114 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-06-07 | 2021-06-07 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-07
SH_I&C | SH_I&C | 70055115 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-06-14 | 2021-06-20 | 2 | 1 | 2 | PLND SCHD | 523.39 | 523.39 | 2021-06-15
SH_I&C | SH_I&C | 70055116 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-06-21 | 2021-06-21 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-06-21
SH_I&C | SH_I&C | 70055117 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-07-01 | 2021-07-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-01
SH_I&C | SH_I&C | 70055118 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-07-05 | 2021-07-05 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-05
SH_I&C | SH_I&C | 70055119 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-07-12 | 2021-07-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-12
SH_I&C | SH_I&C | 70055120 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-07-20 | 2021-07-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-20
SH_I&C | SH_I&C | 70055121 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-07-26 | 2021-07-26 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-07-26
SH_I&C | SH_I&C | 70055828 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-03 | 2021-08-08 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-03
SH_I&C | SH_I&C | 70055829 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT GMPS MACM PRC SETC | 2021-08-02 | 2021-08-31 | 2 | 1 | 2 | PLND SCHD | 523.39 | 523.39 | 2021-08-02
SH_I&C | SH_I&C | 70055863 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-11 | 2021-08-15 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-11
SH_I&C | SH_I&C | 70055864 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-09 | 2021-08-15 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-09
SH_I&C | SH_I&C | 70055883 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-08-17 | 2021-08-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-17
SH_I&C | SH_I&C | 70055884 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-16 | 2021-08-16 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-16
SH_I&C | SH_I&C | 70055899 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-24 | 2021-08-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-24
SH_I&C | SH_I&C | 70055900 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-23 | 2021-08-23 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-23
SH_I&C | SH_I&C | 70055930 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-30 | 2021-08-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-31
SH_I&C | SH_I&C | 70055931 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-08-30 | 2021-08-31 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-08-31
SH_I&C | SH_I&C | 70056364 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-07 | 2021-09-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-07
SH_I&C | SH_I&C | 70056365 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-06 | 2021-09-06 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-06
SH_I&C | SH_I&C | 70056375 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-15 | 2021-09-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-15
SH_I&C | SH_I&C | 70056376 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-13 | 2021-09-13 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-13
SH_I&C | SH_I&C | 70056427 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-22 | 2021-09-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-22
SH_I&C | SH_I&C | 70056428 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-22 | 2021-09-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-22
SH_I&C | SH_I&C | 70056491 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-27 | 2021-09-27 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-27
SH_I&C | SH_I&C | 70056492 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-09-29 | 2021-09-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-09-29
SH_I&C | SH_I&C | 70056983 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-04 | 2021-10-10 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-04
SH_I&C | SH_I&C | 70056984 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-06 | 2021-10-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-06
SH_I&C | SH_I&C | 70057037 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-11 | 2021-10-11 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-11
SH_I&C | SH_I&C | 70057038 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-11 | 2021-10-11 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-11
SH_I&C | SH_I&C | 70057080 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-21 | 2021-10-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-21
SH_I&C | SH_I&C | 70057081 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-19 | 2021-10-24 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-19
SH_I&C | SH_I&C | 70057183 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | Annual Surveillance Test | 4 | TECO CNF PRT NMAT PRC SETC | 2021-10-06 | 2021-10-30 | 4 | 1 | 4 | PLND SCHD | 1320 | 1320 | 2021-10-07
SH_I&C | SH_VEND | 70057183 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | Vendor Assistance | 4 | TECO CNF PRT NMAT PRC SETC | 2021-10-06 | 2021-10-30 | 4 | 1 | 4 | PLND SCHD | 1320 | 1320 | 2021-10-07
SH_I&C | SH_VEND | 70057183 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | Vendor Assistance | 8 | TECO CNF PRT NMAT PRC SETC | 2021-10-06 | 2021-10-30 | 8 | 1 | 8 | PLND SCHD | 1320 | 1320 | 2021-10-07
SH_I&C | SH_I&C | 70057183 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Vendor Maintenance | 5Y QAL2 Function test audit | 8 | TECO CNF PRT NMAT PRC SETC | 2021-10-06 | 2021-10-30 | 8 | 1 | 8 | PLND SCHD | 1320 | 1320 | 2021-10-07
SH_I&C | SH_I&C | 70057184 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Annual Surveillance Test | 4 | TECO CNF NMAT PPRT PRC SETC | 2021-11-16 | 2021-11-30 | 4 | 1 | 4 | PLND SCHD | 1375 | 1375 | 2021-11-25
SH_I&C | SH_VEND | 70057184 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Vendor Assistance | 4 | TECO CNF NMAT PPRT PRC SETC | 2021-11-16 | 2021-11-30 | 4 | 1 | 4 | PLND SCHD | 1375 | 1375 | 2021-11-25
SH_I&C | SH_VEND | 70057184 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Vendor Assistance | 8 | TECO CNF NMAT PPRT PRC SETC | 2021-11-16 | 2021-11-30 | 8 | 1 | 8 | PLND SCHD | 1375 | 1375 | 2021-11-25
SH_I&C | SH_I&C | 70057184 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | 5Y QAL2 Function test audit | 8 | TECO CNF NMAT PPRT PRC SETC | 2021-11-16 | 2021-11-30 | 8 | 1 | 8 | PLND SCHD | 1375 | 1375 | 2021-11-25
SH_I&C | SH_I&C | 70057184 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | Assist Vendor and act as PA | 1 | TECO CNF NMAT PPRT PRC SETC | 2021-11-16 | 2021-11-30 | 1 | 1 | 1 | PLND SCHD | 1375 | 1375 | 2021-11-25
SH_I&C | SH_VEND | 70057184 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Vendor Maintenance | QAL2 Linearity checks | 16 | TECO CNF NMAT PPRT PRC SETC | 2021-11-16 | 2021-11-30 | 16 | 1 | 16 | PLND SCHD | 1375 | 1375 | 2021-11-25
SH_I&C | SH_I&C | 70057188 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-25 | 2021-10-25 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-25
SH_I&C | SH_I&C | 70057189 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-10-25 | 2021-10-25 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-10-26
SH_I&C | SH_I&C | 70057233 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-01 | 2021-11-01 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-01
SH_I&C | SH_I&C | 70057234 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-03 | 2021-11-30 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-03
SH_I&C | SH_I&C | 70057515 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-08 | 2021-11-14 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-08
SH_I&C | SH_I&C | 70057516 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-08 | 2021-11-14 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-08
SH_I&C | SH_I&C | 70057546 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-15 | 2021-11-15 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-15
SH_I&C | SH_I&C | 70057547 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-15 | 2021-11-15 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-15
SH_I&C | SH_I&C | 70057563 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-09-22 | 2021-09-30 | 4 | 1 | 4 | PLND SCHD | 6214.71 | 6214.71 | 2021-09-22
SH_I&C | SH_VEND | 70057563 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-09-22 | 2021-09-30 | 4 | 1 | 4 | PLND SCHD | 6214.71 | 6214.71 | 2021-09-22
SH_I&C | SH_I&C | 70057563 | A | 43AT69002 | SM02 | Train 1 Nox Analyser Maintenance | order spare parts | 0 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-09-22 | 2021-09-30 | 0.5 | 1 | 0.5 | PLND SCHD | 6214.71 | 6214.71 | 2021-09-22
SH_I&C | SH_I&C | 70057564 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-09-22 | 2021-12-31 | 4 | 1 | 4 | PLND SCHD | 219.99 | 219.99 | 2021-09-22
SH_I&C | SH_VEND | 70057564 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | 6M Nox Analyser Calibration (Orbital) | 4 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-09-22 | 2021-12-31 | 4 | 1 | 4 | PLND SCHD | 219.99 | 219.99 | 2021-09-22
SH_I&C | SH_I&C | 70057564 | A | 44AT69002 | SM02 | Train 2 Nox Analyser Maintenance | Order spare parts used | 0 | TECO CNF GMPS MACM PPRT PRC SETC | 2021-09-22 | 2021-12-31 | 0.5 | 1 | 0.5 | PLND SCHD | 219.99 | 219.99 | 2021-09-22
SH_I&C | SH_I&C | 70057573 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 1 | TECO CNF PRT NMAT PRC SETC | 2021-11-22 | 2021-11-22 | 2 | 1 | 2 | PLND SCHD | 55 | 55 | 2021-11-22
SH_I&C | SH_I&C | 70057574 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 1 | TECO CNF PRT NMAT PRC SETC | 2021-11-22 | 2021-11-22 | 2 | 1 | 2 | PLND SCHD | 55 | 55 | 2021-11-22
SH_I&C | SH_I&C | 70057631 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-29 | 2021-11-29 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-29
SH_I&C | SH_I&C | 70057632 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-11-29 | 2021-11-29 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-11-29
SH_I&C | SH_I&C | 70058122 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-12-06 | 2021-12-06 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-12-06
SH_I&C | SH_I&C | 70058123 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-12-06 | 2021-12-06 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-12-06
SH_I&C | SH_I&C | 70058133 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-12-14 | 2021-12-14 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-12-13
SH_I&C | SH_I&C | 70058134 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF NMAT PRC SETC | 2021-12-14 | 2021-12-14 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-12-13
SH_I&C | SH_I&C | 70058152 | A | 43AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-12-20 | 2021-12-20 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-12-20
SH_I&C | SH_I&C | 70058153 | A | 44AT69002 | SM02 | 1W STACK NOX CO2 O2 CEMS ANALYZER PM | Inspect And Calibrate | 2 | TECO CNF PRT NMAT PRC SETC | 2021-12-20 | 2021-12-20 | 2 | 1 | 2 | PLND SCHD | 110 | 110 | 2021-12-20
SH_NOTIF | SH_NOTIF | 70000816 | A | 44AT69002 | SM02 | NOX Analyser Train 2 calibration | NOX Analyser Train 2 calibration | 0 | TECO CNF PRT CSER NMAT PRC SETC | 2009-05-13 | 2009-05-13 | 0 | 0 | 0 |  | 0 | 0 | 2012-07-03
SH_TELCM | SH_TELCM | 60008392 |  | 43AT69002 | SM01 | (91) NOx CEMS PC fails on GA activation | (91) NOx CEMS PC fails on GA activation | 2 | TECO CNF PRT NMAT PRC SETC | 2014-10-22 | 2014-10-28 | 2 | 1 | 2 |  | 110 | 110 | 2014-10-23
SH_TELCM | SH_TELCM | 60008393 | A | 44AT69002 | SM01 | (91) NOx CEMS PC fails on GA activation | (91) NOx CEMS PC fails on GA activation | 2 | TECO CNF PRT NMAT PRC SETC | 2014-10-22 | 2014-10-28 | 2 | 1 | 2 |  | 110 | 110 | 2014-10-23