## Process Review
1 | Area | Location | Type | Sources | Control Measures | Risk/Impact | Regular Inspection? | Additional Measures required? | Priority | Proposed Measure | Expected Cost | Progress? | Proposed start date | Date completed | Comments
2 | 120 | Cemfuel | None
3 | 121 | Profuel | fine paper and plastic | Trailers | Enclosed building | Low | Yes | No
4 |  |  |  | Level 6 | Enclosed building | Low | Yes | No
5 | 161 | Limestone | Limestone - coarse | Laminator building | Enclosed building. Vents have been assessed for dust and not significant
6 |  |  |  |  | Automatic doors have been replaced and are operating well | Low | Yes | No
7 |  |  |  | Conveyors | Partially or fully enclosed. Particle size | Low | Yes | No
8 |  |  |  | Transfer points | fully enclosed with the exception of BC03 to BC30 | Med | Yes | Yes | 3 | Additional Sheeting |  |  |  |  | Cladding replacement programme starting 2016
|  | Coal Store | Coal | Openings | Water misting | Low | no | Yes | 5 | Update misting on rear opening. | 1000 |  |  |  | No off site problems reported, but further measures can be considered
9 | 162 | Crane Bay | Clinker | Front Doors | Automated Doors | Med/High | Yes | Yes | 1 | Door replacement programme. | 50000 | Yes | 2014-09-01
10 |  |  | PFA |  | Training
11 |  |  | Sand |  | Tool box talks
12 |  |  | Limestone |  | Management intervention
13 |  |  | Coal |  | Option to use in manual (sand)
14 |  |  | Gypsum |  | CCTV
15 |  |  |  | Side Doors | Access controlled by Shift Manager | Low | no | no
16 |  |  |  | Sheeting | Structural Survey | Med | Yes | FIR | 5 | Replacement of damaged sheets |  |  |  |  | Cladding replacement programme starting 2016
17 |  |  |  | Gypsum Door | Training | Med | no | FIR | 4 | Investigate cost of Door replacement |  |  |  |  | Quotes required
18 |  |  |  | General | Clinker transport dedusting maintenance incorporated into contract | Med | Yes | No
20 |  |  |  |  | Closing of Man Doors (High Level) | Med | no | Yes | 2 | Industrial self closures | 500 |  | 2015-07-01
22 | 181 | MBM | MBM | Discharge point | Discharge procedures | Low | Yes | No
23 |  |  |  | RF01 | Regular cleaning/Fully enclosed | Low | Yes | No
24 |  |  |  | Blocked Line clearance | Cleaned immediately | Low | - | No
25 | 331 | Raw Mill Feed | PFA/Sand/Limestone | Feeder area | Partially enclosed | Low | Yes | Yes | 5 | Additional Door on opening to BC03 |  |  | Q2 2016 |  | quotes required
26 | [9 empty] | Replace Sheeting adjacent to Slurry Mills
27 |  |  |  | Conveyors | Enclosed with the exception of BC01 | Low | Yes | No
28 |  |  |  | Transfer Points | Partially enclosed | Low | Yes | Yes | 5 | Fit Door below BC03/BC01 tranfer point |  |  | Q2 2016 |  | quotes required
29 | 341 | Raw Mill | PFA/Sand/Limestone | BC02/DG02 | Partially enclosed | Low | Yes | No |  | Impractical to enclose any further
30 |  |  | Raw Meal | Reject system | Reject to shed | Med | Yes | Yes | 1 | Reject returns system | 80000 | Yes
|  |  |  | Main GCT - SC08 | Enclosed Chute to skip | Med | Yes | Yes | 4 | Upgrade gearbox with potential of reducing dust to outside | 15000 |  | 2016-01-01
31 |  |  | General | Man Doors - stairwell | Signage on doors | Low | no | Yes | 3 | Industrial self closures | 2500 |  | 2015-07-01
32 |  |  |  | Man Door at Rejects elevator | None | Low | Yes | Yes | 2 | Replace/Repair door | 1000 |  |  |  | Contractor input required, costs and dates
33 | 361 | Kiln Feed | Raw Meal | Tunnel | Enclosed | Low | Yes | Yes | 3 | Industrial self closures | 500 |  | 2015-07-01
34 | [9 empty] | Additional Door before blower room | 1000
35 | [9 empty] | Repair Door adjacent to elevators | 500
36 |  |  |  | Silo Tops | Enclosed | Low | Yes | No
37 |  |  |  | Level 9 | Enclosed | Med | No | Yes | 5 | Industrial self closures | 500 |  | 2015-07-01
38 | 421 | Preheater Tower | Raw Meal | Cyclone blockage clearance | Procedure in place | High | yes | no
39 |  |  |  |  | Chemistry control
40 |  |  |  |  | Process control
41 |  |  | Calcined raw meal | Kiln Inlet seal | Process control | Med | Yes | No
42 |  |  |  |  | CCTV
44 | 441 | Cooler | Clinker | Kiln outlet seal | Chemistry | low
45 |  |  |  |  | Process control | low | yes | no
46 |  |  |  | Man doors | Self closers in place | low | no | no
47 |  |  |  | Roller door | open only when access required. | low | yes | no
48 |  |  |  | Conveyor (CV01) | Enclosed in building | low | yes | no
49 |  |  |  | Transfer Points | Enclosed in building | low | yes | no
50 |  |  | Clinker Dust | Gas stream | Bag filter | med | yes (CEMS) | no
51 |  |  |  | Heat Exchanger | visual/routes | med | yes | yes | 2 | New system to be installed | 300000 |  | 2016-01-01
53 | 451 | ByPass | Dust | Gas Conditioning tower outlet | Enclosed building, with roller shutter door | low | yes | yes | 1 | Sealing around door to be improved | 2000 |  | 2015-08-01
54 |  |  |  | Dust storage silos/loading head | Enclosed building, plastic strip doors | low | no | no
55 |  |  |  | Transport system | Fully enclosed with interlocks | low | no | no
57 | 461 | Coal Mill | Milled coal | filter system | fully enclosed, mill on PM | low | yes | no
58 |  |  |  |  | Enclosed building
59 |  |  |  | FK Pump | Enclosed building | low | yes | no
61 | 462 | Coal Feed | Coal dust | blowing line | inspection/NDT | med | yes | no
65 | 471 | Clinker transport | Clinker Dust | CV02 | Enclosed building | med | yes | yes | 2 | Replace sheeting at non drive end, enclose skip area. Improve door area. | 3000 |  | 2015-08-01
66 |  |  |  | Export Silo | Roller shutter doors | low | yes | no
67 |  |  |  | Dome | Doors, sheeting | med/high | yes | yes | 4 | Work on penthouse access, investigation of door closure |  |  | 2016-01-01 |  | Scope of works to be defined
68 |  |  |  | Clinker belts B-F | Doors | med | no | yes | 1 | Additional route required |  |  | 2015-07-01 |  | no cost, internal procedure required
69 |  |  |  | Clinker Belt G, disused loading head | Checks, enclosed | med | no | yes | 3 | Remove/blank off old loading head | 4000 |  | 2016-01-01 |  | costs and dates to be confirmed with contractors
70 |  |  |  | Vehicle movements in dome | Process control to provide space fully inside dome | med | yes, when in progress | Possible
71 |  |  |  | Tensioning Unit for g belt | Currently sheeted | med | no | yes | 5 | Requires door fitting to bottom | 1000 |  | 2016-01-01 |  | costs and dates to be confirmed with contractors
|  |  |  | Clinker Hoppers | Within crane store and additional sheeting covers | med | no | Yes | 2 | Inspect current situation and investigate proposals for improvement |  |  |  |  | scope to be defined before costings.
73 |  | Cement mill house | Gypsum | Feeders | Enclosed building, sheeting | low | yes | no
74 |  |  | Limestone | conveyors | Doors | low | yes | no
75 |  |  | Clinker | Mills | Checks/maintenance | low | yes | no
76 |  |  | Cement | Stacks | Filters | low/med | yes (CEMS) | no
81 |  | Ferrous Silo | Ferrous sulphate | Transfer points | inspections/PM | low |  | no
83 |  | Cement transport | Cement | Blowing lines | NDT/CCTV | med/high | yes | no
85 |  | Storage silos | Cement | Filter units | inspections/PM | low | yes | no
86 |  |  |  | Loading heads | inspections/PM | low | yes | no
87 |  |  |  | Penthouse/roof | doors | low | yes | no
89 |  | Packing dock | This will be reviewed and added to as the system is started up.
91
92 | 0 | General | Various | Expansion Joints | Maintenance programme | Med | - | Yes | 2 | Register of expansion joints on site |  |  |  |  | Internal review required
94 |  |  |  | Airslides | Maintenance programme | Med | implemented | Yes | 2 | Review inspection schedule |  |  |  | 2015-06-01 | Maintenance programmeme on SAP reviewed for frequency and issued
95 |  |  |  | Small Bag Filters | Process checks | Med | implemented | Yes | 2 | Review inspection routes to ensure all filters are captured routinely |  |  |  |  | Issued on ongoing programmeme.
97 |  |  | Dust | Road Movements | Bowser, sweeper wagon (see control measures) | low |  | no, but being considered for improvement |  | Investigate fixed sprinkler system trial for road wetting. |  |  |  |  | Scope of trial to be determined prior to costings.
98 |  |  | Dust | Hard Standing | limited | low |  | no, but being considered for improvement |  | Investigate converting to concreted areas | 300000 |  |  |  | Conversion from compacted aggregates to mitigate any impact from crushed limestone.
99
100

## Control Measures
Routes to consitute the main Control measures: Major projects to be documentend on following sheet.
Action | Frequency | Check | Control
Shift Managers route | one minimum per shift | Documented and reported to morning meeting | Actions minuted as required
Other routes | Two per shift. | Documented and reported to area contact. | Reported to daily production meeting, Notifications rasied as required and planned in at planning meeting.
Bowser/sweeper routes | Whole route to be covered as a minimum once per day. Shift Mananger to direct to additional areas when required. | SM to check and direct