## Action Log
Action Log
Action ID | Document | NRW Comment | Action Required | Response
1 | OPRA | We have reviewed the OPRA profile submitted with the application and have made the following changes. This has resulted in the score increasing from 46 to 64, and the fee increasing from £8,050 to £11,200. Therefore, an additional fee of £3,150 is required. | Pay the additional application fee . Once this has been paid, please confirm this has been done, with confirmation of the date of payment, amount and reference used. | After adjusting the questions in the OPRA, the application fee was £10,850. The outstanding fee of £2,800 has now been paid. Payment reference: EPRDENBIGHCC0001
2 | OPRA | Complexity Attribute has changed from A11 to A09 as the site is proposing to accepted hazardous waste (soil, batteries and WEEE). The hazardous soil means the site must be treated as a hazardous waste transfer station. NOTE: this change has required further questions on the Operator Performance tab to be completed which may alter the fee further. | Complete the unanswered questions on the Operator Performance tab | The OPRA score has been recalculated. The remaining operator performance questions have further altered the submission fee. (See Action 1)
3 | Technical Ability | The required primary qualification for the activity applied for is HROC4, the primary and continuing competence awards provided for Mr David Driver can be used. | Provide contact information for Mr Driver for our records | Contact details for Mr David Driver can be found in the document: DCC.020 Technical Competency Details
4 & 5 | Technical Ability | Document DCC.019 Hazardous waste qualifications registration has been provided as proof of registration for two members of staff onto the HROC4 course. However the email chain does not provide any information on who has been registered other than “Gareth and Phil”. We also note that this email chain originates from June 2022. | Confirm who has been registered for this award, and provide their contact information for our records. Provide an update on the obtaining of the qualification. | Contact details for other members of staff registered on the course can be found in the document: DCC.020 Technical Competency Details
6 | Site condition report | Document DCC.001 Site Condition Report 1, 2, 3 and 4 have been provided but these are only the desktop studies of the local area. The Site Condition Report itself has not been provided. | Provide the site condition report written in line with our H5 Site Condition Report guidance- Natural Resources Wales / Horizontal guidance | The site condiiton report and remaining appendices have now been incldued in the package (DCC.001 Site Condition Report)
7 | Management System | DCC.003 Operating Techniques Document v1.0 includes a drainage plan; however it is not legible when zoomed in. | Provide the drainage plan as a separate document | The drainage plan has now been provided as a separate document: DCC.021 Site Drainage Plan
8 | Management System | Our guidance (How to comply with your permit) states that your EMS must include information on the following which has not yet been provided: (a) procedures to enable you to apply the waste hierarchy of re-use, recover, recycle, dispose (b) your Duty of Care (c) Closure (d) Complaints | Update your management system documents to include the above points. | The management documents containing this information have been added to the permit package: DCC. 004_EMS.S2.06 (Complaints Procedure) DCC.004_EMS.S2.07 (Complaints Form) DCC.004_EMS.S2.08 (Environmental Performance, Legal Compliance and Internal Auditing) and DCC.004_EMS.S4.02 (Waste Acceptance Procedures and Sampling)
9a | ERA | Document DCC.007a Site Layout Plan notes an existing newt pond inside the permit boundary. On our reviews of the local area we cannot find reference to an existing newt pond, nor is there any other references to a newt pond or a need for a newt pond in the rest of the application (except for a brief mention in the Fire Prevention & Mitigation Plan). We have also not found any records of newts in the local area. | Explain the inclusion of a newt pond, and if relevant include the presence of newts within your ERA. | The newt pond has been included on the basis of the findings of a newt survey undertaken at, and around, the site. Evidence of newts was found at a pond c.480m from the site's northern boundary. The site installed exclusion fencing and clear trapped any newts on the site pre-construction - this work has been done under Licence obtained from NRW. A landscape strip was created to the north of the site to mitigate the loss of greenfield habitat and newt pond was included within this strip. The pond is outside of the security fence of the WTS. The presence of newts has now been included with the ERA (DCC.002 Environment Risk Assessment)
9b | ERA | Our review has identified a local wild life site to the east of the site called Coed Parc-Pierce which is a broadleaved woodland, with Alder, Ash and Beech communities. It is a limestone woodland just to the north of Denbigh Quarry to the west of the site on the same footprint of one of the ancient woodlands already identified within your ERA. | This local wildlife site needs to be included within the ERA. Its location has been included for your information. | Coed Parc-Pierce wildlife site has now been included within the ERA. (DCC.002 Environment Risk Assessment)
9c | ERA | Our review has identified a pond to the north of the site, which is also included in your site plan, however section 2.1.4 of your ERA states there are no local water bodies within 1km of the site. | This needs to be corrected in your ERA, and risks addressed where relevant. | Following ground investigations during the newt mitigation survey of the site, the area marked 'pond' was found to be a grassy hollow that became temporarily inundated in the wettest weather. The presence of this feature has now been included within the ERA. (DCC.002 Environment Risk Assessment)
10 | Pest Management Plan | The pest management plan (PMP) has been reviewed against our guidance and management plan requirements. The following needs to be included in your PMP: (a) Site operating times | Update your PMP to include the sites operating times. | Site operating times have now been added to DCC.013 Pest Management Plan
11 | Dust Management Plan | The dust management plan (DMP) has been reviewed against our guidance and management plan requirements. The following needs to be included in your DMP: (a) Site operating times (b) Reference to specific dust producing wastes. Currently your dust management plan discusses waste in general terms only. It also specifically states that glass is not dusty by nature, however you have also specified in Section 3 of DCC.003 Operating Techniques Document v1.0 states that glass will be “size reduced by pushing/crushing the material against the bay walls” which would generate dust. Other potential dust creating wates are soil and green wastes, however all wastes should be assessed and where relevant be specifically included in your DMP. (c) visual monitoring methods and how dust emissions are detected. Some information is included in section 5; however it is vague and does detail what the trigger levels for dust are, or what an acceptable level is. We would expect all sites to have a formal visual monitoring inspection and designated monitoring points. (d) Monitoring of the weather conditions. Section 4.3.3 gives a triggering wind speed and temperature, but does not include where this information is from, or say how these are known. Weather conditions are fundamental in regards to the generation and transportation of dust emissions from sites. (e) how staff will be trained on the DMP (f) how appropriate records will be kept (for example of monitoring, complaints) (g) how the records of the monitoring and complaints will be reviewed with the aim of improving operations on site | Update your DMP to include all the points | DCC.0014 Dust Management Plan has been updated to address the points raised. For point (b) dust-producing wastes have now been added to the DMP, however glass has not been added. Glass is not crushed to dust on site and is not inherantly dusty. The previous comment within DCC.003 Operating Techniques referring to crushing glass has been removed as this was added in error.
12 | Fire Prevention & Mitigation Plan | The Fire Prevention and Mitigation Plan (FPMP) includes several site plans; however these are not legible when zoomed in. | Provide all the plans from the FPMP as separate documents. | The site plans from the FPMP have now been provided as separate documents: DCC.021 Site Drainage Plan DCC.022 Emergency Equipment Locations & Emergency Vehicle Tracking Plan DCC.023 Firewater Containment Plan DCC.024 Site Surfacing Plan DCC.025 Waste Material Location
13 | Fire Prevention & Mitigation Plan | Several bookmarks in the FPMP are broke, and some of the references are not correct, for example within section 4.1 Quarantine area it refers to Figure 1-3 but it does not contain the information referred to in this section. | Fix any broken references and make corrections where relevant. | Cross-referencing has been fixed throughout the FPMP. The full size version of the plan in Figure 1-3 (DCC.025 Waste Material Location Plan)contains the details of the size, location and separation distances of the quarantine area.
14 | Fire Prevention & Mitigation Plan | The FPMP has been reviewed against our Fire prevention and mitigation plan: waste management guidance. The following needs to be included in your FPMP and has been listed as per the section in our guidance: (a) 5. Fire Prevention and Mitigation Plan contents: (i) the minimum separation/fire break distance required between all waste/baled waste stacks, and between buildings and waste/baled waste stacks- Figure 1-4 has some distances but this is only for the inside of the main building and not the rest of the site where combustible material is also stored. (ii) the fire prevention techniques used, including management of hotspots (signs of potential self-combustion), monitoring, reporting, recording and actions (iii) techniques used to minimise the risk of fire spreading within the site or from the site (iv) Site plan: areas where hazardous materials are stored (location of gas cylinders, process areas, chemicals, piles of combustible materials, oil & fuel tanks) (v) Site plan: main access routes for fire engines (typical FRS vehicle access requirements are below) & any alternative access points around the site perimeter to assist fire fighting (vi) Site plan: the location of plant, protective clothing and pollution control equipment and materials (b) 10. Baled waste storage- information required by this section does not appear to have been included despite baled waste being created and stored on site (c) 12. Waste stored within a building- information required by this section does not appear to have been included despite waste being stored in a building (d) 13. Waste stored in containers- information required by this section does not appear to have been included despite waste being stored in containers (e) 21. Managing water run-off- your FPMP does not include how much fire water can be contained on site | Update your FPMP to include the above points. | DCC.005 Fire Prevention and Mitigation Plan (FPMP) has been updated to address all points. a) (i) New site plan showing relevant dimensions has been added to the FPMP. (Also submitted as a separate document, see Action 13) (ii) Section 3.0 has been updated to include fire prevention techniques. (iii) Section 3.0 has been updated to include techniques to minimise the risk of fire spread. (iv)(v)(vi) The emergency site plan has been updated to include all raised points. PPE is stored within the main building - this has been added to the FPMP. b) c) & d) Section 2.3 has been restructured to clarify waste storage and processes. All information has now been included. e) Water containment capacity has been added to Section 4.2.
15 | Odour Management Plan | Please note that the DCC.016 Odour Impact Assessment has not been assessed, as it is not a required document, and all relevant information should be included in the Odour Management Plan and Risk Assessment. The odour management plan (OMP) has been reviewed against our guidance and management plan requirements. The following needs to be included in your OMP: (a) Site operating times (b) Daily throughput limit (c) Maximum storage quantities for odorous wastes (d) Site plan: monitoring points (e) Complaints procedure: information on what actions will occur in the event of multiple complaints being received in a short time. (f) how staff will be trained on the OMP (g) how appropriate records will be kept (for example of monitoring, complaints) (h) how the records of the monitoring and complaints will be reviewed with the aim of improving operations on site | Update your OMP to include the above points | DCC.011 Odour Management Plan has been updated to included all requested information.
16 | Noise Impact Assessment | The Noise Impact Assessment (NIA) has been assessed against the requirements of BS4142. The following points need to be addressed: (a) Statement of competency for all persons contributing to the assessment- while it is stated in section 1.1.4 that the author and reviewers are fully accredited members with the Institute of Acoustics; information on their competency levels or qualifications have not been given. (b) Description of sources of sounds- Section 3 of DCC.003 Operating Techniques Document v1.0 states that glass will be “size reduced by pushing/crushing the material against the bay walls”. This source of noise has not been included in the NIA. (c) measurement locations - while Figure 4.1: Environmental Sound Measurement Location includes all 3 monitoring locations, Table 4.1: Description of Measurement Locations only includes location “A” and not “L1” and “L2”. (d) Weather conditions- information given in section 4.3 Meteorological Conditions is only for the May 2022 measurements at location “A”. Information has not been given for the September 2019 measurements at locations “L1” and “L2”. (e) Date(s) and time(s) of measurements- information given in sections 4.1 and 4.2 are only for the May 2022 measurements at location “A”. Information has not been given for the September 2019 measurements at locations “L1” and “L2”. (f) Background sound level(s) and measurement time interval(s) and in the case of measurements taken at an equivalent location, the reasons for presuming it to be equivalent. The September 2019 monitoring has been used for the background used in the assessment for receptors R2, R3, and R4, however all the relevant data from this monitoring has not been provided, including justification for the typical LA90 chosen Additionally it has not been justified why the location of L2 is equivalent to R2, R3 and R4. | Update your NIA to include the above points. | DCC.017 Noise Impact Assessment has been updated to address all points raised. For point (b), the previous comment within DCC.003 Operating Techniques referring to pushing/crushing glass has been removed as it was added in error.
17 | Noise Impact Assessment | Section 6.3.1 of the NIA refers to an acoustic model, however this has not been supplied. | Provide the acoustic modelling for assessment | The acoustic model data has been supplied: DCC.017a Acoustic Modelling Data
18 | General | Section 6.3.2 of the NIA states that bays are 5 meters high, however the FPMP states they are 3 meters high (which may be 4 meters if the 1 meter freeboard has not been included in the 3 meter height), and Section 4.2.3 of the Nosie Management Plan states the northern wall is 4 meters high. This disparity needs to be addressed in all affected supporting documents. | Clarify the above, and amend the relevant documents ensuring consistency across your application. | Bay walls are a minimum 4m high, and there is an extension to the back wall for noise mitigation purposes, bringing this wall to 7m high. The heights referred to in the FPMP refer to the waste pile height up to the 3m fill line. Wall heights have been clarified throughout the documents, where applicable.
19 | Noise Management Plan | The noise management plan (NMP) has been reviewed against our guidance and management plan requirements. The following needs to be included in your OMP: (i) Site operating times (j) how staff will be trained on the OMP (k) how appropriate records will be kept (for example of monitoring, complaints) (l) how the records of the monitoring and complaints will be reviewed with the aim of improving operations on site | Update your NMP to include the above points | DCC.012 Noise Management Plan has been updated to include all requested information.