## Project Plan Workbook Index
Record |  | Date & Version | [7 empty] | YES
Project Plan Workbook Template |  | February 2024 V1.15 | [7 empty] | NO
PROJECT PLAN WORKBOOK INDEX | [9 empty] | N/A
Project Name: | A494 River Dee Bridge Deck over-slabbing Contingency Scheme |  |  |  |  | Project No: | 21-NM-CHR-003
[6 empty] | Date: |  |  | E
H
C
DOCUMENT STATUS:
(E= Email H= Hard Copy C= CD) | [5 empty] | Format: | E |  | P
(P=Preliminary I= For information T=For tender | [5 empty] | Status: | P |  | I
C=Construction PS= Planning Submission) | [8 empty] | T
Document Title |  |  | Originating Company |  | Completed Yes/No/N/A |  | Comments |  | C
Project Management Plan (PMP) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd. |  | NO |  |  |  | PS
Construction Phase Health & Safety Plan (CPP) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd. |  | NO
Construction Environmental Management Plan (CEMP) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd. |  | NO
Traffic Management Plan (TMP) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd. |  | NO
Project Roles & Responsibilities Matrix |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd. |  | NO
TRANSMITTAL RECORD:
Company |  |  |  |  | Name |  | Number of Copies
The documents are issued to you for: |  |  | Review / Comment
Return to: |  |  |  | Please sign a copy of this transmittal sheet as acknowledgement of receipt and return within seven days
Name: |  |  |  |  | I/ we acknowledge the receipt of documents above
Company:
Address: | Ty Glyn, Ruthin, Canol Y Dre, Denbighshire, LL15 1QW | Sign
E-mail: |  |  |  |  | Name |  | Signature | Date

## PMP
PROJECT MANAGEMENT PLAN (PMP)
Project Name: | A494 River Dee Bridge Deck over-slabbing Contingency Scheme
Project Number: | 21-NM-CHR-003
Project Details
Project Description: |  | The North and Mid Wales Trunk Road Agent (NMWTRA) have commissioned a project to develop a major maintenance intervention should a critical defect be identified within the A494 River Dee Bridge structure and enable this to be implemented with minimal impact on traffic conditions. The proposed design intervention comprises of removing a depth of existing road surfacing and replacing with a new thin reinforced concrete over-slab with combined waterproof and wearing membrane (hence forth referred to as the ‘over-slabbing works’). Enabling works are required to parts of the central reserve and to the Riverside Way Junction to facilitate contraflow traffic management arrangements during construction. The enabling works consist of construction 2Nr crossovers through the central reserve west of the existing bridge and works to widen the Riverside Way Junction.
Project Location: |  | Enter your project location here
Plan Approvals
Written by: | Name: |  |  |  | Signature: |  |  | Date:
Approved by: | Name: |  |  |  | Signature: |  |  | Date:
Explanatory Notes:-
(i) Origination: Tender phase origination resides with the Project Manager. Construction Phase update will be the responsibility of the Site Manager.
(ii) Approval: Tender phase approval resides with the Contracts Manager or Regional Director. Construction Phase approval will be the responsibility of the Project Manager.
(iii) Revision: The plan will be revised to reflect changes that have been made to the product, project or contract, work practices, service provision or Quality assurance procedures. Where changes are made to the plan an assessment of the impacts of the changes will be carried out and recorded in the Version Control section below.
Version Control
Description of changes |  |  | Date | Revision | Page No. | Comments
Explanatory Notes:-
This Project Management Plan will be added to, reviewed and updated as the project develops, further design work is completed, information from subcontractors starting work becomes available, unforeseen circumstances or variations to planned circumstances arise or where the operations management team deem it is necessary.
If sections are deemed not applicable DO NOT DELETE. Replace text with 'not applicable' on this project.
CONTENT
Section Ref | Content | [6 empty] | Comments
Introduction
1.0 | Project Details and Management Responsibilities
1.1 | Project Organisation and Resource
1.2 | Scope of works
1.3 | Project Timescales
2.0 | Project Plans
3.0 | Project Objectives and Performance Indicators
4.0 | Best Practice Initiatives
5.0 | Planning and Programming
6.0 | Risk Management
7.0 | Commercial Arrangements and Reporting
8.0 | Control of Documents, Data and Records
8.1 | IT Infrastructure
8.2 | Document Control
8.3 | Record Control
8.4 | Mandatory Client or Other Third Party Documentation Requirements
9.0 | Procurement
9.1 | Material Purchasing
9.2 | Plant Hire & Management
9.3 | Subcontract Procurement
10.0 | Client Supplied Product
11.0 | Customer Feedback
12.0 | Design Management
12.1 | Design and Development
12.2 | Design Change
13.0 | Process Control
13.1 | Work Procedures and Method Statements
13.2 | Workmanship Inspection and Testing
13.3 | Temporary Works Control
13.4 | Inspection, Testing and Monitoring Equipment
14.0 | Control of Non Conforming Product
14.1 | Rework and Defects
14.2 | Corrective and Preventive Action
15.0 | Handover and Aftercare
16.0 | Protection of Completed Works
17.0 | Internal Audit
18.0 | Training and Competency
19.0 | Record Referencing Matrix
20.0 | Further Guidance
Explanatory Notes:-
In this template Plan, guidance and sample content is included where deemed necessary. This is indicated by the inclusion of yellow boxes with text in brackets { }. On completing this plan all sample and guidance text should be deleted or overwritten as required.
Introduction
(a) The Project Management Plan (PMP) is a controlled document that outlines the resources and processes for carrying out all works associated with this project. The PMP describes how Jones Bros will perform the project (design, procurement, construction, commissioning and handover).
(b) One of the primary purposes of the Project Management Plan is to define what elements of the Jones Bros BMS will be put in place on specific projects.
(c) This plan has been developed in compliance with the requirements of ISO 9001 - Quality Management System, ISO 45001 - Occupational health and safety and ISO 14001 - Environmental Management and is mandated on all Jones Bros projects as part of the Jones Bros BMS and is therefore required to be in place and kept up to date through the project.
(d) We aim to reduce the provision of generic information and to only provide in this Project Management Plan and all other associated plans project specific information that should help with the communication and risk management of this project. Other non project specific information referenced in this plan will be clearly identified with the location where it is available. If there is a need to review these documents they will be provided on request.
(e) The PMP is intended to be an evolving live document developed during the tender phase. It shall summarise how Jones Bros plan to design, procure, construct and commission the works for the price we have signed up to, based upon project-specific needs and requirements.
(f) The PMP is intended to be revised, expanded and updated throughout the duration of the project. The Bid Manager or Project Manager shall lead the development of the PMP during the pre-award phases of the project with support from various functions. The Project Manager shall be responsible for developing the PMP and ensuring that changes are documented and communicated to all parties.
(g) After the project has been awarded, the PMP is updated with final details and the project-specific management processes and plans shall be handed over to the Site Manager for implementation and ongoing update through the construction phase. It is recognised that some parts of the PMP may be replaced by separate stand-alone documents that are specifically designed for use during the Design and Construction phase. These will be referenced accordingly throughout the plan.
(h) A single Project Management Plan is produced for the project (unless stated otherwise in section 1.2). It is updated as required, at a minimum of monthly intervals, throughout the project lifecycle or in response to significant change on the project.
SECTION 1 |  |  | PROJECT DETAILS AND MANAGEMENT RESPONSIBILITIES
1.1) Project Organisation and Resource
(a) Agreed responsibilities and Specific duties for key roles are outlined in the Jones Bros Business Management system under 03 -Knowledge area - 03.21 - HR - 03.21.01 Job Role Descriptions. Responsibilities are also identified in associated Process Flow Charts (PFC) held in the Jones Bros BMS 03 - Knowledge area - 03.03 Process Flow Charts and, where appropriate, referenced throughout this plan.
(b) Communication and display of appointments: |  |  | A copy of the appointments is to be displayed on the project’s health and safety notice board and in the project filing structure {insert location}.
(c) Specific responsibilities for this project have identified and listed throughout the development of this Project Plan Workbook. All roles captured throughout the document will be highlighted below and can be filtered for briefing in the:
Project Roles & Responsibilities Matrix
(d) All appointments on the matrix are to be signed for by each individual as acceptance and understanding of the issued roles and responsibilities for the project.
(e) Appointments will be reviewed and updated throughout the project, reflecting any changes or movement in the project as required.
Role | Name |  |  | Company |  | Address |  | E-mail | Telephone
Client | {insert name} |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) |  | Insert Address |  | {insert email} | {insert tel no.}
Client Contract Admin | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Principal Contractor | Jones Bros |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Workforce Planning Manager | Alan Manuel |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | alan.manuel@jones-bros.com | 07384834594
IT Infrastructure Section Manager | Gerallt Ellis |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | gerallt@jones-bros.com | 07584 705103
IT Systems Section Manager | Colin Jones |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | colin.jones@jones-bros.com | 07423 686839
Jones Bros Internal Auditor | Ellis Ashton |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | ellisa@jones-bros.com | 07384 835329
Principal Designer | (Insert name) |  |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Designer | (Insert name) |  |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Architect | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Structural Engineer | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Mechanical Consultant | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Electrical Consultant | (Insert name) |  |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Contract Director | Hefin Lloyd-Davies |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | hefin@jones-bros.com | 07887 722560
Contracts Manager | Daniel Robat Williams |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | robat@jones-bros.com | 07787 100752
Project Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Agent | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Senior Works Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Works Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Foreman 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Foreman 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Foreman 3 | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Engineer 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Engineer 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Engineer 3 | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Commercial Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Quantity Surveyor | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Senior Health & Safety Manager | Michael Jolley |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | michaeljo@jones-bros.com | 07795 648184
Environment Manager | Sam Higgitt |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | samh@jones-bros.com | 07766 747133
Design Manager | Dylan Parry |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | dylan.parry@jones-bros.com | 07918 797076
Designated Individual | {insert name} |  |  |  |  | {insert address} |  | {insert email} | {insert tel no.}
PC Temporary Work Co-Ordinator | {insert name} |  |  |  |  | {insert address} |  | {insert email} | {insert tel no.}
Temporary Works Co-ordinator | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Temporary Works Supervisor | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | {insert address} |  | {insert email} | {insert tel no.}
Temporary Works Designer | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Temporary Works Design Checker | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Quality & Business Improvement Manager | Jonathan Dennehy |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | Jonathan.Dennehy@jones-bros.com | 07443265165
Quality Controller (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Document Controller (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Material Buyer | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Plant Administrator (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
CSR Co-ordinator | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
CSR Administrator (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Commissioning Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Commissioning Engineer | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Aftercare Supervisor | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Fire Officer | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 3 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 4 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Mental Health First Aider 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Mental Health First Aider 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Traffic Management Coordinator | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Traffic Management Supervisor | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Project Energy Management Champion (Only if project is valued at over £1 million and/or over 20 weeks in duration) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Other | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | {insert address} |  | {insert email} | {insert tel no.}
1.2) Scope of Works
The A494 River Dee Bridge Deck Over-Slabbing Contingency Scheme is a major maintenance intervention that involves the replacement of the existing road surface with a new reinforced concrete over-slab and combined waterproof and wearing membrane. The works will be contained within the existing footprint of the bridges surface structure and above the existing concrete deck slab. Below deck debris netting will be installed and the top 75mm of the bridge deck, existing kerbs and movement joints removed and disposed off-site. Concrete deck repairs will be carried out and new structural mesh will also be installed across the entire bridge deck. The combined waterproof and wearing membrane shall also be applied to the hard verge and central reserve.
1.3) Project Timescale
Contract Award Date |  |  | {dd/mm/yyyy} |  | Commissioning Start |  |  | {dd/mm/yyyy}
Contract Commencement Date |  |  | {dd/mm/yyyy} |  | Practical Completion |  |  | {dd/mm/yyyy}
Contract Period |  |  | {xx weeks} |  | Take Over Certificate |  |  | {dd/mm/yyyy}
Site Start Date |  |  | {dd/mm/yyyy} |  | Planned Contract Completion |  |  | {dd/mm/yyyy}
SECTION 2 |  |  | PROJECT PLANS
The following Project Plans and Schedules/ Registers are required on this project to support the implementation of this Project Management Plan. Plans indicated in red below are mandatory and must be in place on all Jones Bros projects, with the exception of the Construction Phase Health and Safety Plan which is only required when Jones Bros are fulfilling the role of Principal Contractor. In this instance we would work to the Principal Contractor's Plan. The client and/or nature of the project will define the requirement for other plans.
Plan Title |  | BMS Ref. | Required | Plan Owner |  | Review Frequency |  | Filing Location on Pansophy
(a) Mandatory Plans and Schedules/ Registers
Construction Phase Health and Safety Plan |  | CPP | Y |  |  | Monthly |  | (07.07.1 Preconstruction Health & Safety Plan)
Construction Environmental Management Plan (CEMP) |  | CEMP | Y |  |  | Monthly |  | (07.08.02 Environmental Plan)
Inspection and Test Plan |  | QA-f-002 | Y |  |  | Monthly |  | (07.09.01 Test & Inspection Plan)
Risk Register |  | WW-f-008 | Y |  |  | Monthly |  | (07.08.03 Risk Assessments)
Material Procurement Schedule |  | CO-f-014 | Y |  |  | Monthly |  | (07.10.04 Lookahead Programme)
Sub-Contractor Procurement Schedule |  | CO-f-013 | Y |  |  | Monthly |  | (07.18.03 Orders)
Handover Plan |  |  | Y |  |  | As and When Received |  | (07.09.06 Hand Over Documentation)
(b) Other Plans
Site Waste Management Plan |  | EN-f-010 | Y | Jonathan Maitland |  | Monthly
Traffic Management Plan |  | TMP | Y | Jonathan Maitland |  | Monthly
Emergency Response Plan |  | HS-f-093 | Y | Jonathan Maitland |  | Monthly
SECTION 3 |  |  | PROJECT OBJECTIVES AND PERFORMANCE INDICATORS
(a) Jones Bros company wide Health & Safety, Environmental, Energy and Quality business objectives are set annually and are accessible to the business through the BMS. These will be displayed on the project noticeboards._016).
BP-g-003 - Business Management System Objectives
b) Client specific Key Performance Indicators (KPI) {have/ have not} been specified on this project. {If Client specific indicators are in place consider referencing them in the table below as they will be the measures Jones Bros will be assessed against.}
(c) When setting project specific objectives and performance measures consideration is given to the specific nature and complexity of the project, Client specification, performance requirements and the Jones Bros Company wide objectives.
(d) The person responsible for measuring and reporting progress against targets is | [5 empty] | Insert Name |  | Insert Role
(e) Progress on this project will be monitored {weekly/ monthly} as part of the Project Progress Reporting process. | [7 empty] | CO-f-001 - Project Monthly Report
Explanatory Notes:-
An objective/ indicator is a specific result that a project aims to achieve within a time frame and with available resource, consider those issues that are important to the success of a project and hence these become the key issues that will be tracked and measured. Pay attention to what the Client wants to measure and therefore deems important.
(d) The following project specific objectives will be measured throughout this project:
Project Specific Objective/ Performance Indicator | [5 empty] | Target |  | Method of measurement
(i) Safely - project team to return home safely at the end of each day. | [5 empty] | Zero accidents |  | Monthly accident reporting
(ii) Programme - project delivered on time. | [5 empty] | As per Programme |  | Monthly Progress Reports
(iii) Cost - project delivered within budget (subject to agreed variations and additional works). | [5 empty] | As per Cost Forecast |  | Monthly Progress Reports
(iv) Environmentally - undertake construction with due consideration to stakeholders and environment | [5 empty] | Zero environmental incidents |  | Monthly accident reporting
(v) Quality - deliver construction works in accordance with the specification. | [5 empty] | Zero Defects |  | Complete ITP to satisfy Design Specification - Defects Management Process NCR Process
SECTION 4 |  |  | BEST PRACTICE INITIATIVES
The Jones Bros team have signed up to the following industry best practice initiatives on this project.
Best Practice Initiative | [5 empty] | Registration Links |  | Target Level | Comment
Considerate Constructors - Considerate Contractor Registration (If Required) | [5 empty] | QC-f-020 - Project Details for Considerate Contractors |  | {Bronze/ Silver/ Gold} | Not Required
{BREEAM} | [7 empty] | {Good/ Excellent}
Client & Design/ Design / Design & Construction/ Construction Award {CEEQUAL}
{CE Demonstration Project}
{Others}
SECTION 5 |  |  | PLANNING AND PROGRAMMING
(a) Planning and programming on this project will be administered in accordance with the Jones Bros Project Start Up & Commercial Review Process
PFC033 - Project Start UP & Commercial Review(S)
(b) The person responsible for updating the programme on this project is |  |  |  |  | (Insert Name)
(c) A copy of the construction programme should be located in 07.02 Records/Logs 07.02.09 Plans and Programme
(d) Programmes this will be updated / reviewed at regular intervals throughout the project.
(e ) Frequency of updates will be |  |  | Please Specify:
(e) Copies of programmes will be administered by |  |  | {insert name of person who will provide copies} |  |  |  | with prior approval from the Project Manager.
(f) {Define any Client or Contract specific requirements that will require amendment to or deviations from the Jones Bros Standard Process}
SECTION 6 |  |  | RISK MANAGEMENT
(a) {Based on a review of the contract documentation, insert here a summary of the key commercial and contractual aspects identified on this project. This should include (but not be limited to) the form of contract, the effect of any Client’s amendments, payment terms, any gain share / pain share arrangements and the systems to be used for cost control, tracking, reporting and forecasting.}
(b) Risk Management activities will be conducted in accordance with the Jones Bros Risk and Opportunities Process
Procedure Co-p-017 Notifications, Claims and Quotations
(c) A risk register will be maintained on this project. The register will reside as part of the commercial records for the project and will be administered in line with the review timelines below
WW-f-008 - Project Risk Register Template
(d) The person responsible for administering and maintaining the risk register on this project is: | [6 empty] | (Insert name)
(e) The register will be reviewed |  | Please Specify: |  |  | and when significant change occurs on the project.
(f) For the avoidance of doubt, the contractor shall be responsible for all ground risk involved in the design, procurement and construction of their works.
SECTION 7 |  |  | COMMERCIAL ARRANGEMENTS AND REPORTING
(a) Commercial Management activities on this project will be undertaken in accordance with the relevant Jones Bros Process as identified below.
Process Reference and link | [7 empty] | Responsibility
(i) Contract Administration | [5 empty] | CO-p-005 - Commercial Review & Project Startup |  | (Insert name)
(ii) Risk and Opportunity | [5 empty] | CO-p-005 - Commercial Review & Project Startup |  | (Insert name)
(iii) Variation Orders | [5 empty] | PFC050 - Subcontractor & Supplier Management Process |  | (Insert name)
(iv) Cost Control | [5 empty] | PFC053 - Preparing Cost Plans & Cost-Value Reconciliations |  | (Insert name)
(v) Cost Reporting | [5 empty] | PFC053 - Preparing Cost Plans & Cost-Value Reconciliations |  | (Insert name)
(vi) Cost Forecasting | [5 empty] | PFC053 - Preparing Cost Plans & Cost-Value Reconciliations |  | (Insert name)
(b) The following commercial arrangements have been identified on this project:
Insurance Type |  | Levels Required |  |  | Jones Bros Arrangements for this Project |  |  | Responsibility
Insurances |  | {as specified in the contract} |  |  | {State arrangements in place} |  |  | (Insert name)
Warranty |  | {as specified in the contract} |  |  | {State arrangements in place} |  |  | (Insert name)
Retention |  | {as specified in the contract} |  |  | {State arrangements in place} |  |  | (Insert name)
Guarantees |  | {as specified in the contract} |  |  | {State arrangements in place} |  |  | (Insert name)
{others} |  | {as specified in the contract} |  |  | {State arrangements in place} |  |  | (Insert name)
SECTION 8 |  |  | CONTROL OF DOCUMENTS, DATA AND RECORDS
8.1) IT Infrastructure:
(a) The IT Infrastructure on this project has been established in accordance with the BMS process for Project IT Start-up. This process ensures that the IT arrangements on a given project are effective and appropriate and where necessary are able to dovetail or support access to Client systems.
PFC033 - Project Start UP & Commercial Review
(b) The point of contact for the administration and management of the IT on this project is | [6 empty] | Gerallt Ellis
(c) The IT arrangements and infrastructure implemented on this project are outlined in the Jones Bros IT Logistics Plan which is located in the Project Filing Structure {07.02 Records/Logs 07.02.14 Project IT System Information}
IT-f-001 Site Setting Up Information
(d) {Insert here any project specific requirements/arrangements for the sharing/dovetailing of systems. For example the use of collaborative portals or information sharing platforms. Project teams should consider documenting a project specific protocol around IT Infrastructure relating to document and record management in order that rules and guidance are established and communicated, as standard Jones Bros processes have been written around the Jones Bros Company approach and there is minimal consideration given to other systems, such as Client and Principal Contractor systems, in the standard company processes.}
8.2) Document Control:
(a) The person responsible for the general administration of documents on this project is | [5 empty] | (Insert name)
(b) The person responsible for the administration of drawings on this project is | [5 empty] | (Insert name)
(c) The Jones Bros Master Drawing and Technical Information Register(s) is/are produced to ensure that the permanent works constructed are as per the drawings issued at the time and therefore compliant. On receipt of drawings they will be reviewed checked and distributed in accordance with the arrangements outlined in the Design Plan (Form):
PD-f-005 - Drawing Register
CO-f-003 - Design Management Form
(d) The Drawing and Technical Information Register is located in the Document Store\02 Drawings on pansophy saved against the project
(e) The Drawing and Technical Information Register and a complete set of drawings current and superseded will be archived with the project. The drawings form a key quality record providing traceability and supporting evidence showing that Jones Bros have at all times adhered to the required drawing.
(f) Documents to be kept as “Quality records” are identified on the standard Project Filing Index listed in QC-p-010 - Document Working Procedures. Additional Quality records to be maintained for this project include (list here):
QC-p-010 - Document Working Procedures
(g) Archiving on this project will follow the Jones Bros standard requirements as outlined in the Jones Bros Archive Planning and Allocation Process:
QC-p-001 - Document Archive Management
(h) Specific retention requirements that will be adhered to on this project are also specified on the Project Filing Index
QC-g-009 - Retention Periods for Data
(i) {Insert here a summary of any specific Client or Contract arrangements that have been specified on this project in respect of the management of records and information. Consider those processes that may require amendment to or deviations from the Jones Bros Standard Process}
8.3) Record Control:
(a) Project records are filed in accordance with Jones Bros Process for the Control of Project Records
QC-p-010 - Document Working Procedures
(b) At the close of the project all electronic records including e-mail correspondence for the project will remain on the Jones Bros Document management system and is strictly access controlled. All written paper records will be stored for 12 years post project completion using the Jones Bros document archive process and system:
QC-p-001 - Document Archive Management
(c) {Insert here the project specific arrangements around the management and storage of project related e-mails. It is important to ensure that copies of project related e-mails are stored and archived with the project records as key decisions and agreements are frequently made in e-mails.}
(d) {Insert here project specific arrangements for the management and archive of electronic records. These are records identified on the Project Filing Index as having a primary format as electronic. For example...Electronic records are copied to an external hard drive and taken by the Project Manager each week and copied to the main electronic storage location on the regional server.}
8.4) Mandatory client or other third party documentation requirements:
(a) On this project we {are/ are not} required to work to other contractors procedures.
(b) Any deviation from the Jones Bros BMS is to be approved by the appointed Project Manager. The Jones Bros Quality Manager is to be made aware of the requirements to deviate from the BMS.
Explanatory Notes:-
Amend this text and the table below as appropriate: For minor deviations for example 1 or 2 forms then list them below, however, for major system deviations where we are required to adopt the Client or Principal
contractor Systems then a separate Document Bridging Matrix must be complete during the set-up stage of the project. This document should be communicated to the project team and the Project Manager must ensure that access is granted by the Client Principal Contractor to the required processes and forms.
(d) The following individual documents will be replaced by the principal contractors procedural documentation:
Contractor Procedure/ Form |  |  | Equivalent Jones Bros Procedure/ Form being removed |  |  |  | Location in site filing
SECTION 9 |  |  | PROCUREMENT
(a) Material & Subcontractor procurement Schedules have been produced for this project and is located in Project Filing Structure 07.10.04 Look ahead Programme. These schedules identify key packages and items, the milestone dates for major awards (aligned to the programme) and pricing and budget information:
CO-f-014 - Material Procurement Schedule
CO-f-013 - Sub-Contractor Procurement Schedule
(b) The Procurement Schedule is a key tool to support the effective and timely procurement of key packages of work and commodities throughout the project. It is originated at Tender Stage and then updated as the project moves through its lifecycle.
(c) The person responsible for administering and maintaining the Procurement Schedules on this project is | [7 empty] | (Insert name)
9.1) Material Purchasing:
(a) The person responsible for co-ordinating the purchasing of material on this project is | [5 empty] | (Insert name)
(b) All material purchases on this project will be administered in accordance with the Jones Process for Material Ordering
PFC058 - Material Procurement & Management(S)
(c) Authority levels governing the ability of project teams to purchase materials on a project is embedded in the COINS Procurement system. In accordance with the Materials Ordering Process. All materials are to be requisitioned through the COINS ERP system.
PFC010d - Purchasing Materials(S)
(d) On this project the following people are authorised to raise requisitions for material items:
Name |  |  |  | Position on the project
(Insert name) |  |  |  | Project Manager
(Insert name) |  |  |  | Works Manager
(Insert name) |  |  |  | Foreman 1
(Insert name) |  |  |  | Site Engineer 1
(Insert name) |  |  |  | Quantity Surveyor
{list others as required}
Quantities and Costs. These will be authorised by the following people only, on this project:
Name |  |  |  | Position on the project
(Insert name) |  |  |  | Works Manager
(Insert name) |  |  |  | Foreman 1
(Insert name) |  |  |  | Site Engineer 1
{list others as required}
(f) Material cost returns will be produced to control and manage quantities and cost for bulk call-off items against budget on this project
CO-f-015 - Cost Plan & Cost Value Reconciliation
(g) Material costs will be controlled and reported on this project in accordance with the Jones Bros Cost Control Process
PFC053 - Preparing Cost Plans & Cost-Value Reconciliations(S)
9.2) Plant Hire & Management:
(a) The person responsible for obtaining the plant on this project is: |  |  |  |  | (Insert name)
(b) The person responsible for co-ordinating the plant on this project is: |  |  |  |  | (Insert name)
(c) All plant hire requirements on this project will be administered in accordance with the Jones Bros Process for Plant On-Hire and Plant Off-Hire
PFC067 - Project Plant, Equipment and Labour Planning & Management
(d) Authority levels governing the ability of project teams to hire plant on a project is embedded in the COINS Procurement system. In accordance with the Plant Hire Processes all plant is requisitioned through COINS
(e) On this project the following people are authorised to raise requisitions for the hire of plant items:
Name |  |  |  | Position on the project
Insert Name Person 1 |  |  |  | Position on the project
Insert Name Person 2 |  |  |  | Position on the project
Insert Name Person 3 |  |  |  | Position on the project
(f) A site specific plant hire list is issued weekly for review and updated by the site teams. Copies of these lists are filed in the Project Filing Structure {07.26.02 Resource Forecasts}.
(g) Material costs will be controlled and reported on this project in accordance with the Jones Bros Cost Control Process
PFC053 - Preparing Cost Plans & Cost-Value Reconciliations(S)
9.3) Subcontract Procurement:
(a) The person responsible for managing the preparation of subcontract orders on this project is | [6 empty] | (Insert name)
(b) The selection and appointment of subcontractors is managed in accordance with the Jones Bros Process for Subcontract Procurement Process PFC050 - Subcontract Procurement(S)
PFC050 - Subcontractor & Supplier Management Process
(c) All subcontract packages required on this project are itemised and managed through the Procurement Schedule
CO-f-013 - Sub-Contractor Procurement Schedule
(d) The performance of subcontractors is monitored throughout the project, with issues and resolutions being reviewed monthly as part of the Project Progress
(e) The Project Manager and commercial team will monitor KPI's on key subcontractors. These are completed by the Jones Bros Project team and represent an internal record of performance assessment that will inform future work and appointments.
PFC050 - Subcontractor & Supplier Management Process
SECTION 10 |  |  | CLIENT SUPPLIED PRODUCTS
The following products will be supplied by the client for incorporation into the works:
{Material description here} |  |  |  |  | {Acceptance criteria here}
{Material description here} |  |  |  |  | {Acceptance criteria here}
{Material description here} |  |  |  |  | {Acceptance criteria here}
{Material description here} |  |  |  |  | {Acceptance criteria here}
SECTION 11 |  |  | CUSTOMER FEEDBACK
(a) The views, opinions and feedback of our Client is important to the team. The project team will capture any feedback from the client throughout the project at meetings, and also through formal Client feedback, sought in accordance with Jones Bros Customer Feedback Process
PFC070 - Customer & Project Feedback(S)
(b) {Insert here the specific arrangements agreed on this project that will be implemented in order to assess and obtain feedback on the Jones Bros Project Team Performance. Include specific information relating to whom, what and when feedback will be sought.}
SECTION 12 |  |  | DESIGN MANAGEMENT
a) Jones Bros is/ is not responsible for the management of design on this project. {If Jones Bros is not responsible for design state 'n/a' for (b)}
(b) Jones Bros utilises the external expertise of design consultants to deliver design services to Clients. Design on this project will be managed through the Design Plan all elements of the design process including review, verification, validation and change of design will be outlined in the Design Plan.
PFC028 - Designer Competence Stage One(S) |  |  |  | PFC018 - Subcontract Design(S) |  |  |  | PFC029 - Project Design Management(S)
12.1) Design and Development (design and development may not be required on all projects):
(a) The project specific arrangements for administering and managing design on this project are outlined in the Design Plan which is located in the Document Store\02 Drawings on pansophy saved against the project |  |  |  | File No./ Section No.
(b) The Designer on this project is |  |  | Insert Company Name |  | Lead Contact: |  | (Insert name)
(c) The Jones Bros Design Manager on this projects is |  |  | Dylan Parry
12.2) Design Change (design change is required on all projects)
(a) Changes to the design are controlled in accordance with the Jones Bros Change Control Process and a design change report form:
PFC029 - Project Design Management(S)
PD-f-001 - Design Change Report
(b) Copies of designs before revision are retained in the DLM Document Store\02 Drawings on pansophy saved against the project and clearly marked as superseded.
(c) A master Drawing and Technical Information register will be produced and updated on this project using the Pansophy Project DLM Register Report or using PD-f-005 - Drawing Register
PD-f-005 - Drawing Register
(d) {Insert here a summary any specific Client or contract arrangements that have been specified on this project in respect of the management of design change. Consider those processes that may require amendment to or deviations from the Jones Bros Standard Process}
SECTION 13 |  |  | PROCESS CONTROL
13.1) Works Procedures and Method Statements:
(a) Jones Bros implements an integrated process when assessing risks associated with construction activities. The Task Specific Risk Assessment and Method Statement (RAMS) Process requires the assessment of all risks including Safety, Environment, Quality and Commercial to be considered in relation to the tasks being undertaken.
PFC013 - Risk Assessment Process(S)
(b) A register of RAMS is held in the Project Filing Structure {07.07.03 Risk Assessments} on pansophy saved against the project
HS-f-034 Risk Assessment & Method Statement Register
13.2) Workmanship Inspection and Testing:
(a) Inspection and Test Plan(s) will be used on this project to measure and control the quality of work activities and the resulting project deliverables, in accordance with the Jones Bros Process for preparing a Test & Inspection Plan.
PFC049 - Preparing a Test & Inspection Plan(S)
QA-f-002 - Test & Inspection Plan Template ITP
(b) Quality control methods will include quality assurance of ITPs, work processes, verification and validation, joint reviews, audits, inspections and process assessment, as appropriate.
(c) The ITP will take account of the size and cost of the project and the working methods being used. The level of detail required will inevitably be greater on a large project.
(d) The requirements for ITP's will be defined by the production of Method Statements that identify the key construction activities being undertaken on the project. ITP's will identify the required level of inspection and test against each activity as defined in the contract and/or specification documents.
(e) The ITP's and supporting test results and certificates are located in the Project Filing Structure (07.02 Records / Logs 07.02.07 Quality) on pansophy saved against the project. The use of Baskets to collate phases of quality results is highly recommended (Please speak to the quality manager for advise)
13.3) Temporary Works Control:
(a) Jones Bros {is/ is not}responsible for management and implementation of Temporary Works on this project. {If Jones Bros is not responsible for design state 'n/a for (b)}
(b) A Temporary Works Co-ordinator (TWC) and Temporary Works Supervisors (TWS) have been formally appointed as part of the Jones Bros Project Appointment Process
PFC103 - Managing Temporary Works
Records of appointments will be located in in the Project Filing Structure {07.02.15 Records of Formal Appointments} on pansophy saved against the project
Role |  |  | Name |  |  | Qualification Check Complete (Y/N)
Temporary Works Co-ordinator (TWC) |  |  | (Insert name) |  |  | {Yes/ No - summarise training/ competency}
Temporary Works Supervisor (TWS) |  |  | {insert name} |  |  | {Yes/ No- summarise training/ competency}
(c) Inspection and verification of Temporary Works design is undertaken by | [5 empty] | {insert Company/ Name}
(d) A Temporary Works register has been produced for this project and is located in the Project Filing Structure (07.07.07 Site Inspections & Records) on pansophy saved against the project
HS-f-044 - Temporary Works Register
(e) Temporary Works drawings, drawing registers, design briefs etc. are filed in in the DLM Project Filing Structure (Document Store\02 Drawings) on pansophy against the project |  |  |  |  | File No./ Section No.
13.4) Equipment - Inspection, Testing and Monitoring :
(a) A register is maintained of all calibrated equipment. This register will include those instruments used by Jones Bros and Subcontractors.
QC-f-011 - Equipment and Instrument Calibration Register
(b) Certificates will be obtained confirming calibration status of each item of equipment. These will be checked and filed in the Project Filing Structure (07.02 Records/Logs 07.02.07 Quality) Calibration certificates for Jones Bros Plant and equipment can be obtained from the Plant department Call 01824 703661
(b) Routine checks will also be made in between calibration periods in accordance with the Jones Bros Process PFC017 - Instrument & Equipment Calibration
PFC017 - Instrument & Equipment Calibration
Equipment Listing |  |  |  | Responsibility |  | Frequency | Record Location
Level checks will be carried out and recorded by |  |  |  | (Insert name) |  | Weekly | 07.02 Records/Logs 07.02.07 Quality
Theodolite checks will be carried out and recorded by |  |  |  | (Insert name) |  | Monthly | 07.02 Records/Logs 07.02.07 Quality
Survey audits will be carried out and recorded by |  |  |  | (Insert name) |  | Monthly | 07.02 Records/Logs 07.02.07 Quality
A calibration register is managed by |  |  |  | (Insert name) |  |  | 07.09 Quality 07.09.03 Inspection Reports
Certificates of calibration are held in | [6 empty] | 07.02 Records/Logs 07.02.07 Quality
SECTION 14 |  |  | CONTROL OF NON-CONFORMING PRODUCT
14.1) Rework and defects:
(a) Rework and defects identified are dealt with through the Non-conformity Report (NCR) process
PFC006 - Non-Conformances & Corrective Actions
An NCR is dealt with by completing a non conformance report (NCR)
QC-f-007 - Nonconformity Report - Product
(b) The person responsible for issuing NCR's on this project is |  |  |  |  | (Insert name) |  |  | {insert position}
(c) On completion of each of the Quality Critical Activity and at the end of each Subcontract package of works (as a minimum), any remaining issues are identified on a notification of defect (Snag) form and passed to the appropriate contractor to complete in accordance with the Jones Bros PFC034 - Project Close Out process
PFC034 - Project Close Out
QC-f-007 Non-Conformity Report
14.2) Corrective and Preventive Action:
(a) Copies of NCR's are sent to Subcontractor, Contracts/ Project Manager, Quality Manager and the Site Quantity Surveyor (as appropriate).
(b) Where the NCR involves material the NCR report will be sent to the buyer.
(c) Where a concession is required to incorporate defective goods or materials into the works the NCR report is sent to the client for approval prior to proceeding with any related construction work.
(d) The status of NCR's is monitored using a register by the Site Quality Controller | [7 empty] | (Insert name)
PFC006 - Non-Conformances & Corrective Actions
QC-f-007 Non-Conformity Report
SECTION 15 |  |  | HANDOVER AND AFTERCARE
(a) PFC034 - Project Close Out will detail the activities required for handover of this project, including identifying resources, key dates and deliverables.
(b) All Commissioning, Handover and Aftercare activities on this project will be in accordance with the Jones Bros Processes for Commissioning, Handover and Aftercare process and other linked processes, taking into consideration the requirements of the client and end user which are specified in the contract and relevant project specifications.
PFC034 - Project Close Out
QC-f-039 - Transfer of Control of Area (ToCoA)
CO-f-038 Contract Close Out Check & Sign Off
(c) {Insert here a summary of any specific Client or Contract arrangements that have been specified on this project in respect commissioning, handover and aftercare. Consider those processes that may require amendment to or deviation from the Jones Bros Standard Process}
SECTION 16 |  |  | PROTECTION OF COMPLETED WORKS
(a) Listed below are items of work needing special protection against damage:
Item or Section of Works | [5 empty] | Special measures to be taken
{Item or Section of Works} | [5 empty] | {Special measures to be taken}
{Item or Section of Works} | [5 empty] | {Special measures to be taken}
{Item or Section of Works} | [5 empty] | {Special measures to be taken}
SECTION 17 |  |  | INTERNAL AUDIT
(a) The Jones Bros Quality Manager administers a programme of internal audits across a sample of Jones Bros projects in accordance with the Jones Bros Internal Audit Process
PFC003 - Internal Audit(S)
Master Internal Audit Schedule
(b) The frequency of internal audits are dependent on project complexity, value and risk. On this project audits will be undertaken at a frequency of approximately 1 audit every 3 months.
(c) The auditor for this project is |  | Ellis Ashton
(d) Audit Findings will be closed out within agreed timescales as defined on the audit report. |  |  | Date here
SECTION 18 |  |  | TRAINING AND COMPETENCY
(a) The Training Co-ordinator for this project is Ffion Roberts ffion@jones-bros.com, based at Head Office in Ty-Glyn Ruthin. Call 01824 703661 E-mail Ffion Roberts ffion@jones-bros.com
(b) Competence of personnel is assessed on the basis of appropriate qualification, instruction, training and experience See Roles and Responsibilities descriptions in Document Store\03 Knowledge Area\03.21 HR\03.21.01 Job Role Descriptions. These role description booklets can be used to asses role competence and experience by site a management and line managers.
(c) Quality related instructions are included in method statements which will be the subject of briefings.
(d) Records of competencies are retained in the Head Office in Ty-Glyn Ruthin database, which is compliant with data protection legislation.
TR-f-002 -Master Qualification Matrix
(e) To identify each roles mandatory, as required and career transition training requirements the project management team can refer to the Job role Training Requirements guide
TR-t-001 Job Role Training Requirements Guide
(f) Jones Bros personnel are checked on competence levels prior to appointment and commencement of activities, in accordance with the Jones Bros Process for Recruitment
PFC040 - Recruitment, Interview, Induction and Equipment Issue Process
SECTION 19 |  |  | RECORD REFERENCING MATRIX
Explanatory Notes:-
To support the effective management of projects and remove the potential for duplication of information and effort, all records referred to in this plan are filed in the Jones Bros Project Filing Structure whilst the records are continuing to be update and the project is live. The following matrix supports the navigation and archiving of project records. It enables project teams and third parties (as applicable) to easily navigate the Project Filing Structure.
NOTE: OPERATIONAL CONTROL PROCEDURES PENDING WHICH WILL DEFINE FORMS
Project Management Plan Section Reference | Record Description |  |  |  | BMS Format |  | Project Filing Location
SECTION 20 |  |  | FURTHER GUIDANCE
Further guidance on Quality matters is available from: |  |  |  | Jonathan Dennehy, Quality and Business Improvement Manager Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW Office: Telephone 01824 703661 Mobile: 07443265165
Further guidance on technical matters and temporary works is available from: | [5 empty] | (Insert name)
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content

## CPP
CONSTRUCTION PHASE HEALTH & SAFETY PLAN (CPP)
Project Name: |  | A494 River Dee Bridge Deck over-slabbing Contingency Scheme
Project Number: |  | 21-NM-CHR-003
Project Details
Project Description: |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) have commissioned a project to develop a major maintenance intervention should a critical defect be identified within the A494 River Dee Bridge structure and enable this to be implemented with minimal impact on traffic conditions. The proposed design intervention comprises of removing a depth of existing road surfacing and replacing with a new thin reinforced concrete over-slab with combined waterproof and wearing membrane (hence forth referred to as the ‘over-slabbing works’). Enabling works are required to parts of the central reserve and to the Riverside Way Junction to facilitate contraflow traffic management arrangements during construction. The enabling works consist of construction 2Nr crossovers through the central reserve west of the existing bridge and works to widen the Riverside Way Junction.
Project Location: |  |  | Enter your project location here
Plan Approvals
Written by: |  | Name: | 0 |  | Signature: | 0 |  | Date: | 0
Approved by: |  | Name: | 0 |  | Signature: | 0 |  | Date: | 0
Explanatory Notes:-
Origination: Tender phase origination resides with the Project Manager. Construction Phase update will be the responsibility of the Site Manager.
Approval: Tender phase approval resides with the Contracts Manager or Regional Director. Construction Phase approval will be the responsibility of the Project Manager.
Revision: The plan will be revised to reflect changes that have been made to the product, project or contract, work practices, service provision or Quality Assurance procedures. Where changes are made to the plan an assessment of the impacts of the changes will be carried out and recorded in the Version Control section below.
Version Control
Description of changes |  |  | Date | Revision | Page No. | Comments
Explanatory Notes:-
This Construction Phase Health & Safety Plan will be added to, reviewed and updated as the project develops, further design work is completed, information from subcontractors starting work becomes available, unforeseen circumstances or variations to planned circumstances arise or where the operations management team deem it necessary.
If sections are deemed not applicable DO NOT DELETE. Replace text with 'not applicable on this project'.
CONTENT
Section Ref |  | Content | [5 empty] | Comments
Introduction
1.0 |  | Project Details
| 1.1 | Project Organisation and Resource
| 1.2 | Scope of Works
| 1.3 | Summary of Restrictions Affecting the Works
| 1.4 | Project Timescales
| 1.5 | Notification to HSE
| 1.6 | Site Start-up Checklist
2.0 |  | Management of the Work
| 2.1 | Health and Safety Monitoring
| 2.2 | Communication Methods
| 2.3 | PPE/RPE
| 2.4 | Direction and Co-ordination of Others
| 2.5 | Selection and Appointment of the Supply chain
| 2.6 | Protection of the Public and Site Security
| 2.7 | Site Induction and Training
| 2.8 | Welfare Facilities
| 2.9 | First Aid
| 2.10 | Incident Reporting, Recording and Investigation
| 2.11 | Risk Assessment and Method Statements
| 2.12 | Site Rules
| 2.13 | Drugs and Alcohol
| 2.14 | Mobile Phone Use
| 2.15 | Fire and Emergency Procedures
3.0 |  | Arrangements for Controlling Specific Project Risks
| 3.1 | Pre-construction Information (PCI)
| 3.2 | Delivery and Removal of Materials (including Waste)
| 3.3 | Services, Overhead and Underground Services
| 3.4 | Temporary Structure/ Unstable Structures Identified
| 3.5 | Preventing Falls/ Working at Height
| 3.6 | Scaffolding and Safe Means of Access
| 3.7 | Control of Lifting Operations
| 3.8 | Control of Substances Hazardous to Health (COSHH)
| 3.9 | Manual Handling
| 3.1 | Noise Management
| 3.11 | Maintenance of Plant and Equipment
| 3.12 | Working in Confined Spaces
| 3.13 | Excavations/ Poor Ground Conditions Management/ Wells/ Underground Earthworks/ Tunnels
| 3.14 | Work on or Near Water/ Diving Operations/ Caisson etc. other risks of drowning
| 3.15 | Traffic Routes/ Segregation
| 3.16 | Storage Materials and Management
| 3.17 | Off Site Fire Risks
| 3.18 | Health Risks
4.0 |  | Arrangements for Compiling the Health and Safety File
5.0 |  | Record Referencing Matrix
6.0 |  | Further Guidance
Explanatory Notes:-
In this template Plan, guidance and sample content is included where deemed necessary. This is indicated by the inclusion of yellow boxes with text in brackets { }. On completing this plan all sample and guidance text should be deleted or overwritten as required.
Introduction CPP
(a) This Construction Phase Health and Safety Plan had been prepared specifically for this project in accordance with the CDM Approved Code of Practice and the Jones Bros Health, Safety and Environmental Processes.
(b) The aim of this Construction Phase Health and Safety Plan is to provide clear, concise and specific information required to manage the works and the arrangements for controlling significant project specific site risks.
(c) We are committed to providing a safe place of work and continually review our Safety, Health and Environment (HSE) Processes to provide clear and relevant information through all stages of the project’s life.
(d) This plan has been formulated by taking in to consideration the pre-construction information provided by the client, Principal Designer, designers and following surveys and risk assessment of the environment by the site management team responsible for this project.
(e) The Jones Bros Health, Safety and Environmental (HSE) Processes represent the core arrangements for managing Health and Safety across all Jones Bros operations. In addition, the wider Business Management System (BMS) assists the site management team in the planning, management of, recording and communicating of relevant Health and Safety information to provide a safe place of work, safe systems of work and to provide uniformity and consistency in the management of Health and Safety.
(b) This plan is mandated as part of the Jones Bros BMS and is therefore required to be in place and kept up to date through the project, EXCEPT when Jones Bros are not fulfilling the role of Principal Contractor. In this instance we would work to the Principal Contractors Plan.
(f) Every project will have access to the Jones Bros Health, Safety and Environmental Processes, i.e. Company document management system (Pansophy), or hard copy, as appropriate to the IT available at the workplace.
(g) The Company HSE Process for Construction, Design and Management outlines how Jones Bros manage the CDM process.
PFC056 - Project Set Up - Health & Safety
HS-p-026 - Construction Design Management CDM Procedures
(h) We aim to reduce the provision of generic information and to only provide in this Plan and all other associated plans project specific information that should help with the communication and risk management of this project. Other non-project specific information referenced in this plan will be clearly identified with the location where it is available. If there is a need to review these documents they will be provided on request.
SECTION 1 CPP |  |  | PROJECT DETAILS
1.1) Project Organisation and Resource CPP
(a) Specific Project HSEQ Responsibilities for this project have been defined on the Project Appointment Matrix and relevant specialist appointment letters.
Project Roles & Responsibilities Matrix
(b) Appointments will be reviewed and updated throughout the project, reflecting any changes or movement in the project as required. Changes in appointments will be administered through this document and all Roles and Responsibilities briefed to the individual
Role |  | Company |  | Address |  | E-mail |  | Telephone
Client |  | The North and Mid Wales Trunk Road Agent (NMWTRA) |  | Insert Address |  | {insert email} |  | {insert tel no.}
Principal Designer |  | Insert Company Name |  | Insert Address |  | {insert email} |  | {insert tel no.}
Designer |  | Insert Company Name |  | Insert Company Name |  | {insert email} |  | {insert tel no.}
Architect |  | {insert company} |  | {insert address} |  | {insert email} |  | {insert tel no.}
Principal Contractor |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} |  | {insert tel no.}
1.2) Scope of Works CPP
The A494 River Dee Bridge Deck Over-Slabbing Contingency Scheme is a major maintenance intervention that involves the replacement of the existing road surface with a new reinforced concrete over-slab and combined waterproof and wearing membrane. The works will be contained within the existing footprint of the bridges surface structure and above the existing concrete deck slab. Below deck debris netting will be installed and the top 75mm of the bridge deck, existing kerbs and movement joints removed and disposed off-site. Concrete deck repairs will be carried out and new structural mesh will also be installed across the entire bridge deck. The combined waterproof and wearing membrane shall also be applied to the hard verge and central reserve.
1.3) Summary of Restrictions Affecting the Works CPP
{Include information outlining any constraints affecting the works. It should address any third party interfaces and who is responsible for the management and control of these interfaces. For example......The existing facility will be in full operation during the construction of the extension and full access must be maintained at all times to and from the building (including the open service area to the east of the building) for vehicular and pedestrian traffic. All fire exits and routes of escape must also be kept clear at all times.}
1.4) Project Timescale CPP
Contract Award Date |  |  | {dd/mm/yyyy} |  | Planned Contract Completion |  |  | {dd/mm/yyyy}
Contract Commencement Date |  |  | {dd/mm/yyyy} |  | Form F10 (Rev) Date Submitted (copy of F10 is displayed on noticeboard)
Contract Period |  |  | {xx weeks}
Site Start Date |  |  | {dd/mm/yyyy}
The normal hours of work are as follows:
Monday to Friday: |  |  | 07:00 - 19:00
Saturday: |  |  | 07:00 - 13:00
Sunday: |  |  | No Sunday Working
1.5) Notification to HSE
The Client or Principal Designer has the responsibility of notifying the HSE and the generation of the F10. A copy of HSE Form F10 is displayed in site offices on the HSE Noticeboard. This will be reviewed and updated in liaison with the Client or Principal Designer as required through the project.
1.6) Site Start-up Checklist
Prior to the Works commencing, the Site Manager will complete the necessary Start Up Processes, documented in the Jones Bros BMS and as detailed on the Site Start-up Checklist form. On completion, this form is filed in the Project Filing Structure (07.07.1 Preconstruction Health & Safety Plan) and a copy sent to the HSE Manager.
PFC056 - Site Set Up & Maintenance - Health & Safety
HS-f-100 Setting Up Site Safety Checklist.
SECTION 2 CPP |  |  | MANAGEMENT OF THE WORK
2.1) Health & Safety Monitoring
(a) Monitoring will be carried out on this project in accordance with the Jones Bros process for Measuring and Monitoring Health and Safety Performance
PFC030 - Workplace Inspections(S)
PFC015 - Preparing a WM Foremans Inspection Plan
PFC056 - Site Set Up & Maintenance - Health & Safety
(b) Copies of all Health and Safety monitoring carried out on this project by the site team, the Jones Bros management team, the HSE Advisor, HSE Auditor or by a contractor’s Health and Safety team/representative will be held in the located in the Document Stores 07.02 Records / Logs 07.02.05 Health & Safety and 07.07 Health and Safety 07.07.07 Site Inspections & Records saved against the project
(c) The names below are responsible for Daily/Weekly and Monthly Site HSE checks (additional daily and weekly checks will be required if being used for Cambrian Quarry sites please refer to PFC015 - Preparing a WM Foremans Inspection Plan and PFC056 - Site Set Up & Maintenance - Health & Safety above)
Daily/Weekly HSE Checks |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email}
|  | Daily Delete or add as required (Mandatory must be completed) HS-a-043 - Excavations: Daily Check (Mandatory) HS-a-018 - H&S - Work Stopped for Day: Check (Mandatory) EN-a-001 - Environment Inspection: Daily Check (Mandatory) EN-a-002 - Environment Daily Generator Fuel Recording (Mandatory) |  |  |  |  | Weekly Delete or add as required (Mandatory must be completed) HS-a-002 - Safe Place of Work: Weekly Check (Mandatory)
Available When Required Checks HS-a-023 - Ladder Inspection Record HS-a-029 - Hand-Arm and Whole-Body Vibration Assessment and Monitoring HS-a-033 - Temporary Works Foundation Check HS-a-034 - Falsework Structure Check HS-a-035 - Falsework Timber HS-a-036 - Work Equipment Inspection Report HS-a-050 - HS - Point of Works Risk Assessment HS-a-062 - Mobile Scaffold - Daily Inspection HS-a-045 - Fall Arrest Equipment Pre-use Checks HS-a-048 - HSE Noise Monitoring Record HS-a-015 - Scaffolds: Weekly Check HS-a-019 - Roof Work: Weekly Check HS-a-008 - Noise Weekly Checklist EN-a-003 - Environment - Daily - Watercourse Monitoring Record (Site Specific) EN-a-004 - Environment - Daily Air Quality Monitoring Record (Site Specific) QC-a-001 - Quality Control - Instrument Check QC-a-002 - Quality Control - Machine Control Check
Daily/Weekly HSE Checks |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email}
|  | Daily Delete or add as required (Mandatory must be completed) HS-a-043 - Excavations: Daily Check (Mandatory) HS-a-018 - H&S - Work Stopped for Day: Check (Mandatory) EN-a-001 - Environment Inspection: Daily Check (Mandatory) EN-a-002 - Environment Daily Generator Fuel Recording (Mandatory) |  |  |  |  | Weekly Delete or add as required (Mandatory must be completed) HS-a-002 - Safe Place of Work: Weekly Check (Mandatory)
Available When Required Checks HS-a-023 - Ladder Inspection Record HS-a-029 - Hand-Arm and Whole-Body Vibration Assessment and Monitoring HS-a-033 - Temporary Works Foundation Check HS-a-034 - Falsework Structure Check HS-a-035 - Falsework Timber HS-a-036 - Work Equipment Inspection Report HS-a-050 - HS - Point of Works Risk Assessment HS-a-062 - Mobile Scaffold - Daily Inspection HS-a-045 - Fall Arrest Equipment Pre-use Checks HS-a-048 - HSE Noise Monitoring Record HS-a-015 - Scaffolds: Weekly Check HS-a-019 - Roof Work: Weekly Check HS-a-008 - Noise Weekly Checklist EN-a-003 - Environment - Daily - Watercourse Monitoring Record (Site Specific) EN-a-004 - Environment - Daily Air Quality Monitoring Record (Site Specific) QC-a-001 - Quality Control - Instrument Check QC-a-002 - Quality Control - Machine Control Check
Daily/Weekly HSE Checks |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email}
|  | Daily Delete or add as required (Mandatory must be completed) HS-a-043 - Excavations: Daily Check (Mandatory) HS-a-018 - H&S - Work Stopped for Day: Check (Mandatory) EN-a-001 - Environment Inspection: Daily Check (Mandatory) EN-a-002 - Environment Daily Generator Fuel Recording (Mandatory) |  |  |  |  | Weekly Delete or add as required (Mandatory must be completed) HS-a-002 - Safe Place of Work: Weekly Check (Mandatory)
Available When Required Checks HS-a-023 - Ladder Inspection Record HS-a-029 - Hand-Arm and Whole-Body Vibration Assessment and Monitoring HS-a-033 - Temporary Works Foundation Check HS-a-034 - Falsework Structure Check HS-a-035 - Falsework Timber HS-a-036 - Work Equipment Inspection Report HS-a-050 - HS - Point of Works Risk Assessment HS-a-062 - Mobile Scaffold - Daily Inspection HS-a-045 - Fall Arrest Equipment Pre-use Checks HS-a-048 - HSE Noise Monitoring Record HS-a-015 - Scaffolds: Weekly Check HS-a-019 - Roof Work: Weekly Check HS-a-008 - Noise Weekly Checklist EN-a-003 - Environment - Daily - Watercourse Monitoring Record (Site Specific) EN-a-004 - Environment - Daily Air Quality Monitoring Record (Site Specific) QC-a-001 - Quality Control - Instrument Check QC-a-002 - Quality Control - Machine Control Check
(d) In addition to self monitoring, that will be carried out by members of the site management team in accordance with the responsibilities allocated to them to meet legal statutory requirements and Jones Bros HSE Processes, the site will be monitored by a professional and qualified HSE Advisor with a Site Safety and Environmental Review Forms provided at each visit. Senior Jones Bros Management teams also carry out periodic inspections of sites. Jones Bros also use the services of the Building Safety Group (BSG) to carry out Health & Safety inspections on site
HS-a-021 - H&S - Site Inspection Report (Available on the Pim App) (For use by the Jones Bros HSE Team only)
HS-a-025 - H&S - Senior Managers Tour (Available on the Pim App)
EN-a-007 - Environment - Site Inspection Report (Available on the Pim App) (For use by the Jones Bros HSE Team only)
(e) In addition to visiting site on a regular basis the HSE Advisor will provide Health and Safety support as requested or deemed necessary.
(f) Actions identified as a result of inspections will be reviewed and closed out promptly by the relevant members of the project team.
The regional HSE Advisor is:
Name: |  | Michael Jolley |  |  |  | Telephone No: | 07795 648184
2.2) Communication Methods
(a) Company methods of communication that the project must comply with, as applicable, are clearly laid out in the Internal Communication plan process
BP-p-003 - Communication Plan
(b) The project shall have a Health and Safety notice board established in accordance with Jones Bros Site set up procedures
HS-p-011 - Setting Up Site
(c) The project specific methods of effective communication are recorded in the Jones Bros Communication plan. All persons will be advised of the selected methods for the project during Site induction
BP-p-003 - Communication Plan
HS-f-088 - Site Induction Slide Template | [5 empty] | HS-f-088a Visitors Site Induction Slide Template
Site Inductions are recorded on forms:
HS-f-020 - Site Induction Form | [5 empty] | HS-f-020a Visitors Site Induction Form
or PIM Mobile App Forms HS-a-022 Site Induction or HS-a-022a Site Visitors Induction Form
All Inductions will be registered on the induction register:
HS-f-019 - Induction Register
(d) The attendance of Site Safety Forums is obligatory by contractors; other persons will be invited to attend as appropriate.
(e) Additional meetings will be held as deemed necessary throughout the project. For example these may be triggered by issues relating to changes in design that need to be communicated to contractors. Contractors will be invited to these additional meetings as appropriate where the issues will be discussed and copies of relevant/ revised documents will be made available.
(f) Toolbox Talks, Risk & Method Statement briefings and daily site briefings are important methods of consultation with the workforce; Jones Bros also operates an “open door” policy on all projects
HS-f-001 - Daily Briefing (To record all daily briefings on site including Near misses, Unsafe Acts, Safe Observations, Key Risks and daily activities)
HS-f-035 - Toolbox Talk Form (toolbox talk template)
HSEQ Toolbox Talk Index (Contains a list with links to all previously delivered Health & Safety and Environmental toolbox talks)
HSEQ Alert Index (Contains a list with links to all previously delivered Health & Safety and Environmental alerts)
HS-f-007 - Briefing Register (For all RAMS, Toolbox, COSHH Alerts Permit to Works and More Briefings)
All daily briefing records will be saved in 07 Project Administration\07.07 Health and Safety\07.07.16 Daily Briefings against the project
PFC013 - Risk Assessment Process(S)
PFC056 - Site Set Up & Maintenance - Health & Safety
RAMS briefings will always be recorded on
HS-f-084 - Risk Assessment and Method Statement |  |  |  | or briefing register
Task briefings will always be recorded on
HS -123 Task Briefing Sheet
HS-f-007 - Briefing Register (For all RAMS, Task Briefings, Toolbox, COSHH Alerts Permit to Works and More Briefings)
All RAMS/Task Briefings will be saved against the project in document pool 07.07 Health & Safety 07.07.03 Risk Assessments
Where required, translators will be provided for Non-English Speaking Workforce.
RAMS, Task Briefings, Daily Briefings and Toolbox Talks & Alerts will be conducted by:
Name: |  | Insert Name |  |  |  | Telephone No:
Name: |  | Insert Name |  |  |  | Telephone No:
The following methods of communication (not generic) are applied on this project for the following:
Client: |  |  |  | Information requested by the Client to be provided as required. Regular Progress Meetings to include relevant Agenda items covering Health & Safety issues. Reports and minutes will be held in the Project Filing Structure (07.04 Minutes 07.04.03 Client Meeting) against the project. The PC and Client will carry undertake formal monthly meetings where health & safety, progress, issues and concerns and design amendments shall be discussed and recorded. It will be the responsibility of the Client with backing of the PC to liaise with the Local Authority in regards to planning issues or public enquiries
The exchange of Health and Safety information between contractors: |  |  |  | Information regarding Health and Safety will be exchanged on the project in a number of ways :- 1. Health & Safety Plan; 2. Method Statements; 3. Risk Assessments; 4. Safety and Environmental Alerts; 5. Daily Briefings; 6. Safety Forums; 7. Toolbox Talks; 8. Panel of Enquiries; 8. Correspondence (letters, memos); 9. Minutes of meetings Copies of all risk assessments / method statements / COSHH statements from all sub-contractors expected to work on the project will be approved by the site management team and filed in the construction phase plan or associated file. All relevant workers will be informed of the hazards and risks on site that could affect them, this will be done in either site induction or through the medium of tool box talks. Any information that is required for the health and safety file will be handed by the sub-contractor to Jones Bros site management for inclusion into the health and safety file. Daily informal meetings will take place between Jones bros and other contractors with regard to the general running of the site including expected activities, deliveries, interaction of workers etc that will be expected to take place of the day. All subcontractors will undergo a site specific induction before they start work on site. Subcontractors are also expected to sign in and out of site. Everyone on site including subcontractors should be encouraged to take an active interest in safety issues. Everyone should be given the chance to express views or concerns It is the responsibility of all parties on site to communicate with each other with regard to identified hazards, risks and precautionary measures. It is the responsibility of Jones Bros and subcontractor to communicate with each other and report any shortfalls in health and safety procedures.
Third Parties: |  |  |  | The project team will deal with all communications from Third Parties promptly and make a record of all actions taken to deal with complaints regarding Health & Safety. Records will be held in the Project Filing Structure (07 Project Administration 07.01 Project Correspondence) against the project Daily informal meetings will take place between Jones bros and other contractors with regard to the general running of the site including expected activities, deliveries, interaction of workers etc that will be expected to take place of the day. Daily meetings will be conducted with the ecological clerk of works for the project and an environmental watercourse register updated daily to include for any advice or issues raised. Weekly coordination meetings will be undertaken by all contractors and third parties carrying out activities on site. Progress, health and safety and coordination of activities to be discussed as well as any other business. This will be conducted on Friday morning to reflect on the week and plan for the next. Archaeological monitoring will be required on the project and a watching brief will be conducted when excavating in this area. As PC, Jones Bros will inform the relevant parties well in advance off the excavation works, giving the timescales we plan to carry out the works in these areas to provide sufficient time for an archaeological clerk of works to be obtained and prepare for the site.
Handling Design Changes: |  |  |  | Design Change will be managed and communicated in accordance with the Jones Bros Design Change Process:
PFC029 - Project Design Management(S)
Jones Bros will liaise regularly with the designers regarding design carried out during the construction phase, including any designs by a specialist contractor. A drawing register will be compiled to control the issue of design information to relevant contractors and members of the project team. This will be monitored by the Contracts Manager. Design meetings will be held pre-construction and during construction as necessary. These will be attended by the Designers and as required by the Client and Contractors. Any changes to the initial design or additional design works which may include temporary works will be reviewed in regards to the health and safety aspects of the construction. The lead designer will be informed of any temporary works designs that may be required in order for the construction works to progress, so that this information can be communicated to other designers on the project. Design changes will also be managed via the contract procedures and forms. Any specific arrangements for this project will be outlined in the:
CO-f-003 - Design Management Form
Include any other project specific methods as appropriate: |  |  |  | Enter Information here like below: At the site induction it will be made clear that Jones Bros want to actively engage with the workforce on the project for feedback on near misses, ideas to improve health and safety on the site, and to install a better attitude towards health & safety culture on the project. The workforce will be informed of their responsibility to submit Incident Prevention Cards (IPC) to inform management of good and bad practice that they have identified on site. This will help to identify trends and create a positive safety culture. The outcomes of the observations will be communicated with the workforce to let them know what steps have been taken as a result. It is important that supervisors on the project convey all health and safety information to their team working on the site, and that they receive comments on the risk assessments and method statements that must be provided and explained to the workforce prior to the activity starting. Prior to undertaking any activity the workforce will be briefed on the relevant risk assessment and method statement associated, as well as any further documentation that may aid the safe and successful completion of the activity. Toolbox talks, both company wide and site specific, will be carried out during the life of the project, these will be for all personnel on site. Safety Induction will be given to all personnel attending site. A delivery driver site induction will also be implemented on site that will be specific to deliveries made on site.
2.3) PPE/RPE
(a) Standard PPE/RPE of Hard Hat, High Visibility Clothing and safety footwear will be issued to all personnel. Additional PPE/RPE to be issued to specific personnel based on the Risk Assessment produced for a specific task. Refer to PPE procedures
PFC037 - PPE Work Wear Requisitioning & Issue(S)
HS-f-014 PPE Workwear Requisition & Issue Record Form
HS-a-058G - HS - PPE Workwear Requisition - Replenishment (JB) (Available on the PIM application)
HS-a-058H - HS - PPE Workwear Requisition - Replenishment (Cambrian) (Available on the PIM application)
(b) A record is kept of all issued PPE/RPE is to be kept against each employees HR record and any project specific issues saved in 07.02 Record/Logs 07.02.12 PPE Issue & Receipt against the project
(c) All project specific PPE packages received on site are to be recorded using Mobile Custom Form HS-a-049 - H&S - PPE/WorkWear Order Site Receipt
2.4) Direction and Co-ordination of Others
(a) All Suppliers and Sub-contractors are informed of their HSE responsibilities, and their capabilities are checked as part of the Subcontract Procurement process, prior to them arriving on site through pre-start meetings and as part of the order placement process.
PPFC050 - Subcontractor & Supplier Management Process
(b) The Supplier and Sub-contractors are responsible for ensuring their own work meets the required standards in Health and Safety. If the Supplier is found to be lacking in this regard then they must be informed, at first verbally and then if it continues in writing. Further transgressions will result in a prohibition notice being issued.
(c) The Principal Contractor will ensure that the Sub-contractors on the project conform to all necessary regulations, legislation and processes.
(d) Prior to carrying out work, all employees and subcontractors are required to attend Site Inductions. Once on site they are required to attend co-ordination/progress meetings as defined by the site team.
PFC056 - Site Set Up & Maintenance - Health & Safety
2.5) Selection and Appointment of the Supply chain
(a) The competency and capability of all Sub-contractors is evaluated prior to selection in accordance with the Jones Bros Subcontractor Procurement Process
PPFC050 - Subcontractor & Supplier Management Process
The following additional methods of evaluation will be used on this project:-
Designers: |  |  | Prior to appointment all Designers will be included on the Jones Bros approved subcontractor database having completed:
PFC018 - Subcontract Design(S) |  |  | HS-f-046 - Designer Stage Two Assessment Form
Sub-Contractors (PRC_PR_000): |  |  | Prior to appointment all Sub-contractors will be included on the Jones Bros approved subcontractor database having complete a:
PPFC050 - Subcontractor & Supplier Management Process |  |  | FI-f-001 - New Subcontractor Form
The method of work is signed up to as part of the Subcontract Pre-award Meeting, this meeting outlines the contract requirements and follows a standards agenda
CO-f-005 - Subcontract Management Form
Before a Sub-contractor arrives on site they are informed in meetings of what is required of them and what identified risks there are currently on site. A method statement with risk assessments is required from the contractor prior to starting work. This will be reviewed by Site Management to make sure all the HSE requirements are met. This will be recorded on:
HS-f-065 - Documentation Appraisal Form
If any new contractor has any risks associated with their work then all current parties on site will be informed. The Client will be kept informed at all times through progress meetings and the production of method statements and risk assessments. All subcontractors' performance will be reviewed on the project using:
QC-f-015 - Subcontractor Performance Monitoring
Material Suppliers: |  |  | Material Suppliers will provide COSHH information, instructions for use etc. as appropriate. Method statements are required for lifting and delivery. Proof of competence of drivers for specific loads will be requested, as required. High risk supplier's performance will be reviewed on the project using:
QC-f-040 - Supplier Performance Monitoring
Plant and Machinery Suppliers: |  |  | Plant and Machinery suppliers will provide proof of competence of drivers, as required. Certification for Plant and Machinery and all associated lifting equipment will be provided on delivery.
Others, please specify.
Records of contractor evaluations are stored against the subcontractor name in the company COINS system. For more advice or access speak to the Jones Bros Procurement Officer (Amanda Marten).
2.6) Protection of the Public and Site Security
(a) The minimum standards for ensuring protection of the public and a secure site are identified in the Jones Bros protecting the public procedures document
HS-p-014 - Protecting the Public
(b) Security of the site is paramount both in terms of protecting the public and securing the site from trespassers and intruders.
(c) {Insert here the security requirements or reference where the site security risk assessment can be found which should include project specific security measures not generic information. i.e. type of fencing, signing in procedures, employment of security personnel, alarm systems, provision of gateman, provision of lockable cabins how many, etc.}
2.7) Site Induction and Training
(a) No one is allowed to work on site without first receiving and understanding a site specific health and safety induction. The site induction includes information on the hazards and the controls put in place to eliminate / reduce the risk that have been identified by the site specific risk assessments, specific site rules, emergency procedures and the identification of nominated contacts. Project specific site inductions and toolbox talks shall be carried out for all persons working on site. A site specific induction will be produced as a presentation to operatives and will be delivered by the Site Foreman prior to the individual being allowed to start work on site. Inductions will be arranged by the site agents and delivered by one of the site management team in the meeting room of the site compound. Inductions will take place at 08:00am on weekdays. Each individual completes a site induction form and this form is filed on site in either the Construction phase plan or an associated file. This form is then archived for 5 years after completion of the project before being disposed of. Visitors to site will receive a shorter induction if they are to be accompanied – otherwise the full site induction will be presented. A delivery driver site induction will also be implemented on site that will be specific to deliveries made on site. Operatives will be provided with on-site training for specific activities as required. Additional safety aspects of all operations will be delivered via toolbox talks by the Site Foreman. Face to face communication of safe working methods is considered to be a far more effective method of communication than the provision of documents. Project specific site inductions are carried out for all persons required to work on site in accordance with
PFC056 - Site Set Up & Maintenance - Health & Safety
HS-p-001 - Managing Health & Safety at Work
HS-f-088 - Site Induction Slide Template | [5 empty] | HS-f-088a Visitors Site Induction Slide Template
Available Site Induction Videos all available on the Jones Bros Pansophy System and viewable on Microsoft Teams
Induction Video Microsoft Stream Teams link
HS-g-023 - Site Rules, Welfare & Housekeeping (VIDEO) HS-g-016 - JB Site Health, Safety and Environment Induction (VIDEO) HS-g-002 - JB PPIZ Compilation (VIDEO) HS-g-004 - JB Mobile Phone (VIDEO) HS-g-005 - JB Cameras & Mirrors (VIDEO) HS-g-006 - JB Speeding (VIDEO) HS-g-007 - JB Challenging Behaviour (VIDEO) HS-g-017 - JB Landfill Construction Projects Site Induction (VIDEO) HS-g-020 - JB Coastal Defence Induction (VIDEO) (if applicable) HS-t-004 – Operating Instructions ADTs (incl. tipping) HS-g-022 - WWT Working at Height (VIDEO) HS-g-024 - WWT Workplace Transport Video HS-g-025 - WWT Hazardous Dust Video HS-g-021 - WWT Manual Handling Video
They are recorded using the Site Induction Forms:_000).
HS-f-020 - Site Induction Form (paper form) | [5 empty] | HS-f-020a Visitors Site Induction Form
or PIM Mobile App Forms HS-a-022 Site Induction or HS-a-022a Visitors Site Induction
All Inductions will be registered on:
HS-f-019 - Induction Register
(b) All visitors and delivery drivers will received a visitors site induction.
(c) Site specific training requirements such as toolbox talks will be delivered by a works manager or foreman in accordance with
HS-p-001 - Managing Health & Safety at Work
and recorded using
HS-f-035 - Toolbox Talk Form (toolbox talk template)
and registered on a
HS-f-007 - Briefing Register (For all RAMS, Toolbox, COSHH Alerts Permit to Works and More Briefings)
A copy of the site specific induction for this project and the records of induction and site specific training carried out are located in the Project Filing Structure {07 Project administration 07.02 Record & Logs 07.02.10 Site Inductions}. These records will be maintained securely as part of the company data protection policy.
(d) The competency levels of persons will be identified prior to the commencement of the project and persons provided with the appropriate training on the tasks to be undertaken. Refer to the TR-t-001 Job Role Training Requirements Guide for guidance on each roles required competencies. As a basic minimum all personnel including contractors will be required to have a valid CPCS, CSCS or safety passport card, where specialist training is required for the activity they are undertaking on site then further training certification may be required. This will be confirmed on a case by case basis.
TR-t-001 Job Role Training Requirements Guide
For a list of current competencies refer to:
TR-f-002 -Master Qualification Matrix
To identify the general roles and responsibilities for all roles on site see the Job role descriptions in the business management system (Pansophy) (Document pool 03 knowledge 03.21 HR 03.21.01 Job Role Descriptions)
Where additional training is identified during Health and Safety planning, or individual’s performance development reviews, this will be arranged in consultation with the Jones Bros Training and Work Force Manager
(e) Site Personnel will be provided with on-site training for specific activities. Safety aspects of all operations will be discussed prior to commencing via RAMS/task briefings or toolbox talks.
(f) The competency via the training matrix levels for personnel operating equipment, plant etc. whilst working on the site will be checked by the site management team and copies of any formal training certificates will be kept on site until the work is completed, they are located in the Knowledge area of the Business Management System under (Document pool 03 knowledge 03.19 Training Certificates)
(g) We are committed to achieving a fully qualified workforce (CSCS or equivalent). In addition, the competency levels for persons on this project are in line with the Competency Training Matrix provided in the BMSHR_GN_000).
TR-t-001 Job Role Training Requirements Guide
h) {Outline any Client, Contract or Project specific requirements that will require amendment to or deviations from the Jones Bros Standard Processes}
Identify here any project competencies required in addition to those stated in the Jones Bros TR-t-001 Job Role Training Requirements Guide
TR-t-001 Job Role Training Requirements Guide
2.8) Welfare Facilities
(a) The minimum standards to be complied with are included in the Jones Bros setting up site procedures on the BMS
HS-p-011 - Setting Up Site
(b) The welfare facilities provided on this site will be shared with the subcontractors.
(c) The welfare facilities provided for this project
{either complete the list below deleting if not applicable or refer to where a list of project specific welfare equipment is located. (Not generic provisions) - DELETE THIS TEXT}
Maximum No. of persons on site:
No. and type of toilets:
No. of Mess Rooms:
No. of Drying Rooms:
No. of Shower Rooms:
Type of Water Supply:
Equipment for heating food:
Equipment for drinks:
Method of heating:
Type of lighting:
Housekeeping Arrangements:
Provision of catering facilities:
Others:
2.9) First Aid
(a) The number of appointed first aiders and appointed persons for this project is... {identify whether first aider / appointed person or both and include number of each}. The names of first aiders and location of first aid equipment is identified on the Project Responsibility Matrix
Project Roles & Responsibilities
They are also to be included on the Emergency Notice for this project that is displayed on the project’s Health and Safety notice board. These persons will also be identified to all employees during their induction will be identified by green cross stickers on helmets.
(b) The first aid boxes and eye wash facilities will be re-filled after each use, visibly checked each week during the weekly inspections and monthly checks carried out and recorded by the person identified on the site responsibility checklist
Project Roles & Responsibilities
(c) The first aid requirements for this project have been specifically risk assessed for the type of work and numbers of persons. The project specific first aid assessment can be located in the Project Filing Structure {07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments}.
No. of first aid boxes & size:
Location of first aid boxes:
Location of eye wash station:
Stretchers:
Blankets:
Resuscitation Equipment Other as applicable
2.10) Incident Reporting, Recording and Investigation
(a) Incident reporting will be carried out using the Jones Bros BMS Incident Notification Process:
PFC025 - Incident Prevention, Notification Reporting Process
Incident investigation is in line with the requirements outlined in the Jones Bros BMS Investigation Reporting Process
PFC027 - Investigation Reporting
All incidents, including environmental incidents and all near misses, will be notified using mobile custom form:
HS-a-020 - H&S - Incident Notification Form (Available on the PIM mobile application)
All Investigations will be conducted using form All reports will be filed against the project in an access controlled document pool (07 Project Administration\07.07 Health and Safety\07.07.13 Incidents and Investigations)
QC-f-030 - Investigation Report
(b) All incidents will be reported immediately to the HSE Department by telephone and using the HS-a-020 - H&S - Incident Notification Form (Available on the PIM mobile application)
(c) All incidents will be investigated, the person undertaking the investigation and the type of investigation will depend upon the severity or potential severity.
(d) The requirement to report all incidents, method of recording and location of blank incident reporting sheets will be communicated to persons working on the project during the site induction.
(e) The responsibility for reporting RIDDOR incidents rests with HSE Department.
(f) Where any Incident is reportable to the Health and Safety Executive the employer of the injured person will be responsible for ensuring it is reported. A copy of the F2508 will be filed (confidentially) on the site. Where a contractor does not provide evidence of reporting to the Health and Safety Executive the project’s site management team will make contact with the Jones Bros HSE Manager for guidance.
(g) Investigations will be carried out and risk assessment reviews undertaken following the investigation. Where lessons can be learnt Safety Alerts, Toolbox Talks, Information Sheets or other appropriate media will be used to communicate the information across Jones Bros.
(h) Significant near misses will be treated in the same manner as an Incident with appropriate investigations undertaken and reported in accordance with the Jones Bros process
PFC025 - Incident Prevention, Notification Reporting Process
(i) All near misses will be recorded using the Jones Bros Incident Prevention and control process above and using:
HS-a-020 - H&S - Incident Notification Form (Available on the PIM mobile application)
When any one on site identifies an Improvement Suggestion, Good Practice/Safe Act, Unsafe Act, Unsafe Condition, Unsafe Procedure, Environment they will follow the incident prevention and notification reporting process above but will report the using an incident prevention paper card available on in the compound office or by using the HS-a051 H&S incident prevention card custom form available on the PIM application.
HS-f-094 - Together Safer Incident Prevention Card Template
or by using the custom form available on the mobile app that can be set to notify all interested parties on site and in the HSE team, internal users on the project should be set to (Item Reviewer)
HS-a-051 - H&S - Incident Prevention Card (available on the PIM mobile application)
HS-T-001 - Together Safer Incident Prevention & Control Process Presentation
HS-T-002 -Together Safer Poster How to Transfer an Incident Prevention Paper Card to Pansophy Site Managers
HS-T-003 -Together Safer Poster How to Use an Incident Prevention Card using the mobile App
(j) {Outline any Client, Contract or Project specific requirements that will require amendment to or deviations from the Jones Bros Standard Processes}
(i) Incident information and records of investigations shall be kept in APPE/Appendix 12 – filed securely for data protection of any individual’s who may be named. Incident report forms and incident investigations shall not be released to any third party without formal permission from the Company’s senior management team.
2.11) Risk Assessment and Method Statements
(a) Risk Assessments and Method Statements (RAMS), Task Briefings and Permits to Work will be produced for the workplace and for individual tasks undertaken on the project will be produced as applicable. The Jones Bros Risk Assessment and Method Statement (RAMS) Process this includes the system to be used for identifying hazards and for recording risk assessments. RAMS/Task Briefings will be reviewed on a regular basis and updated prior to any changes been made to the working practice or activity.
PFC013 - Risk Assessment Process(S)
(b) A register of all Jones Bros' and contractors' risk assessments/ method statements will be produced and located in the project filing structure {07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments}. This will be updated as work progresses and contractors are appointed throughout the lifetime of the project. The Site Management Team will ensure that all risk assessments and method statements have been approved and then briefed to all relevant personnel and keep records of briefings held on site in the Project Filing Structure {07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments}.
HS-f-034 Risk Assessment & Method Statement Register
(c) An overall method statement is produced prior to work commencing on site and from this document task specific method statements will be written for all activities. The overall method statement will clarify the components of construction for the project. From this, detailed method statements will be produced for each element of the works prior to work commencing on site. Method Statements are to be prepared in line with Jones Bros guidelines. If a safe system of work changes then all works must cease for this activity until the RAMS are updated, reviewed and approved by senior management.
(d) Where contractors are used to undertake the works, the Site Management Team will review the risk assessments and method statements they produce and approve or comment on as appropriate. This will be recorded on a document appraisal form. We would ask that RAMS are submitted two weeks before works are due to start on site to allow review of the RAMS and any changes to be made prior to works starting.
HS-f-065 - Documentation Appraisal Form
Where the work is identified as high risk additional support can be provided by the HSE Advisor. Contractors will not be allowed to work on this project until they have provided a relevant risk assessment / method statement as appropriate and received approval back from the Site Management Team. Method statements and risk assessment reviews will be attached to the document reviewed.
(e) All risk assessments are to be in place prior to work commencing on site. This includes any work to be carried out by sub-contractors. Risk Assessments are to be attached to the method statements.
(f) A member / members of the Site Management Team have been appointed for the issue of permits. These persons are identified on the Project Appointment Matrix
Project Roles & Responsibilities
(g) A “permit to work” shall be issued by the appointed person, the persons issuing and receiving the permit will sign it off and a copy of the permit will be held by both parties. When the work is complete the appointed person will check the work area before closing out the permit.
(h) Copies of permits to work will be filed in the Project Filing Structure 07 Project Administration\07.07 Health and Safety\07.07.06 Work Permits}.
2.12) Site Rules
(a) The specific site rules for this project are located in the Site Induction. A copy of these rules will be issued to all contractors at the pre-start meeting / with the confirmed order and will be brought to the attention of every person working on site during the site induction.
HS-f-088 - Site Induction Slide Template | [5 empty] | HS-f-088a Visitors Site Induction Slide Template
(b) A copy of the site rules will be displayed on the project’s Health and Safety notice board. These will be reviewed throughout the project’s duration.
(c) Employees who breach Health and Safety site rules will be subjected to the disciplinary procedures as laid down in the Company’s staff handbook. Where contractors breach site rules. A safety warning notice will be issued. Further transgressions will result in the issue of a prohibition notice. (Copies of these documents are to be sent to the HSE Department. For subcontractors information should be copied to the procurement department for recording on the subcontractors file.)
(d) {Outline any site specific method of dealing with breaches e.g. red card systems, points system which ever is applicable}.
2.13) Drugs and Alcohol
(a) Jones Bros have a Drugs and Alcohol Policy. Contractors/visitors are advised prior to appointment or at induction that the Policy applies to all persons working or visiting this project.
JB-Policy-022 - Drugs & Alcohol Policy
The company Drugs and Alcohol procedures covers Pre-Employment screening, For Cause Screening, Random Screening and High Risk Project Screening:
PFC041 - Drugs & Alcohol Testing Process
(b) {Outline any Client, Contract or Project specific requirements that will require amendment to or deviations from the Jones Bros Standard Processes}
2.14) Mobile Phone use
(a) The use of mobile phones is restricted on all Jones Bros Sites as per the Jones Bros Mobile Phone Policy
JB-Policy-023 - Mobile Phone Policy
(b) {Include here specific areas where mobile phones are allowed or agreements made to use as part of the work process i.e. lone working areas as method of communication in event of emergency}.
2.15) Fire and Emergency Preparedness
a) The requirements detailed in the Company BMS set the minimum standards in respect of Fire Prevention, Emergency Preparation and Response procedures. These will be followed and emergency plans edited to the specific requirements of the project.
PFC056 - Site Set Up & Maintenance - Health & Safety
HS-p-013 - Fire Safety on Sites
HS-p-019 - Emergency Planning
(b) The Construction Site Fire Safety Plan. All Emergency plans for this project will be located in the Project Filing Structure Section (07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan) This plan identifies access for emergency vehicles to site, fire assembly point, persons appointed as fire wardens, fire fighting equipment requirements, means of raising the alarm, the position of highly flammable material stores areas and details the specific risks and controls appropriate to this project. The Fire Safety Plan is reviewed at regular intervals throughout the project’s duration or following any incident.
HS-f-023 Basic Emergency Procedures Template
HS-f-093 Wind Farm Emergency Response Plan Template
HS-f-095 Emergency Procedure Flow Charts Templates |  |  |  |  | These emergency process flow chart templates can be used within the emergency plan documents and used for display on project notice boards
(c) The Emergency plans for this project displayed is on the site notice board and the details shall be communicated to all personnel during their site induction.
(d) Task specific emergency / rescue plans will be produced prior to: {Amend to identify the types of work identified for this specific project
• Working at height using Harness, Safety Nets, rope climbing etc. | [5 empty] | PFC083 - Working at Height
• Confined Space Work | [5 empty] | PFC084 - Confined Spaces
• Working adjacent to/ over water | [5 empty] | HS-p-036 - Working over or Adjacent to Water
• Working on “Live” electrical systems | [5 empty] | HS-p-039 - Electrical Safety
• Excavations | [5 empty] | PFC100 - Managing Safety in Excavations
• Lifting Operations | [5 empty] | PFC104 - Managing Lifting Operations(S)
Other
SECTION 3 CPP |  |  | ARRANGEMENTS FOR CONTROLLING SPECIFIC PROJECT RISKS
All work carried out will be in accordance with the relevant Health and Safety legislation, primarily the requirements set out in the Health and Safety at Work Act, giving particular regard to providing safe places of work, safe plant and equipment, the provision of competent persons, provision of information, instruction and training. The Management of Health and Safety at Work Regulations, which is also adhered to, requires risk assessments to be carried out in order that significant risks are identified and suitable and sufficient control measures are utilised.
Explanatory Notes:-
vii) The general controls to be employed for controlling significant risks are those identified in the Jones Bros BMS WW-f-008 - Project Risk Register. The specific significant site risks for this project are managed through the Jones Bros Task Specific Risk Assessment and Method Statement (RAMS) Process which will trigger the relevant Operational Controls and where necessary further site specific measures. All RAMS are located in Document Store\07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments
PFC013 - Risk Assessment Process(S)
WW-f-008 - Project Risk Register
3.1) Pre-construction Information |  |  | {Include in here any significant risks identified in the pre-construction information and the control measures to be implemented to control them. From the information provided delete categories that are not relevant and include project specific issues. Amend the contents page of this plan according to the contents of this section. Including only those risk areas relevant to the project in question. The following are guidance – include project specific arrangements as identified, reference the Jones Bros HSE Operational Controls rather than repeat generic information. This information could be provided on a separate project specific risk assessment and identified as being part of project filing location File No. Section No i.e. Workplace Risk Assessment}.
3.2) Delivery and Removal of Materials (including Waste) | [5 empty] | EN-p-001 Waste Management Procedure |  |  | Please Specify:
EN-f-010 - Site Waste Management Plan
{Detail here the specific controls set up for this project i.e. the location for deliveries and removal of materials including waste with a safe systems of work. See the CEMP for more details.
3.3) Services and Overhead and Underground Services |  |  |  |  | HS-p-015 - Avoiding Danger from Underground Services |  |  |  | Please Specify:
HS-p-039 - Electrical Safety
Custom Form HS-a-007 - Electricity: Weekly Check
Detail here the specific requirements you have made for the disconnection of services, the names of competent persons employed to undertake any specialist work, the requirements for surveys before excavations take place, the provision of risk assessments and method statements, the permit to work before breaking ground, the requirements for signage and provision of goalposts}.
3.4) Temporary Structures / Unstable Structures identified |  |  |  |  | PFC103 - Managing Temporary Works |  |  |  | Please Specify:
HS-p-017 - Temporary Works
HS-f-044 Temporary Works Register
{Insert here any temporary works and identify competent persons and designs and safe system of work specific to the project – or reference project filing location where this is controlled}.
3.5) Preventing Falls / Working at Height |  |  |  |  | PFC083 - Working at Height |  |  | Please Specify:
{Insert here either location of risk assessments / safe systems for work at height or excavations}.
3.6) Scaffolding and Safe Means of Access |  |  |  |  | PFC103 - Managing Temporary Works |  |  | Please Specify:
HS-p-017 - Temporary Works
HS-f-044 Temporary Works Register
{Insert here specific arrangements/ controls in place on this project}.
3.7) Control of Lifting Operations |  |  |  |  | PFC104 - Managing Lifting Operations(S) |  |  |  | Please Specify:
{Insert here specific arrangements/ controls in place on this project}.
3.8) Control of Substances Hazardous to Health (COSHH) |  |  |  |  | HS-p-012 - Substances Hazardous to Health |  |  |  | Please Specify:
PFC056 - Site Set Up & Maintenance - Health & Safety
HS-f-031 - COSHH Assessment
HS-f-022 - COSHH Inventory
{Insert here specific arrangements/ controls in place on this project}.
3.9) Manual Handling |  |  |  |  | PFC105 - Manual Handling(S) |  |  | Please Specify:
{Insert here specific details for inspections, checking maintenance etc.}.
3.10) Noise Management |  |  |  |  | PFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
HS-p-031 - Control of Noise
{Insert here specific details for inspections, checking etc.}.
3.11) Maintenance of Plant and Equipment |  |  |  |  | PFC067 - Project Plant, Equipment and Labour Planning & Management |  |  |  | Please Specify:
PFC017 - Instrument & Equipment Calibration
QC-f-011 - Equipment Calibration and Testing Register
{Insert here specific details for inspections, checking maintenance etc.}.
3.12) Working in Confined Spaces |  |  |  |  | PFC084 - Confined Spaces |  |  |  | Please Specify:
HS-f-056 - Permit to Work Confined Space Entry
HS-f-070 - Permit Register
{Identify the specific details and what will happen on this project not what may happen}.
3.13) Excavations / Poor Ground Condition Management / Wells / Underground Earthwork / Tunnels |  |  |  |  | PFC100 - Managing Safety in Excavations |  |  |  | Please Specify:
HS-f-042 – Permit to Dig
HS-f-070 - Permit Register
{Identify the specific details and what will happen on this project not what may happen}.
3.14) Work on or Near Water etc. – other risks of drowning |  |  |  |  | HS-p-036 - Working over or Adjacent to Water |  |  |  | Please Specify:
{Include emergency and first aid controls}.
3.15) Traffic Routes / Segregation |  |  |  |  | HS-p-037 - Site Traffic and Pedestrian Management |  |  |  | Please Specify:
Traffic Management Plan
{Provide a traffic management plan specific for the project, drawings etc. and detail signage etc. that will be required, speed limits, information to contractors}.
3.16) Storage Materials and Management |  |  |  |  | PFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
EN-p-003 Oil Storage & Handling
PFC058 - Material Procurement & Management(S)
PFC056 - Site Set Up & Maintenance - Health & Safety
HS-f-031 - COSHH Assessment
HS-f-022 - COSHH Inventory
{Include in site drawing areas where materials will be stored, the specific flammable materials / hazardous materials management and identification}.
3.17) Off Site Fire Risks |  |  |  |  | HS-p-013 - Fire Safety on Sites |  |  | Please Specify:
{Provide details of measures in place to control the risk of fire spreading to adjacent premises}.
3.18) Health Risks | [7 empty] | Please Specify:
The removal of asbestosE_OC_000); |  |  | {Identify the project specific arrangements in respect of asbestos removal, if applicable}. Full details will be in the Construction Environment Management Plan (CEMP)
Construction Environment Management Plan (CEMP)
HS-p-034 - Asbestos
EN-p-001 - Waste Management Procedure
EN-f-010 Site Waste Management Plan
Dealing with contaminated land(SHE_OC_000); |  |  | {Identify the project specific arrangements in respect of contaminated land, if applicable}. Full details will be in the Construction Environment Management Plan (CEMP)
PFC102 - Contaminated Sites(S)
Leptospirosis (SHE_GN_000); |  |  | All personnel will be briefed who are likely to come into contact with sewage or likely to be working in areas of suspected rat infestation against the relevant RAMS and briefing register.
HS-p-035 - Leptospirosis - Weil's Disease
Vibration |  |  | (identify the project arrangement in respect to assessing and monitoring vibration activities on site) HS-f-018 is to be used as an inventory of all Hand & Whole body vibration plant and equipment on site. The project is to use either: HS-f-017 Hand Arm & Whole Body Vibration Assessment and monitoring paper template or Custom form HS-f-017- Hand-Arm & Whole-Body Vibration Assessment and Monitoring
PFC039 - Control of Vibration Process (HAV) & (WBV)
HS-f-018 Hand-Arm & Whole Body Vibration – Site Inventory
HS-f-017- Hand-Arm & Whole-Body Vibration Assessment and Monitoring
HS-a-029 Hand-Arm & Whole-Body Vibration Assessment and Monitoring (Available on the PIM Mobile application)
Occupational Health |  |  | Jones Bros has a system of Occupational Health that focuses on the physical and mental wellbeing of employees in the workplace. The aim of occupational health is to prevent work-related illness and injury by: encouraging safe working practices. The Occupational Health system includes: Together Safer Programme (working towards a safer working environment) Regular Health Screening of all Staff Mates in Mind training and awareness with supporting EAP 24 hour help lines bike to work scheme Regular sporting events (entering teams into local sporting events)
People and Plant Interface Zones (PPIZ) |  |  | The PPIZ is the area where people and moving plant can come together where the person is at high risk of being contacted by the item of plant. The danger zone will in certain circumstances be demarcated by a physical barrier. However, this will not always be possible depending on where plant is required to work. To prevent any inadvertent exposure to moving plant the PPIZ will be communicated to every person who accesses site and it will be done as a minimum requirement in the Site Specific Induction. The rule of thumb is the distance from the edge of the zone to the item of plant is 20m. Red Zone – Danger Zone Amber Zone – Access Waiting Zone Green Zone – Access Zone Red/Blue Zone – Collision Zone The PPIZ procedure is detailed in the Safe Working Instruction SWI042. The procedure forms part of the site induction and takes the form of a series of instructional Jones Bros-specific videos. To complement these a series of posters has been produced which are displayed in the site canteen. There are specific PPIZ procedures for the following situations: 1. Vehicles Approaching Wheeled (Fast) or Tracked (Slow) Plant 2. People Approaching Plant on Foot 3. Refuelling Items of Plant (Tractor & Bowser) 4. Refuelling Items of Plant (Static Bowser/tank) 5. Working in the People & Plant Interface Zone – People with machines 6. Working in the People & Plant Interface Zone – Two Excavators haymaking
Design Hazards |  |  | A design risk assessment will be in place for the project which will outline the health and safety risks involved with the design and stating suggested work methods. The design risk assessment will be reviewed and updated by the designer when there is a change to the design. Materials requiring precautions should be identified in the design stage and made known to the contractor.
Refuelling |  |  | Access and egress routes will be fixed and free from obstructions. There should be no other plant in the area and no need to pass stationary plant or vehicles when entering the refuelling exclusion zone. A designated refuelling operative will be in place so that only one person should need to enter the refuelling zone. This area will be separated from all pedestrian zones. Spill kit bin to be provided at the designated refuelling location. Each item of plant should then also have their own spill kit kept within their item of plant. Prior to fuelling all plant must be made safe and isolated with the keys removed until the fuelling process is complete. The spill response team will be trained in using spill kits and pollution prevention measures. No refuelling of mobile plant shall be undertaken within 10m of a watercourse or 50m of an abstraction borehole. Make sure fuel, oil and chemical storage on site is secure. Site the storage on an impervious base within a secondary containment system such as a bund. The base and bund walls should be impermeable to the material stored and able to contain at least 110% of the volume stored. Site the storage area above any flood water level and where possible away from high-risk locations (such as within 10 metres of a watercourse or 50 metres of a well, borehole or spring), to minimise the risk of a spill entering the water environment. Detailed guidelines concerning above ground oil storage tanks can found in our guidance PPG2 - reference 13 - and in PPG 26 – reference 14.
Spill Response Procedure |  |  | Spill containment procedures are outlined in EN-p-002 'Spill Response Procedure'. Procedures for dealing with different spills are outlined in this document as well as the reporting procedure. All sites are to be registered with Adler and Allan, our external spill response team. If the spill is large scale and too great for the site team to handle then the HSEQ department and Adler and Allan should both be contacted immediately.
Insert Other Significant Risks and Arrangements (specific to this location) to control them.
Other
Other
Other
Other
Other
SECTION 4 CPP |  |  | ARRANGEMENTS FOR COMPILING THE HEALTH & SAFETY FILE
Enter information as the example below Once these Contract works commence, the Contractor must keep a Health and Safety File in line with the agreed format, as the project progresses and be presented for review at Progress Meetings when requested. At or near the conclusion of the project, the PC shall assist the Principal Designer in providing all documentation that is deemed necessary for inclusion into the Health and Safety File. The Contractor’s Works shall not be deemed suitable for Taking Over until the necessary information for the Health and Safety File has been reviewed and accepted by the Employer and Principal Designer. The following information regarding the Health and Safety File is from, either, the Construction (Design and Management) Regulations 2015, or, the associated guidance published from time to time by the Health & Safety Executive. The Health and Safety File shall contain the information needed to allow future construction work, including cleaning, maintenance, alterations, refurbishment and demolition to be carried out safely. Information in the file should alert those carrying out such work to risks, and should help them to decide how to work safely. The file should form a key part of the information provided to the Employer, or the Employer’s successor, as required to provide for future construction projects under the CDM Regulations. Clients, Designers, Principal Contractor, other contractors and the Principal Designer all have legal duties in respect of the Health and Safety File. The following information shall be considered when putting together the file. (Additional information and guidance can be found on the HSE website). The level of detail should be such to allow the likely risks to be identified and addressed by those carrying out the work. • A brief description of the work carried out; • Description of Duty Holders, Principal Contractor, main sub-contractors’, Designers, Principal Designer, Client, health and safety contacts; • Details of main suppliers; • Any residual hazards and how they have been considered; • Key structural principles and safe working loads, particularly where these may preclude placing scaffolding or heavy machinery; • Hazardous materials used and specialist maintenance requirements; • Information regarding the removal or dismantling of installed plant and equipment; • Health and safety information about equipment provided for cleaning or maintaining the structure; • The nature, location and markings of significant services, including underground cables, gas supply equipment, fire-fighting services etc.; • Information and as-built drawings of the structure, its plant and equipment; • Reference made to any other project files not relevant for inclusion in CDM H&S Content, i.e. O&M Files, handovers files, etc.
Jones Bros Project Manager / Agent will be responsible for compiling the Health and Safety File and will update and review the document regularly. The document will be stored electronically on Pansophy, Jones Bros' business management system. An electronic and hardcopy document will be provided to the Principal Designer on completion of the works. Any information that is required for the Health and Safety File will be handed by the sub contractor to Jones Bros site management for inclusion in the Health and Safety File. The designers and Jones Bros will ensure that any features of the structure which will involve significant risk to health & safety during the structure’s lifetime are also passed on to the Principal Designer. On completion of the project, the Principal Designer will hand over the Health and Safety File to the client. The client must keep the health & safety file, and ideally on the premises to which it refers.
SECTION 5 CPP |  |  | RECORD REFERENCING MATRIX
Explanatory Notes:-
To support the effective management of projects and remove the potential for duplication of information and effort, all records referred to in this plan are filed in the Jones Bros Project Filing Structure whilst the records are continuing to be update and the project is live. The following matrix supports the navigation and archiving of project records. It enables project teams and third parties (as applicable) to easily navigate the Project Filing Structure.
HS Plan Section Reference |  | Record Description |  |  |  | BMS Format |  | Project Filing Location
1.1 |  | Project Appointment Matrix |  |  |  | Project Roles & Responsibilities |  | 07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
1.1 |  | Specific Appointment Letters |  |  |  | Various |  | 07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
1.4 |  | Construction Programme |  |  |  | n/a |  | 07 Project Administration\07.10 Plans and Programmes\07.10.02 Contract Programme
1.5 |  | HSE F10 |  |  |  | n/a |  | Notice Board & 07 Project Administration\07.07 Health and Safety\07.07.01 Preconstruction Health & Safety Plan
1.6 |  | Site Start-up Checklist |  |  |  | HS-f-100 - Setting Up Site Safety Checklist |  | 07.07.1 Preconstruction Health & Safety Plan Section No. 8.20}
2.1 |  | HSE Inspections and Audits |  |  |  | HS-a-021 - H&S Site Inspection Report HS-a-025 - H&S Senior Managers Tour EN-a-007 - Environment Site Inspection Report |  | 07.07 Health and Safety 07.07.07 Site Inspections & Records
2.2 |  | Briefing Record |  |  |  | HS-f-007 - Briefing Register |  | 07 Project Administration\07.07 Health and Safety\07.07.16 Daily Briefings
2.2, 2.7 |  | Toolbox Talks Record |  |  |  | HS-f-007 - Briefing Register |  | 07 Project Administration\07.07 Health and Safety\07.07.16 Daily Briefings
2.3 |  | PPE/RPE Issue |  |  |  | HS-f-014 PPE Workwear Requisition & Issue Record Form |  | 07 Project Administration\07.02 Records / Logs\07.02.12 PPE Issue & Receipt
Mobile Custom Form HS-a-028 H&S PPE Issue for use on site
2.5 |  | Consultant Questionnaires |  |  |  | HS-f-046 - Designer Stage Two Assessment |  | COINS system
2.5 |  | Supply Chain Questionnaires including subcontractors |  |  |  | FI-f-001 - New Subcontractor Form
2.7 |  | Induction Records |  |  |  | HS-f-019 - Induction Register |  | 07 Project administration 07.02 Record & Logs 07.02.10 Site Inductions}
2.7 |  | Training Records |  |  |  | TR-f-002 -Master Qualification Matrix |  | 17 Training Business Unit\17.09 Qualifications\17.09.01 Qualifications Matrix
2.9 |  | First Aid Arrangements |  |  |  | Roles & Responsibilities |  | 07.07.1 Preconstruction Health & Safety Plan
2.1 |  | Incident Reports |  |  |  | QC-f-030 - Investigation Report |  | 07 Project Administration\07.07 Health and Safety\07.07.13 Incidents and Investigations)
2.11 |  | Risk & Method Statement Register |  |  |  | HS-f-034 - Risk Assessment & Method Statement Register |  | 07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments
2.11 |  | Permit to Work |  |  |  | PFC013 - Risk Assessment Process(S) |  | 07 Project Administration\07.07 Health and Safety\07.07.06 Work Permits.
2.12 |  | Site Rules |  |  |  | HS-f-088 - Site Induction Slide Template & HS-f-088a Visitors Site Induction Slide Template |  | 07 Project Administration\07.02 Records / Logs\07.02.10 Site Inductions
2.15 |  | Fire Plan |  |  |  | HS-p-019 - Emergency Planning |  | (07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
3.1 |  | Workplace Risk Assessments |  |  |  | PFC013 - Risk Assessment Process(S) |  | 07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments
WW-f-008 - Project Risk Register
3.2 |  | Waste Records |  |  |  | EN-f-009 - Waste Monitoring Form |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
3.3 |  | Services |  |  |  | HS-p-015 - Avoiding Danger from Underground Services |  | Document Store\07 Project Administration\07.02 Records / Logs\07.02.05 Health & Safety
HS-p-039 - Electrical Safety
Custom Form HS-a-007 - Electricity: Weekly Check
3.5 |  | Temporary Works Records |  |  |  | HS-f-044 - Temporary Works Register |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.07 Site Inspections & Records
3.6 |  | Working at Height Records |  |  |  | HS-f-004 Working at Height Permit |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.06 Work Permits
HS-f-070 - Permit Register
3.6 |  | Scaffolding Records |  |  |  | HS-f-044 - Temporary Works Register |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.07 Site Inspections & Records
3.7 |  | Lifting Records |  |  |  | HS-f-110 - Lift Plan - Mobile Lifting Equipment |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.04 Method Statements
3.9 |  | Manual Handling Records
3.11 |  | Plant and Equipment Records |  |  |  | PL-f-001 - Site Plant Register & Inspections - Control |  | Document Store\07 Project Administration\07.02 Records / Logs\07.02.11 Plant Inspections
PL-f-006 - Plant Defect Register
[6 empty] | QC-f-011 - Equipment and Instrument Calibration Register |  | Document Store\07 Project Administration\07.09 Quality\07.09.03 Inspection Reports
3.12 |  | Confined Space Records |  |  |  | HS-f-056 Permit to Work Confined Space Entry |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.06 Work Permits
HS-f-070 - Permit Register
3.13 |  | Excavation Records |  |  |  | HS-f-042 – Permit to Dig |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.06 Work Permits
HS-f-042a - Permit to Dig - Landfill
HS-f-070 - Permit Register
3.15 |  | Traffic Management Records |  |  |  | Traffic Management Plan |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.01 Preconstruction Health & Safety Plan
TMP
3.16 |  | COSHH Records |  |  |  | HS-f-022 - COSHH Inventory |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.05a COSHH Assessments
HS-f-031 - COSHH Assessment
3.18 |  | Asbestos Record |  |  |  | EN-f-010 Site Waste Management Plan |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
[6 empty] | EN-f-009 - Waste Monitoring Form |  | Document Store\07 Project Administration\07.08 Environmental\07.08.05 Site Inspections & Records
EN-f-008 - Waste Transfer Note
[6 empty] | CEMP |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
3.14 |  | Noise Management records
3.14 |  | Weil's Disease
3.15 |  | Storage Materials and Management
3.16 |  | Off Site Fire Risks
SECTION 6 CPP |  |  | FURTHER GUIDANCE
Further guidance on Health and Safety matters is available from |  |  |  |  | the HSE Team on 01824 703661 or E-mail hseqt@jones-bros.com
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
(CON_PR_006)

## CEMP
CONSTRUCTION ENVIRONMENT MANAGEMENT PLAN (CEMP)
Project Name: |  | A494 River Dee Bridge Deck over-slabbing Contingency Scheme
Project Number: |  | 21-NM-CHR-003
Project Details
Project Description: |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) have commissioned a project to develop a major maintenance intervention should a critical defect be identified within the A494 River Dee Bridge structure and enable this to be implemented with minimal impact on traffic conditions. The proposed design intervention comprises of removing a depth of existing road surfacing and replacing with a new thin reinforced concrete over-slab with combined waterproof and wearing membrane (hence forth referred to as the ‘over-slabbing works’). Enabling works are required to parts of the central reserve and to the Riverside Way Junction to facilitate contraflow traffic management arrangements during construction. The enabling works consist of construction 2Nr crossovers through the central reserve west of the existing bridge and works to widen the Riverside Way Junction.
Project Location: |  |  | Enter your project location here
Plan Approvals
Written by: |  | Name: | 0 |  | Signature: | 0 |  | Date: | 0
Approved by: |  | Name: | 0 |  | Signature: | 0 |  | Date: | 0
Explanatory Notes:-
Origination: Tender phase origination resides with the Project Manager. Construction Phase update will be the responsibility of the Site Manager.
Approval: Tender phase approval resides with the Contracts Manager or Regional Director. Construction Phase approval will be the responsibility of the Project Manager.
Revision: The plan will be revised to reflect changes that have been made to the product, project or contract, work practices, service provision or Quality Assurance procedures. Where changes are made to the plan an assessment of the impacts of the changes will be carried out and recorded in the Version Control section below.
Version Control
Description of changes |  |  | Date | Revision | Page No. | Comments
Explanatory Notes:-
This Project Management Plan will be added to, reviewed and updated as the project develops, further design work is completed, information from subcontractors starting work becomes available, unforeseen circumstances or variations to planned circumstances arise or where the operations management team deem it is necessary.
If sections are deemed not applicable DO NOT DELETE. Replace text with "not applicable on this project".
CONTENT
Section Ref |  | Content | [5 empty] | Comments
INTRODUCTION
1.0 |  | PROJECT DETAILS
| 1.1 | Project Organisation and Resource
| 1.2 | Scope of Works
| 1.3 | Project Timescale
2.0 |  | OBJECTIVES
3.0 |  | LEGAL AND CONTRACTUAL ENVIRONMENT
4.0 |  | COMMUNICATION AND CONSULTATION
| 4.1 | Liaison with Client and Designers
| 4.2 | Regulatory Agencies
| 4.3 | Public Relations
5.0 |  | CONSENTS PERMITS AND LICENCES
6.0 |  | ENVIRONMENTAL RISKS AND MITIGATION
7.0 |  | MANAGEMENT CONTROLS
| 7.1 | Incident Reporting and Investigation
| 7.2 | Communication and Consultation
| 7.3 | Ecology
| 7.4 | Hazardous Materials incorporating COSHH
| 7.5 | Housekeeping and Safe Access
| 7.6 | Land Use Management
| 7.7 | Nuisance Management
| 7.8 | Resource Management
| 7.9 | Waste Management
| 7.1 | Water Management
| 7.11 | Storage
| 7.12 | Fuelling
| 7.13 | Site Security
8.0 |  | EMERGENCY PREPAREDNESS AND RESPONSE
| 8.1 | Arrangements for Reporting Significant Environmental Incidents
| 8.2 | Arrangements for Reporting Minor Environmental Incidents
9.0 |  | MONITORING AND MEASURING PERFORMANCE
10.0 |  | ENERGY MANAGEMENT (EM)
11.0 |  | TRAINING, AWARENESS AND COMPETENCY
12.0 |  | RECORD REFERENCING MATRIX
13.0 |  | FURTHER GUIDANCE
Explanatory Notes:-
In this template Plan, guidance and sample content is included where deemed necessary. This is indicated by the inclusion of yellow boxes with text in brackets { }. On completing this plan all sample and guidance text should be deleted or overwritten as required.
Introduction CEMP
(a) Jones Bros operates a Business Management System (BMS) accredited to ISO14001 Environmental Management and ISO50001 Energy Management. All works conducted on this site are conducted in accordance with the processes contained within the BMS.
(b) This plan is mandated as part of the Jones Bros BMS and is therefore required to be in place and kept up to date through the project.
(c) This Construction Environmental Management Plan (CEMP) has been developed to identify and manage the environmental risks associated with this project and is a fundamental requirement of the Jones Bros BMS.
(d) Jones Bros recognises the Environmental benefits of improved environmental performance as: - i) Reduced damage to our natural environment; ii) Reduced demand for natural resources and iii) Reduced disturbance to our neighbours.
(e) The company also recognises the economic benefits of improved environmental performance and recognises that, “Preventing pollution is cheaper than curing it”.
(f) We aim to reduce the provision of generic information and to only provide in this Plan and all other associated plans project specific information that should help with the communication and risk management of this project. Other non-project specific information referenced in this plan will be clearly identified with the location where it is available. If there is a need to review these documents they will be provided on request.
Explanatory Notes:-
The following information has been included here to emphasise its environmental importance. It is repeated in specific Method Statements elsewhere where relevant. This document may also refer to specific Method Statements where further details may be found and the appropriate reference should be made.
SECTION 1 CEMP |  |  | PROJECT DETAILS
1.1) Project Organisation and Resource CEMP
(a) Agreed responsibilities for key roles are outlined in the BMS. Specific duties and responsibilities are also identified in associated plans and process maps held in the Jones Bros BMS and where appropriate referenced throughout this plan.
(b) Specific Project Environmental Responsibilities for this project have been defined and are allocated in accordance with the Project Appointment Process
PFC033 - Project Start UP & Commercial Review(S)
Appointments are documented on the Project Appointment Matrix and relevant specialist appointment letters.
(c) A copy of the appointments is displayed on the project notice board and it shall be signed by all persons who have been allocated specific responsibilities on this project.
(d) Appointments will be reviewed and updated throughout the project, reflecting any changes or movement in the project as required. Changes in appointments will be administered through and recorded in this Project plan workbook_FM_000).
Role |  | Name |  | Company |  | Address |  | E-mail | Telephone
Client |  | {insert name} |  | The North and Mid Wales Trunk Road Agent (NMWTRA) |  | Insert Address |  | {insert email} | {insert tel no.}
Client Contract Admin |  | {insert name} |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Principal Designer |  | (Insert name) |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Designer |  | (Insert name) |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Director |  | Hefin Lloyd-Davies |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | hefin@jones-bros.com | 07887 722560
Contracts Manager |  | Daniel Robat Williams |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | robat@jones-bros.com | 07787 100752
Project Manager |  | (Insert name) |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Works Manager |  | (Insert name) |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Environment Manager |  | Sam Higgitt |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | samh@jones-bros.com | 07766 747133
CSR Co-ordinator |  | (Insert name) |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
1.2) Scope of Works CEMP
The A494 River Dee Bridge Deck Over-Slabbing Contingency Scheme is a major maintenance intervention that involves the replacement of the existing road surface with a new reinforced concrete over-slab and combined waterproof and wearing membrane. The works will be contained within the existing footprint of the bridges surface structure and above the existing concrete deck slab. Below deck debris netting will be installed and the top 75mm of the bridge deck, existing kerbs and movement joints removed and disposed off-site. Concrete deck repairs will be carried out and new structural mesh will also be installed across the entire bridge deck. The combined waterproof and wearing membrane shall also be applied to the hard verge and central reserve.
1.3) Project Timescale CEMP
Contract Award Date |  |  | {dd/mm/yyyy} |  | Commissioning Start |  |  | {dd/mm/yyyy}
Contract Commencement Date |  |  | {dd/mm/yyyy} |  | Practical Completion |  |  | {dd/mm/yyyy}
Contract Period |  |  | {xx weeks} |  | Take Over Certificate |  |  | {dd/mm/yyyy}
Site Start Date |  |  | {dd/mm/yyyy} |  | Planned Contract Completion |  |  | {dd/mm/yyyy}
SECTION 2 CEMP |  |  | OBJECTIVES
(a) The Site Management Team has considered the identified project environmental risks and defined the following environmentally related objectives and targets.
No. | Objective |  |  |  | Target |  | Responsibility |  | Completion Date
1
2
3
4
5
(b) The Site Management Team will ensure that progress is periodically reviewed as part of the monthly Site HSE Review meetings.
SECTION 3 CEMP |  |  | LEGAL AND CONTRACTUAL ENVIRONMENT
(a) Jones Bros maintains access to applicable environmental legal requirements, which details all environmental legislation applicable to the environmental risks associated with this project and the Company’s general activities.
(c) The other main requirements applicable to this project are: |  |  |  | {Contractual requirements – Include any environmental requirements Client’s Environmental Policy Statement; Industry Best Practice Standards regarding environment; Environmental Good Practice Guide; C650; CIRIA (2005); Control of water Pollution from Linear Construction Projects – Technical Guidance; C648; CIRIA (2006) - amend and add to list as appropriate}.
(b) Further support and guidance concerning environmental legislative requirements can be obtained from:-
Name: |  | Sam Higgitt |  |  |  | Telephone No: |  |  | 07766 747133
Qualifications: |  | {Insert brief overview of qualifications} |  |  |  | Frequency of Visits:
SECTION 4 CEMP |  |  | COMMUNICATION AND CONSULTATION
4.1) Liaison with Client and Designers
{In regular meetings with the client and designers environmental issues affecting the design will be raised and discussed. Alternative approaches and alterations to the design may be required where environmental improvements can be achieved and these will be discussed and agreed with the client and designers as the works proceed}.
4.2) Regulatory Agencies
The following table sets out the Regulators likely to be involved in the project and their responsibility (this is not an exhaustive list):
Regulator |  |  |  |  | Responsibility
Local Authority |  |  |  |  | Noise, Air Quality, Traffic, Nuisance, Traffic
Environment Agency/ National Resources Wales/ Scottish Environment Protection Agency |  |  |  |  | Discharge to watercourses, Waste Treatment & Disposal, Effluent Discharge, Abstraction Licences.
Water Utilities |  |  |  |  | Foul Water Discharge to Sewer, Standpipe Use & Licences
Special Interest Groups |  |  |  |  | Ecological Interest
Local Archaeological Trusts |  |  |  |  | Archaeological Interest
Health and Safety Executive |  |  |  |  | Health and Safety Issues
Include others as appropriate
4.3) Public Relations
Jones Bros recognises that in order to complete the project with the minimum of disturbance to neighbours, good public relations is vital. Project specific arrangements are considered when planning specific tasks and construction activities, which will be included in relevant method statements. However, the following arrangements have been implemented on this project:- (Please delete or add below)
(a) Visit occupants of particularly sensitive buildings and keep them informed of progress.
(b) Prepare a leaflet and distribute it to nearby residents or occupiers. Provide updates.
(c) Identify key local community representatives, such as parish councillors and keep them informed.
(d) Write articles about the progress on site in the local press.
(e) Display a contact board at the site perimeter so that the public know who to contact if they have a complaint or a comment to make. Use this board to display information on the phasing and other relevant matters.
(f) Establish a complaint line and check that it works by calling it.
(g) When complaints arise deal with them quickly and in accordance with a defined complaints procedure. Create a log of complaints. Jones Bros complaint process is as defined in PFC006 Non-Conformances and Corrective Actions.
(h) Consider providing a position so that passers-by can observe activities on site.
(i) Be able to identify your neighbours and understand their views}.
SECTION 5 CEMP |  |  | CONSENT, PERMITS AND LICENCES
(a) The need for any environmental legislative consents, permits and / or licences and exemptions relating to work associated with this Project has been identified during the environmental risk assessment process
PFC059 - Site Set Up & Maintenance - Environmental
EN-f-024 - Environmental Aspects and Impacts Risk Assessment
(b) A register of those required on this project is located in the Project Filing Structure {Document Store\07 Project Administration\07.08 Environmental\07.08.01 Environmental Impact Statement}.
SECTION 6 CEMP |  |  | ENVIRONMENTAL RISKS AND MITIGATION
(a) The Site Management Team ensures that the environmental risks are identified, reviewed and updated throughout the duration of this project so as to identify any environmental threats, impacts and potential issues that may arise from activities carried out within the scope of the contract works.
(b) For this Project, the Site Management team has completed the pre-construction environmental risk assessment
EN-f-024 - Environmental Aspects and Impacts Risk Assessment
which identifies potential environmental risks caused by site activities and assigns a level of possible risk. The matrix identifies i) the construction activity, ii) the lifecycle stages at which certain risks may arise, iii) potential environmental aspects & their impacts and iv) associated environmental risk.
(c) Jones Bros implement an integrated process when assessing risks associated with construction activities. The Task Specific Risk Assessment and Method Statement (RAMS) Process requires environmental risk along with Safety and Quality risks to be considered specific to the tasks being undertaken.
PFC013 - Risk Assessment Process(S)
(d) The Site Management team review all risks on a monthly basis and revises, when necessary, the Risk Assessments, Method Statements and Management Plans throughout the duration of the project to take account of changing circumstances and ensure that suitable and adequate control measures have been implemented.
SECTION 7 CEMP |  |  | MANAGEMENT CONTROLS
The following represent, as identified from the Environmental Risk Assessment process, the Jones Bros Processes and Operational Controls that will be adopted and implemented on this project. Reference should also be made to Task Specific Risk Assessments and Method Statements that will identify additional requirements or deviations from those controls dependent on the risks associated with specific tasks.
Jones Bros Operational Control Document |  |  |  |  | BM Reference |  |  | Required
7.1) Incident Reporting and Investigation |  |  |  |  | PFC025 - Incident Prevention, Notification & Investigation Reporting Process |  |  |  | Please Specify:
All incidents will be reported within 2 hours to the Jones Bros HSE Team using the Incident Notification Form on a mobile device. The HSE Team will notify any regulators required. All evidence will be gathered by the site team during this period to feed the correct information back to the HSE Team so that an investigation to the cause can be established. Jones Bros shall notify the client of any environmental incidents/near misses as soon as practicable after its occurrence. Minor environmental incidents will be discussed in weekly meetings. If any substances or articles are deposited otherwise than as permitted as part of the Licensed Activities of the Marine License or in the Licensed Area full details of the circumstances shall be notified to the Licensing Authority within 48 hours of the incident occurring.
7.2) Communication and Consultation |  |  |  |  | BP-p-003 - Communication Plan |  |  |  | Please Specify:
Ensure that multiple channels of communication are utilised so that as many stakeholders as possible are informed of the programme. Advertising via multiple methods, including, newspaper, local radio stations, promotion on social media platforms as well as providing local newsletters containing translations in Welsh and Braille and placing information in local community centres such as libraries and tourist information centres. Community engagement and pre-application consultation sessions will be held. The Jones Bros Environmental Team will keep in regular contact with the project team, and conduct inspections quarterly at the site and attend during environmentally sensitive phases of the works. The following information will be made available: 1. Residents of properties near construction activities will be provided with information detailing any specific noisy activities, and their likely duration; 2. Jones Bros shall publicise the construction programme (i.e. through mailings to local residents, through an on-site information board at the site access or other means) for the commencement and duration of operations, and named contacts for daytime and out of hours periods 3.Contact details for queries or further information. Environmental information will be relayed to the workforce via the induction, RAMS, COSHH Assessments and Toolbox Talks. The workforce will be encouranged to provide observations and report concerns to site management by either speaking with their supervisors or through the use of Incident Prevention Cards (IPCs). Daily informal meetings will take place between Jones Bros and other contractors with regards to the general running of the site. Weekly coordination meetings will be undertaken by all contractors and third parties carrying out activities on site. Environmental management and coordination of activities will be discussed as well as any other business. Information requested by the Client will be provided in a timely manner. Regular Progress Meetings will be held with the client where any environmental issues will be reported and discussed. Reports and minutes will be held in the Project Filing Structure (07.04 Minutes 07.04.03 Client Meeting) against the project. It will be the responsibility of the Client with backing of the PC to liaise with the Local Authority in regards to environmental issues or public enquiries." All communication agreements outlined in the Marine License will be followed to the agreed timelimes.
7.3) Ecology |  |  |  | EN-f-024 - Environmental Aspects and Impacts Risk Assessment |  |  |  |  | Please Specify:
EN-a-008 - Environment - ECOW Log (The ECOW log is for Jones Bros Environmental Specialists use only)
Ecological Calendar
The designated sites which are crossed by the bridge are the River Dee and Bala Lake SAC and River Dee SSSI. No significant effects on the Annex I habitats that are a primary reason for selection of the SAC are envisaged, as the habitat type supporting these communities does not occur at the location of the proposed Scheme. The SSSI includes intertidal mud and sandflats and saltmarsh. These habitats would not be directly affected by land take. All works would be in existing hard standing. Otters are a feature of interest of the River Dee and Bala Lake SAC which is crossed by the bridge and evidence of otters has been found along the River Dee. Suitable secure sites for natal dens and suitable rest-up are absent from the areas directly below the bridge or compound sites. Passage for otters along the River Dee would be maintained. Species that are a primary reason for selection / designation of the River Dee and Bala Lake SAC and the River Dee SSSI could be exposed to indirect effects. Salmonids, sea and river lamprey could be exposed to pollution incidents and/or changes in water quality during maintenance/construction works. These species, and otter, could be exposed to lighting and vibration / noise during the bridge repair works. Night-time working is likely to be required to enable the emergency works to progress as quickly as possible and to minimise disruption to traffic. The main environmental risk associated with this operation is light spillage onto the River Dee and potentially adverse effects on migratory fish and otters. While night-time working may be unavoidable, the negative effects could be mitigated by directional lighting considerations to reduce the risk of light trespass onto the surface of the river. While works will not result in a direct impact on the River Dee SAC/SSSI, potential indirect risk exists. The proposed works, for example, will be carried out directly over the designated sites. Any loss of containment e.g., concrete/cement wastewater or spill of fuel, oil, chemicals (i.e., hydraulic fluid), or concrete/cement wash water could therefore have an indirect effect. Pollution prevention measures will be strictly enforced onsite and Pollution Prevention Guidance (GPP5) measures will be strictly adhered to, reducing the likelihood of a loss of containment occurring. All mitigation measures detailed within ‘noise’ and ‘road drainage and water environment’ will be adhered to. All site personnel will be made aware of the protected status of the River Dee SAC/SSSI. There will be no materials, ancillary plant, vehicles or NRMM stored within 10 m of the River Dee. To reduce disturbance, standard construction hours will be 07:30 - 17:30 (Monday to Friday). If any works are required out with the agreed working hours, these would be agreed with FCC. Toolbox Talks will be delivered to all site personnel prior to works commencing. The Toolbox Talks will provide details of protected species that have the potential to be impacted by the works and any mitigation measures required to prevent disturbance. The custom form EN-a-008 - Environment - ECOW Log can be used on site by Environmental Specialists to document environmental observations both positive and negative providing Advisory, Good Practice and Immediate Action comments. Daily environmental checks will be undertaken.
7.4) Hazardous Materials Incorporating COSHH |  |  |  |  | PFC056 - Site Set Up & Maintenance - Health & Safety |  |  |  | Please Specify:
HS-p-012 - Substances Hazardous to Health
HS-f-031 COSHH Assessment
HS-f-022 COSHH Inventory
The site specific Pollution Control Plan, Site Waste Management Plan and Environmental Risk Assessment for the project site outline all mitigation measures to be adhered to, to prevent incidents from occurring as a result of poor COSHH and Hazardous Material handling, storage and disposal. Jones Bros Waste Management Procedure, Spill Response Procedure and Substances Hazardous to Health Procedure must be followed to protect the environment and workers' health. All COSHH will be stored in line with the Pollution Control Plan, with mitigation measures and a response plan in place to protect the environment from any harm due to COSHH spillages. Spill Kit Awareness internal Training will also be delivered to the project team, to mitigate incidents from fuel and chemical spillages and poor handling practices. In the event of a major spill incident which cannot be handled at site-level, Jones Bros Spill Response Contractor Adler and Allen will be contacted in line with the HSE Team only. A Material Safety Data Sheet (MSDS), provided by the material manufacturer that contains information on the potential hazards (health, fire, reactivity and environmental), will be obtained for each hazardous substance on site. From this information, a COSHH assessment will be written to provide hazard identification, first aid, firefighting, accidental release, handling & storage, disposal conditions and how to work safely with the chemical product. The MSDS and COSHH assessments will be available to all relevant personnel on the project. This includes all first aiders. This allows any injured parties to receive first aid measures in accordance with the MSDS and COSHH assessment for the substance. There will be a COSHH store located at the main compound that will have adequate ventilation and appropriate firefighting equipment for the substances being stored. The COSHH store will have a bunded drip tray with a capacity of no less than 110% of the container's storage capacity, in line with the requirements outlined in the Marine License. All containers/drums/vessels etc. containing hazardous materials will be correctly labelled. Substances must not be decanted into an unlabelled container. Storage of all substances must be in the original container delivered by the manufacturer.
7.5) Housekeeping & Safe Access |  |  |  |  | PFC056 - Site Set Up & Maintenance - Health & Safety |  |  |  | Please Specify:
HS-p-011 - Setting Up Site
HS-p-027 - Housekeeping
HS-f-100–Setting Up Site Safety Checklist
All materials and COSHH will be stored appropriately to avoid any incidents from slips, trips, falls and fires. Cleaners will frequently clean welfare areas to minimise risks to the Jones Bros workforce and subcontractors. Waste will be segregated from materials and welfare facilities. Cabins will be cleaned regularly and vermin traps will be set up around the site and in welfare cabins. Waste will not be allowed to build up on site or in the skips. Jones Bros will coordinate with the skip company to ensure they are emptied regularly. Traffic routes that have been agreed with planning will be communicated with all suppliers and delivery drivers. Signage will be installed around site to direct people. Deliveries will be planned for off peak times of the day to reduce traffic on the roads during peak times. Small deliveries will be left at the security gate to reduce traffic on the site tracks and will be picked up by the site team when passing. Large deliveries will be scheduled and a suitable storage location will be allocated prior to arrival. Storage area for scheduled deliveries will be communicated to the security guard so they can effectively communicate location to the driver. Daily Inspections will be carried out by the site management to ensure good housekeeping. This will include inspecting the storage of hazardous materials and the management of waste to prevent a build-up. Toolbox talks will be communiated to the work force on the importance of good housekeeping.
7.6) Land Use Management |  |  |  |  | PFC102 - Contaminated Sites(S) |  |  |  | Please Specify:
HS-p-020 Contaminated Sites
HS-f-031 COSHH Assessment
EN-f-023 Soil Management Plan (Project-Specific - see criteria for population in document)
HS-f-022 COSHH Inventory
New or temporary accesses to all affected properties will be in place prior to severance of existing access routes. These locations are shown on site boundary plans. If any contamination is discovered, all works in the vicinity should be stopped, the incident reported to the Jones Bros HSE Team via PIM Mobile and appropriate action taken to prevent harm to the environmental and people through following controls in the Pollution Control Plan. Stands of invasive species are to be managed in line with this CEMP, the Pollution Control Plan and Environmental Risk Assessment to prevent spread of seeds and spores, including introduction of invasive or problem species to the site. Contractors must ensure that all plant machinery and equipment are free from foreign material on arrival at site, and that all plant machinery are clean when departing the site. It is recommended that principles such as the Check Clean Dry are strictly followed. Material moved around the site, or imported onto site during the construction will be chemically tested for its intended use and shown to not present a risk to controlled waters or human receptors. Movement of materials will be undertaken in accordance with the relevant waste legislation and guidance (CL:AIRE Contaminated Land Definition of Waste: Development Industry Code of Practice). It is also assumed that future construction works will be undertaken in accordance with legislative requirements, statutory and regulatory guidance and industry best practice. Within the construction phase, an Principal Contractor will be responsible for ensuring the scheme is legally compliant, and consider the risk of Asbestos and linked legislation. The site specific Pollution Control Plan, Site Waste Management Plan and Environmental Risk Assessment for the project site outline all mitigation measures to be adhered to, to prevent incidents from occurring as a result of poor COSHH and Hazardous Material handling, storage and disposal. Jones Bros Waste Management Procedure, Spill Response Procedure and Substances Hazardous to Health Procedure must be followed to protect the environment and workers' health.
7.7) Nuisance Management |  |  |  |  | EN-f-024 - Environmental Aspects and Impacts Risk Assessment |  |  |  | Please Specify:
PFC059 - Site Set Up & Maintenance - Environmental
EN-f-014 Noise & Vibration Management Plan
The construction/maintenance works required has the potential to cause driver stress from the short periods of full or partial closure of the A494 required to undertake the works, causing diversions, congestion, increased journey times and a greater risk of accidents. The Scheme does not require the closure of any Public Rights of Way or Cycle Routes, though these do pass underneath the River Dee Bridge. The key route is the NCN568, which runs underneath the A494 River Dee Bridge and crosses NCN 5 at the Hawarden Bridge (Shotton). Measures will need to be taken to ensure that path users are not affected by pollutants such as dust and run-off during construction and maintenance operations. During the maintenance/construction works, temporary noise and vibration impacts associated with the Scheme have the potential to directly affect sensitive receptors, including nearby residential properties (for example, those at Claremont Avenue), Toyota and the Haulage and Auto Repair yard. Pollution Control Plan to be followed for all pollution including the following nuisances: noise, vibration, dust, fumes, silt pollution and odors. Environmental risk assessment shows controls in place to manage nuisances to the public.
7.8) Resource Management |  |  |  |  | PFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
EN-p-004 Energy Efficient Procurement Procedure
PFC053 - Preparing Cost Plans & Cost-Value Reconciliations(S)
PFC067 - Project Plant, Equipment and Labour Planning & Management
The Aspects and Impacts Register is to be followed regarding resource management. Protection of all watercourses in line with Pollution Control Plan, and materials to be managed in a way that reduces waste, as per site waste management plan. Jones Bros are committed to reducing carbon emissions per £1m turnover from all operations by 25% from the 2019-20 baseline by 2024-25. To achieve this objective the company uses robust carbon management principles including: • The utilisation of Hydrotreated Vegetable Oil (HVO) Fuel to run all site operated plant on this project, to reduce net emissions by 90% compared to conventional diesel fuel • Using solar-power and hybrid battery generation for facilities and temporary lighting where possible, for minimum fuel use and lower noise • Appoint carbon champions on site to promote energy conservation • Local self-delivery (>90%) using our North Wales based plant and labour force to minimise travel and material transport. Staff and plant will all come from within 30 miles of the site • Use of local quarries for aggregate, bituminous material and concrete provision • Carefully following habitat and species protection measures, and developing new methods • Closely examining designs to reduce embedded energy and/or materials use • Re-using all existing rock armour as raw material within the works • Segregating and managing wastes to maximise the amount recycled or diverted from landfill (>99% in 2021-22)
7.9) Waste Management |  |  |  |  | PFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
EN-p-001 - Waste Management Procedures
EN-f-010 Site Waste Management Plan
Site personnel, including employees, subcontractors and suppliers will be appropriately briefed regarding general site waste management as part of their site induction. Records of all training will be kept on-site. Site Waste Management plan is to be followed and waste must be separated in line with Waste Separation Requirements (Wales) Regulations 2023. Ecofficiency to manage all waste movements and disposal, all relevant waste transfer notes to be kept. It is expected that any excavated material will retain on site. However, if off-site disposal is required the following will occur: • Material will be identified with testing • A material management plan will be developed under the CL:AIRE Code of Practice. • Suitable storage areas will be identified to process and dry out materials.
7.10) Water Management |  |  |  |  | PFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
EN-p-001 - Waste Management Procedures
EN-f-010 Site Waste Management Plan
EN-f-025 Flood Management Plan (Project Specific) - please see grounds for completion within the document
EN-f-026 Surface Water Management Plan (Site Specific) - please see grounds for completion within the document
GPP 5 Works and maintenance in or near water
In certain areas water can be extracted from the water network to be used on site including water for welfare facilities and dust suppression using licenced standpipes. Prior to the use of a stanpipe, the appropriate licences and permissions must be in place. For further information refer to TBT 140. | [8 empty] | TBT 140
Spill Kit Awareness Internal Training will be delivered to the project team to prevent any incidents occurring during handling and use of chemicals and fuels.. Spill kits will be available within each plant / vehicle on-site and also located close to identified pollution sources or sensitive receptors. Refuelling will only be undertaken at designated refuelling areas (e.g., on hardstanding, with spill kits available, and >10 m from drainage entry points and the River Dee, where practicable). Only designated trained and competent operatives will be authorised to refuel plant. Generators, and other ancillary plant and NRMM, where there is a risk of leakage of oil or fuel, will have internal bunding OR must have a secondary containment system (e.g., drip trays, plant nappies, etc.) placed beneath them that meets 110% capacity requirements. Containment systems will also be emptied regularly. The Pollution Control Plan outlines all mitigation, controls and response measures to be undertaken on the project. Due to the proximity of the works to waterbodies and the nature of the works, the most prevalent risks for the water environment are siltation and oil / diesel pollution, via accidental spillages and site run-off. These aspects will need to be managed during the course of the works by implementing and adhering to pollution prevention guidelines and the Marine License. The following PPG are of particular relevance to the works: • GPP1: Understanding your environmental responsibilities. • GPP5: Works and maintenance in or near water • GPP6: Working at construction and demolition sites. • GPP21: Pollution incident response planning • GPP22: Dealing with spills. Pollution prevention guidelines and good working practices to be strictly adhered to during the construction phase of works. Daily environmental checks will be undertaken to make sure we are not contaminating the watercourse. These checks will either be recorded on a paper document or through jones bros' system of PIM mobile checks, these can then be printed and displayed when needed. For each phase, the environmental assessment recommends the following embedded mitigation: Construction Practice working methods to prevent water pollution, appropriate storage of hydrocarbons and petrochemicals, water contaminated with hydrocarbons are passed though oil interceptors, prevent silt-laden run-off or chemicals entering watercourse, and measured to prevent soil becoming compacted. Operation Infrastructure in line with CIRIA C753, and guidance by BSIDB and LLFA, to make sure that surface water run-off is the same before and after development. Potential effects during the construction phase of the scheme include: • Surface water drainage – flows and quality • Construction site runoff – suspended fine sediments and chemical spillages • Changes to drainage channels on-site and surrounding watercourses • Temporary increase in impermeable area and ground compaction • Impacts to groundwater recharge • Impact on flood risk.
7.11) Storage |  |  |  |  | PFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
EN-p-003 Oil Storage & Handling
EN-f-015 Pollution Control Plan
There will be a combination of central storage and workplace storage used on site, the balance between them will depend on the works in progress. It is important to manage storage areas well because they set an example for the site. The following points will be taken into consideration: - i) Ensure that the material suppliers’ instructions on storage are being followed ii) Store materials that are valuable or attractive to thieves in a secure area. iii) Store materials away from waste storage containers and from vehicle movements that could cause accidental damage. iv) Secure lightweight materials to protect them from wind damage or loss. v) Take special care over the storage of materials that are potentially polluting.
All fuels, chemicals (COSHH), hazardous wastes and other potential pollutants likely to arise on the project will be stored and handled in line with the Pollution Control Plan, Spill Kit Awareness Training and Oil Storage and Handling Procedure to mitigate an environmental incident. All materials must be stored appropriately to avoid slips, trips, falls, fires and pollution events, with any poor practices submitted to the HSE Team via Incident Prevention Cards to allow lessons to be learned across the business.
7.12) Fuelling |  |  |  |  | PFC067 - Project Plant Equipment and Labour Planning Management |  |  |  | Please Specify:
EN-p-002 Spill Response Procedure
EN-a-002 Environment Daily Generator Fuel Recording (Mandatory)
All refuelling must follow the Jones Bros refuelling procedure, with any spill incidents notified to the Jones Bros HSE Team within 2 hours and spill response procedure followed. Re-fuelling, where practicable will be undertaken in the main site compound. Refuelling will only be undertaken at designated refuelling areas (e.g., on hardstanding, with spill kits available, and >10 m from drainage entry points and the River Dee, where practicable). Only designated trained and competent operatives will be authorised to refuel plant. Generators, and other ancillary plant and NRMM, where there is a risk of leakage of oil or fuel, will have internal bunding OR must have a secondary containment system (e.g., drip trays, plant nappies, etc.) placed beneath them that meets 110% capacity requirements. Containment systems will also be emptied regularly. Spill Kit Awareness Internal Training will also be delivered to the project team to prevent any incidents occurring dueing handling and use of chemicals and fuels. The Pollution Control Plan outlines all mitigation, controls and response measures to be undertaken on the project. The Main Compound will include bunded refuelling areas, and operations will only be permitted where they comply with method statement/requirements. The refuelling team will be trained and competent operatives. Fuel pipes on plant, outlets at fuel tanks etc. will be regularly checked and maintained to ensure that no drips or leaks to ground occur. Spill kits will be available within each plant / vehicle on-site and also located close to identified pollution sources or sensitive receptors (fuel storage areas etc.).
7.13) Site Security |  |  |  |  | PPFC059 - Site Set Up & Maintenance - Environmental |  |  |  | Please Specify:
HS-p-011 - Setting Up Site
HS-f-100–Setting Up Site Checklist
The site will be overseen by security gaurds. The site will remain secure from any vandals or thieves, with suitable security measures in place as per the Environmental Risk Assessment and Pollution Control plan to mitigate against unwanted access and damage to areas of the site which could lead to pollution (e.g. fuel bowsers or COSHH Stores).
SECTION 8 CEMP |  |  | EMERGENCY PREPAREDNESS AND RESPONSE
(a) The Jones Bros spill response procedure is to be followed which requires each site to register with Adler & Allen who provide 24 hour emergency spill, flood and disaster response All sites must use a site registration form. Registration with Adler & Allen will minimise any potential detrimental environmental impacts.
EN-p-002 - Spill Response Procedure
EN-f-018 Adler & Allen Site Registration
(b) A Pollution Control Plan (PCP) is to be developed and made available to all site personnel. Additionally, the Site Management team will ensure that this PCP is tested at least once and that site personnel are adequately trained in its requirements.
EN-f-015 - Pollution Control Plan
(c) The Site Management team will ensure that environmental emergency equipment (e.g. spill kits) appropriate to the significance of the spill risk and the sensitivity of the surrounding environment are appropriately located and maintained on site.
(d) In the event of a major hazardous material spill incident (i.e., incidents which cannot be dealt with using equipment available on site or spills / pollution which have, or are likely to, enter(ed) a watercourse / drain) site personnel should call the following 24-hour national spill response hotline:
24 Hour Spill Response:
{Adler & Allan} | [5 empty] | {0800 592 827}
(e) Callout personnel for 24-hour coverage shall be arranged by the Site Management Team to take control of and investigate out of hours incidents. The names and contact numbers of these personnel, and the Environment Agency’s / Scottish Environment Protection Agency’s Local Area Office, are displayed on site and related to site personnel during the induction process.
(f) The HSE Manager will, when necessary, report incidents to the Scottish Environment Protection Agency (SEPA) via:
1. Natural Resources Wales | [7 empty] | 0300 065 3000
2. Environment Agency | [7 empty] | 03708 506 506
(g) In the event that the project team identify a suspected cultural heritage asset (e.g., archaeological artefact) all construction related works in the immediate vicinity shall be stopped. Thereafter, the find should be reported to the Site Manager and the HSE Manager who will take all necessary and appropriate action(s), as defined in the Jones Bros Operational Control for Cultural Heritage (pending).
(h) Furthermore, in the event that the project team identify suspected rare or invasive plant species and / or rare fauna (e.g., Great Crested Newts, Water Voles, Bats, Barn Owls, Badgers and breeding Birds) all construction related works in the immediate vicinity shall be stopped. Thereafter, the find should be reported to the Senior Site Manager and the HSE Advisor who shall take all necessary and appropriate action(s), as defined in the Jones Bros Operational Control for Ecology (pending).
8.1 Arrangements for Reporting Significant Environmental Incidents | [7 empty] | PFC025 - Incident Prevention and Notification Reporting Process
(a) Senior Site Manager will notify the Regional Director and the HSE Manager as soon as details are confirmed, but no later than 2 hours after incident occurrence.
(b) Following contact with the Regional Director and the HSE Manager, the Environment Agency / Natural Resources Wales or local authority shall be contacted, when necessary, by telephone as soon as practicable, but no later than one (2) hours after incident confirmed (refer to contact details below).
(c) An HSE Incident Report using the mobile app form must be completed and sent to the HSE Manager.
HS-a-020 H&S - Incident Notification Form (Available on the PIM mobile application)
(d) Jones Bros shall notify the client details of any accident or significant incident as soon as practicable after its occurrence. Jones Bros shall maintain records and make reports concerning the environmental incident/accident as required by law.
8.2 Arrangements for Reporting Near Miss/Minor Environmental Incidents | [6 empty] | PFC025 - Incident Prevention and Notification Reporting Process
(a) Near Miss and Environmental Incidents shall be reported by the Site Manager to Regional Directors and HSE Manager within 2 hours via completing of a HS-a-020 H&S - Incident Notification form using the company mobile application
HS-a-020 H&S - Incident Notification form (Available on the PIM mobile application)
When any one on site identifies an Improvement Suggestion, Good Practice/Safe Act, Unsafe Act, Unsafe Condition, Unsafe Procedure, Environment they will follow the incident prevention and notification reporting process above but will report the using an incident prevention paper card available on in the compound office or by using the HS-a051 H&S incident prevention card custom form available on the PIM application.
HS-f-094 Incident Prevention Card Template (Paper Card)
or by using the custom form available on the mobile app that can be set to notify all interested parties on site and in the HSE team, internal users on the project should be set to (Item Reviewer)
HS-a-051 - H&S - Incident Prevention Card (available on the PIM application)
HS-T-001 - Together Safer Incident Prevention & Control Process Presentation
HS-T-002 -Together Safer Poster How to Transfer an Incident Prevention Paper Card to Pansophy Site Managers
HS-T-003 -Together Safer Poster How to Use an Incident Prevention Card using the mobile App
(b) Jones Bros shall notify the client of any near misses as soon as practicable after its occurrence. Jones Bros shall maintain records and make reports concerning the environmental incident/accident as required by Laws. Minor environmental incidents will be discussed in weekly meetings.
SECTION 9 CEMP |  |  | MONITORING AND MEASURING
(a) Continuous monitoring of environmental performance is achieved via the Jones Bros Process for Monitoring and Measuring Health, Safety and Environment Performance which assesses employees' and contractors' compliance within the requirements of the BMS, this and other plans and the Client and statutory obligations.
PFC059 - Site Set Up & Maintenance - Environmental
(b) HSE inspections are conducted by the HSE Advisor with any findings being copied to the Site Manager who will ensure that appropriate corrective and remedial action(s) are taken in a timely manner. Environmental information from HSE inspections is collated by the HSE Department and analysed for any arising trends. From this analysis, preventative action is taken to prevent recurrence – re-briefings, toolbox talks, etc.
PFC030 - Workplace Inspections(S)
(c) The Site Management Team, with the assistance of the HSE Advisor, will issue Environmental Site Notices on relevant topics e.g., pollution prevention, waste, noise and vibration, which shall be displayed in prominent locations.
(d) The Site Management Team, with the assistance of the HSE Advisor, will ensure that any method statements containing environmental management controls and this EMP are prepared, regularly reviewed and updated as required.
(e) Project audits against the Jones Bros BMS, the requirements of ISO50001 Energy Management, ISO14001 Environmental Management and relevant legislative and other commitments are periodically carried out by the HSE Advisor. Any non-compliance identified is issued to the Site Management team who ensure that timely corrective and preventative action(s) are implemented.
SECTION 10 CEMP |  |  | ENERGY MANAGEMENT (EM)
(a) If the project is valued at over £1 million or a duration of over 20 weeks then the appointment of an energy management champion is required
JB-Policy-007 - Energy Policy
BP-p-004 - Jones Bros Group Business Management System Quality Manual
EN-a-001 Environmental Inspection Daily Check (Mandatory) (Available on the PIM application) Contains a section on Energy Efficiency
EN-a-002 Environment Daily Generator Fuel Recording (Mandatory) (Available on the PIM application)
EN-p-004 - Energy Efficient Procurement
Project Energy Management Champion (Only if project is valued at over £1 million and/or over 20 weeks in duration) |  | (Insert name) |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
SECTION 11 CEMP |  |  | TRAINING, AWARENESS AND COMPETENCY
(a) Courses are run by the Jones Bros HSE Team covering various environmental issues.
(b) The site induction is used to promote overall environmental awareness as well as employee and contractor environment management responsibilities. This site induction is further enhanced through a series of toolbox talks that will be delivered to relevant site personnel on an on-going basis. The environmental toolbox talks that shall be delivered on this project are as follows: (refer to the HSEQ Tool Box Talk index below)
HSEQ Toolbox Talk Index (Contains a list with links to all previously delivered Health & Safety and Environmental toolbox talks)
(c) Attendance at inductions will be recorded using
HS-f-020 - Site Induction Form (paper form) | [5 empty] | HS-f-020a Visitors Site Induction Form
or Mobile App Form
HS-a-022 - H&S - Site Induction
All Inductions will be registered on the
HS-f-019 - Induction Register
Site specific training requirements such as toolbox talks will be delivered in accordance with
HS-p-001 - Managing Health & Safety at Work
and recorded using
HS-f-035 - Toolbox Talk Form (toolbox talk template)
HSEQ Toolbox Talk Index (Contains a list with links to all previously delivered Health & Safety and Environmental toolbox talks)
HSEQ Alert Index (Contains a list with links to all previously delivered Health & Safety and Environmental alerts)
and registered on a
HS-f-007 - Briefing Register (For all RAMS, Toolbox, COSHH Alerts Permit to Works and More Briefings)
The records are retained by the Site Management Team located in the Project Filing Structure {07 Project administration 07.02 Record & Logs 07.02.10 Site Inductions}
(d) At the start of the Project, the Site Management team will review the environmental training requirements of site staff and operatives using the TR-t-001 Staff Training Matrix and ensure any additional training is arranged through the Work Force & Training Manager to address identified deficiencies.
TR-t-001 Staff Training Matrix
(e) Employees are deemed to be environmentally competent once they have fulfilled the environmental training requirements defined within the Master Qualification Matrix and attended the site induction. Subcontractor personnel are deemed to be environmentally competent once they have attended the site induction and they hold a Construction Skills Certification Scheme (CSCS) card.
TR-f-002 -Master Qualification Matrix
(f) Letter drops or similar will be carried out to potentially affected third parties informing them of any work that may impact upon them. Additionally, consultations are held with interested parties (i.e., regulatory authorities and members of the public), where letter drops are deemed ineffective.
Communication Plan Process
BP-p-003 - Communication Plan
SECTION 12 CEMP |  |  | RECORD REFERENCING MATRIX
Explanatory Notes:-
To support the effective management of projects and remove the potential for duplication of information and effort, all records referred to in this plan are filed in the Jones Bros Project Filing Structure whilst the records are continuing to be updated and the project is live. The following matrix supports the navigation and archiving of project records. It enables project teams and third parties (as applicable) to easily navigate the Project Filing Structure.
NOTE: OPERATIONAL CONTROL PROCEDURES PENDING WHICH WILL DEFINE FORMS
Environment Plan Section Reference |  | Record Description |  |  |  | BMS Format |  | Project Filing Location
1.1 |  | Project Appointment Matrix |  |  |  | PROJECT ROLES & RESPONSIBILITES |  | 07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
1.1 |  | Specific Appointment Letters | [5 empty] | 07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
5 |  | Consents and Permits |  |  |  | EN-f-024 - Environmental Aspects and Impacts Risk Assessment |  | 07 Project Administration\07.07 Health and Safety\07.07.06 Work Permits.
6 |  | Environmental Risk Assessment |  |  |  | EN-f-024 - Environmental Aspects and Impacts Risk Assessment |  | Document Store\07 Project Administration\07.08 Environmental\07.08.03 Risk Assessments
7.1 |  | Incident Reporting Form |  |  |  | HS-a-020 H&S - Incident Notification Form |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.13 Incidents and Investigations
7.2 |  | Briefing Records |  |  |  | HS-f-007 - Briefing Register |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.16 Daily Briefings
7.2 |  | Induction Records |  |  |  | HS-f-019 - Induction Register |  | Document Store\07 Project Administration\07.02 Records / Logs\07.02.10 Site Inductions
7.2 |  | Toolbox Talk Records |  |  |  | HS-f-007 - Briefing Register |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.16 Daily Briefings
7.3 |  | Ecology |  |  |  | EN-f-024 - Environmental Aspects and Impacts Risk Assessment |  | Document Store\07 Project Administration\07.08 Environmental\07.08.03 Risk Assessments
7.4 |  | Hazardous Materials |  |  |  | HS-f-031 - COSHH Assessment HS-f-022 - COSHH Inventory |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.05a COSHH Assessments
7.5 |  | Housekeeping and Safe Access |  |  |  | HS-f-100 - Setting Up Site Safety Checklist |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
7.6 |  | Land Use and Management |  |  |  | HS-f-031 - COSHH Assessment HS-f-022 - COSHH Inventory |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.05a COSHH Assessments
7.7 |  | Nuisance Management |  |  |  | EN-f-014 - Noise & Vibration Management Plan |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
7.8 |  | Resource Management |  |  |  | PL-f-007 - Project Resource Requirements and CTC |  | Document Store\07 Project Administration\07.26 Plant & Labour Resource Management\07.26.02 Resource Forecasts
7.1 |  | Waste Management |  |  |  | EN-f-010 - Site Waste Management Plan |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
7.11 |  | Water Management |  |  |  | EN-f-010 - Site Waste Management Plan |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
7.12 |  | Storage |  |  |  | EN-f-015 - Pollution Control Plan |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
7.13 |  | Fuelling |  |  |  | EN-a-002 Environment Daily Generator Fuel Recording (Mandatory) |  | Document Store\07 Project Administration\07.02 Records / Logs\07.02.06 Environmental
7.14 |  | Site Security |  |  |  | HS-f-100–Setting Up Site Checklist |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
8 |  | Spill Response Plan |  |  |  | EN-f-015 - Pollution Control Plan |  | Document Store\07 Project Administration\07.08 Environmental\07.08.02 Environmental Plan
8.1 |  | Arrangements for Reporting Significant Environmental Incidents |  |  |  | HS-a-020 H&S - Incident Notification Form |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.13 Incidents and Investigations
8.2 |  | Arrangements for Reporting Near Miss/Minor Environmental Incidents |  |  |  | HS-f-094 Incident Prevention Card Template (Paper Card) |  | Document Store\07 Project Administration\07.07 Health and Safety\07.07.17 Incident Prevention Cards
9 |  | Inspections and Audit Reports |  |  |  | EN-a-007 - Environment - Site Inspection Report |  | Document Store\07 Project Administration\07.08 Environmental\07.08.05 Site Inspections & Records
SECTION 13 CEMP |  |  | FURTHER GUIDANCE
Further guidance on Environmental matters is available from: |  |  |  |  | the HSE Team on 01824 703661 or E-mail hseqt@jones-bros.com
Note on C40: Click title to navigate to section
Note on C45: Click title to navigate to section
Note on C47: Click title to navigate to section
Note on C49: Click title to navigate to section
Note on C54: Click title to navigate to section
Note on C56: Click title to navigate to section
Note on C58: Click title to navigate to section
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content

## CHAP (hidden)
COMMISSIONING, HANDOVER AND AFTERCARE PLAN (CHAP)
Project Name: |  | A494 River Dee Bridge Deck over-slabbing Contingency Scheme
Project Number: |  | 21-NM-CHR-003
Project Details
Project Description: |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) have commissioned a project to develop a major maintenance intervention should a critical defect be identified within the A494 River Dee Bridge structure and enable this to be implemented with minimal impact on traffic conditions. The proposed design intervention comprises of removing a depth of existing road surfacing and replacing with a new thin reinforced concrete over-slab with combined waterproof and wearing membrane (hence forth referred to as the ‘over-slabbing works’). Enabling works are required to parts of the central reserve and to the Riverside Way Junction to facilitate contraflow traffic management arrangements during construction. The enabling works consist of construction 2Nr crossovers through the central reserve west of the existing bridge and works to widen the Riverside Way Junction.
Project Location: |  |  | Enter your project location here
Plan Approvals
Written by: |  | Name: | 0 |  |  | Signature: | 0 |  | Date: | 0
Approved by: |  | Name: | 0 |  |  | Signature: | 0 |  | Date: | 0
Explanatory Notes:-
Origination: Tender phase origination resides with the Project Manager. Construction Phase update will be the responsibility of the Site Manager.
Approval: Tender phase approval resides with the Contracts Manager or Regional Director. Construction Phase approval will be the responsibility of the Project Manager.
Revision: The plan will be revised to reflect changes that have been made to the product, project or contract, work practices, service provision or Quality Assurance procedures. Where changes are made to the plan an assessment of the impacts of the changes will be carried out and recorded in the Version Control section below.
Version Control
Description of changes |  |  |  | Date | Revision | Page No. | Comments
Explanatory Notes:-
This Plan will be added to, reviewed and updated as the project develops, further design work is completed, information from subcontractors starting work becomes available, unforeseen circumstances or variations to planned circumstances arise or where the operations management team deem it necessary.
If sections are deemed not applicable DO NOT DELETE. Replace text with "not applicable on this project".
CONTENT
Section Ref |  | Content | [6 empty] | Comments
Introduction
1.0 |  | Project Information and Scope
| 1.1 | Scope of Works
| 1.2 | Project Timescale
| 1.3 | Call-out Process
2.0 |  | Organisation and Responsibilities
| 2.1 | Roles and Responsibilities
| 2.2 | Commissioning, Handover and Aftercare Responsibilities
| 2.3 | Reporting
3.0 |  | Co-ordination of Installation and Commissioning
4.0 |  | Commissioning Scope
| 4.1 | Process Units (Turnover Packages)
| 4.2 | Supporting Services
| 4.3 | Interfaces
| 4.4 | Programme
5.0 |  | Design Performance
| 5.1 | Design Considerations
| 5.2 | Performance Criteria
6.0 |  | Risk Management
| 6.1 | Commissioning Activities
| 6.2 | Risk Assessment
7.0 |  | Pre-commissining Requirements
| 7.1 | Off Site
| 7.2 | On Site
| 7.3 | Health and Safety Considerations
8.0 |  | As-Built Information
9.0 |  | Defects Management
10.0 |  | Restrictions and Constraints
11.0 |  | Testing and Demonstration
12.0 |  | Training
13.0 |  | Handover Process
14.0 |  | Aftercare Arrangements
15.0 |  | Record Referencing Matrix
16.0 |  | Further Guidance
Explanatory Notes:-
In this template Plan, guidance and sample content is included where deemed necessary. This is indicated by the inclusion of yellow boxes with text in brackets { }. On completing this plan all sample and guidance text should be deleted or overwritten as required.
Introduction CHAP
(a) This Plan is a ‘stand alone’ document that is developed as part of an integrated and consistent set of plans – project management, design, CSR, health and safety and environment- Its purpose is to set the commissioning, handover and aftercare strategy with respect to roles and responsibilities and to review the solution from a commissioning perspective, and outline how we intend to commission the solution safely.
(b) This plan is mandated on all projects as part of the Jones Bros BMS and is therefore required to be in place and kept up to date throughout the project.
(c) The objectives of this plan are: i) To set the commissioning strategy with respect to roles and responsibilities; ii) To review the project from a commissioning perspective and describe how it is intended to commission the project; iii) To demonstrate in broad terms that the solution can be commissioned safely and efficiently; iv) To identify additional project specific information required to successfully plan commissioning; v) To identify key issues, risks and mitigating measures.
(d) In developing this plan consideration should be given to: i) Existing operational (or other) constraints including shutdown periods and/or tolerable reduced treatment capacities; ii) Key interface issues; iii) Qualities, sources, storage and disposal/discharge of chemicals, raw materials (water) and/or other provision of other apparatus required to commission the plant; iv) The required documents that need to be available as a prerequisite to commissioning (O&M manuals, DSEAR certificates etc.); v) A broad start-up process; vi) The types of tests to be conducted – off site, completion, take-over and performance, including pass/fail criteria; vii) Measurements of the effectiveness of the treatment processes (as appropriate); viii) The outline timescales required; ix) The provision of facilities to enable commissioning e.g. sampling points, by-passes, flow, pressure, temperature and other measurements, cross-connections, ventilation points, drain points and dummy loads.
(e) We aim to reduce the provision of generic information and to only provide in this Plan project specific paperwork that should help with the communication and risk management of this project. Other non-project specific information referenced in this plan will be clearly identified with the location where it is available. If there is a need to review these documents they will be provided on request.
(f) This plan is a live document and will be updated throughout the project.
SECTION 1 CHAP |  |  |  | PROJECT INFORMATION AND SCOPE
1.1) Scope of Works CHAP
The A494 River Dee Bridge Deck Over-Slabbing Contingency Scheme is a major maintenance intervention that involves the replacement of the existing road surface with a new reinforced concrete over-slab and combined waterproof and wearing membrane. The works will be contained within the existing footprint of the bridges surface structure and above the existing concrete deck slab. Below deck debris netting will be installed and the top 75mm of the bridge deck, existing kerbs and movement joints removed and disposed off-site. Concrete deck repairs will be carried out and new structural mesh will also be installed across the entire bridge deck. The combined waterproof and wearing membrane shall also be applied to the hard verge and central reserve.
1.2) Project Timescale CHAP
Contract Award Date |  |  |  | {dd/mm/yyyy} |  | Commissioning Start |  |  | {dd/mm/yyyy}
Contract Commencement Date |  |  |  | {dd/mm/yyyy} |  | Practical Completion |  |  | {dd/mm/yyyy}
Contract Period |  |  |  | {xx weeks} |  | Take Over Certificate |  |  | {dd/mm/yyyy}
Site Start Date |  |  |  | {dd/mm/yyyy} |  | Planned Contract Completion |  |  | {dd/mm/yyyy}
1.3) Call-out Process
{Detail the obligations placed upon Jones Bros to provide out-of-hours response or response to warranty issues when the project is handed over. Include information around how we will respond to problems if we have to provide cover when Jones Bros staff are not on site; how alarms are managed and who the call centre contacts, for example, are we the first response?; details of who is on call with contact numbers; arrangements for entering site out-of-hours, keys, alarm codes, security company contact details, etc.; lone working arrangements, call-in procedures etc. Consider the need for a stand alone protocol that can be produced and issued, as appropriate, to those that need the information.}
SECTION 2 CHAP |  |  |  | ORGANISATION AND RESPONSIBLITIES
2.1) Roles and Responsibilities CHAP
(a) Agreed responsibilities for key roles are outlined in the BMS Manual. Specific duties and responsibilities are also identified and associated plans and process maps held in the Jones Bros BMS and where appropriate referenced throughout this plan.
(b) Specific Project HSEQ Responsibilities for this project have been defined and are allocated in accordance with the Project Appointment Matrix and relevant specialist appointment letters.
{PROJECT ROLES & RESPONSIBILITES}.
(c) Included below is a listing of project team members involved in the handover, commissioning and aftercare phase of this project.
(d) An organisation structure, identifying interfaces with other organisations, has been drafted and is appended to this plan.
Role |  | Name |  |  | Company |  | Address |  | E-mail | Telephone
Client |  | {insert name} |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) |  | Insert Address |  | {insert email} | {insert tel no.}
Client Contract Admin |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Principal Contractor |  | Jones Bros |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Workforce Planning Manager |  | Alan Manuel |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | alan.manuel@jones-bros.com | 07384834594
IT Infrastructure Section Manager |  | Gerallt Ellis |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | gerallt@jones-bros.com | 07584 705103
Jones Bros Internal Auditor |  | Ellis Ashton |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | ellisa@jones-bros.com | 07384 835329
Principal Designer |  | (Insert name) |  |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Designer |  | (Insert name) |  |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Architect |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Structural Engineer |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Mechanical Consultant |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Electrical Consultant |  | (Insert name) |  |  | Insert Company Name |  | Insert Address |  | {insert email} | {insert tel no.}
Contract Director |  | Hefin Lloyd-Davies |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | hefin@jones-bros.com | 07887 722560
Contracts Manager |  | Daniel Robat Williams |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | robat@jones-bros.com | 07787 100752
Project Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Agent |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Senior Works Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Works Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Foreman 1 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Foreman 2 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Foreman 3 |  | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Engineer 1 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Engineer 2 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Engineer 3 |  | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Commercial Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Quantity Surveyor |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Senior Health & Safety Manager |  | Michael Jolley |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | michaeljo@jones-bros.com | 07795 648184
Environment Manager |  | Sam Higgitt |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | samh@jones-bros.com | 07766 747133
Design Manager |  | Dylan Parry |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | dylan.parry@jones-bros.com | 07918 797076
Temporary Works Co-ordinator |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Temporary Works Supervisor |  | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | {insert address} |  | {insert email} | {insert tel no.}
Quality & Business Improvement Manager |  | Jonathan Dennehy |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | Jonathan.Dennehy@jones-bros.com | 07443265165
Quality Controller (Site Based) |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Document Controller (Site Based) |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Material Buyer |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Plant Administrator (Site Based) |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
CSR Co-ordinator |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
CSR Administrator (Site Based) |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Commissioning Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Commissioning Engineer |  | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Aftercare Supervisor |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Fire Officer |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 1 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 2 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 3 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
First Aider 4 |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Traffic Management Coordinator |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Traffic Management Supervisor |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Supplier 1 |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Supplier 2 |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Supplier 3 |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
Supplier 4 |  | {insert name} |  |  | {insert company} |  | {insert address} |  | {insert email} | {insert tel no.}
{insert additional}
2.2) Commissioning, Handover and Aftercare Responsibilities
An outline of key responsibilities through the CHAP phase is outlined in the Jones Bros Responsibilities Matrix
{PROJECT ROLES & RESPONSIBILITES}.
As each project, contract and Client may have different requirements it is intended that this guidance document be utilised and amended as required on a project.
2.3) Reporting
{Amend text below to reflect arrangements on the project - delete this text}
(a) The Commissioning Engineer reports directly to the Project Manager.
(b) Commissioning Team meetings will be held on a regular basis throughout the Project depending on the level of commissioning activity. A standard agenda shall be used and minutes taken at every meeting.
(c) {Define project specific requirements around reporting through the CHA phase of a project}
SECTION 3 CHAP |  |  |  | CO-ORDINATION OF INSTALLATION AND COMMISSIONING
{Amend text below to reflect arrangements on the project - delete this text}
(a) {Numerous shutdowns and/or isolations will be required throughout the project life}.
(b) {Service levels shall be agreed and detailed in the commissioning meeting minutes}.
(c) {A detailed method statement shall be produced by the Commissioning Engineer and agreed with the Client prior to intrusive works taking place}.
(d) The table below shall be populated for each intrusive activity}.
(e) {In all cases involving changes to the existing process stream, shutdown or isolation etc. of existing equipment, the necessary change, shutdown or isolation etc. shall be performed by Occupier}.
(c) {Define project specific requirements around reporting through the CHAP phase of a project}
Criteria |  |  |  |  | Agreed Service Level
SECTION 4 CHAP |  |  |  | COMMISSIONING SCOPE
4.1) Process Units (Turnover Packages)
Explanatory Notes:-
vii) Process Unit Definition: An individual part of the plant where changes are made to the process stream. List all process units that are relevant to the project such as: - contact tank, High lift pumps etc.
The following Process Units will be incorporated into the construction works for this project: {refer to a separate list if required}
Unit |  |  |  |  | Supplier |  |  | Installing Company
4.2) Supporting Services
Explanatory Notes:-
Supporting Plant Definition: An individual part of the plant essential for the process but not part of the process stream. Consider the requirements for power, chemicals etc.
The following Supporting Services will be impacted/ influenced as part of the construction works for this project: {refer to a separate list if required}
Plant |  |  |  |  | Specific requirements (if applicable)
4.3) Interfaces
Explanatory Notes:-
The Commissioning Engineer should consider areas of work where responsibility is not obvious. This may be interconnection of any sort between contractors, provision of a utility service, connection to existing client equipment, or ensuring licences and authorisations e.g. abstraction are provided.
There are numerous interfaces involved in the delivery of this project, including: - {refer to a separate list if required}
Project Interfaces |  |  |  |  | Specific arrangements/ considerations (if applicable)
4.4) Programme
(a) At the outset of the project design, the main programme will show the expected duration and timing of any commissioning activities. As the project progresses, more detail may be given on the timing of commissioning work on specific elements of work.
(b) During the commissioning phase, a detailed completion programme will be maintained by the Project Manager on a weekly basis in accordance with Jones Bros Process referenceG_PR_000).
PFC054 - Programme Preparation & Management(S)
SECTION 5 CHAP |  |  |  | DESIGN AND PERFORMANCE
5.1) Design Considerations
(a) The design team will review the design to ensure, as far as possible, sufficient and appropriate facilities will be available to allow the commissioning and handover to progress smoothly. Specific problems or risks will be identified and temporary facilities such as over-pumping will be outlined, in risk assessments and method statements.
(b) Considerations should include the requirement for: i) Access for testing, sampling and monitoring; ii) Provision of temporary works for testing and monitoring; iii) Provision for pipes and vessels to be tested to the specified pressures and flow rates; iv) Provision for testing over the full range of design conditions; v) Provision for functional testing of all electrical and ICA systems.
5.2) Performance Criteria
(a) The performance criteria for individual process should be based upon measurable inputs and measurable outputs.
(b) The process change can be established by measuring the inputs and outputs of a process unit.
(c) The process requirements for each process unit are detailed in the contract.
SECTION 6 CHAP |  |  |  | RISK MANAGEMENT
{Amend text below to reflect arrangements on the project - delete this text}
(a) {The design team and a member of the commissioning department will review the design to ensure, as far as possible, sufficient and appropriate facilities will be available to allow the commissioning to progress smoothly. Specific problems or risks will be identified and temporary facilities such as over-pumping will be outlined. The review may influence the design and will form the basis of the Process Commissioning Strategy}.
(b) {The Process Commissioning Strategy will contain the high level strategy for starting up the process once the individual process units have been dry and wet tested and are ready to receive process fluids. It will describe any process constraints which may affect flexibility during commissioning. The contractual guarantees and the expected normal operating parameters for each process unit will be summarised to allow the commissioning engineer to test the plant to known requirements}.
(c) {The commissioning strategy will normally be produced before construction begins or soon thereafter. When the construction is near completion and during the following commissioning phase, the commissioning engineer or commissioning co-ordinator may update the commissioning strategy document to suit current site and programme constraints}.
(d) {Whilst commissioning is an activity which requires a flexible and responsive approach, it is important to understand the limitations of the equipment, process and final destinations of all output streams from the plant. Significant changes to the intended process commissioning strategy must be recorded and notified to the process engineer or commissioning co-ordinator for checking and approval. This will help to prevent accidental but avoidable events such as contamination of drinking water, environmental pollution, flooding of structures or damage to equipment}.
(e) {In all cases involving changes to the existing process stream, shutdown or isolation etc. of existing equipment, the necessary change, shutdown or isolation etc. shall be performed by Occupier}.
6.1) Commissioning Activities
(a) The commissioning activities shall be undertaken in a manner that is appropriate to the size and complexity of the project.
(b) Regular meetings shall be held to review events and activities and update procedures accordingly.
(c) Contingency plans shall be in place should things go wrong.
(d) Good communications between all parties involved with commissioning must be maintained throughout. This shall be achieved through regular meetings and briefings.
6.2) Risk Assessments
(a) Risk Assessment and Method Statements will be provided for the workplace and for individual tasks undertaken on the project and permit to work systems will be introduced as applicable.
PFC013 - Risk Assessment Process(S)
(b) A register of all Jones Bros and contractors risk assessments/ method statements will be produced and located in the project filing structure 07 Project Administration\07.07 Health and Safety\07.07.03 Risk Assessments This will be updated as work progresses and contractors are appointed through the lifetime of the project. The Site Management Team will ensure that all risk assessments and method statements have been briefed to all relevant personnel and keep records of briefings held on site in the Project Filing Structure Document Store\07 Project Administration\07.07 Health and Safety\07.07.16 Daily Briefings
SECTION 7 CHAP |  |  |  | PRECOMMISSIONING REQUIREMENTS
7.1) Off Site
(a) The purpose of these tests is to demonstrate that the items of equipment have been manufactured to the required standards before they leave the manufacturer's works.
(b) Satisfactory completion of these tests will allow the equipment to be delivered to site.
(d) All test certificates required to support handover are listed on
(e) Details of planned Acceptance Tests are inserted into the table below {refer to a separate list if required}. All test documentation shall be inserted into the {Commissioning Manual, which forms part of the O&M Manuals}.
Equipment |  |  |  | Manufacturer |  | Location of Test |  |  | Planned Date
7.2) On Site
(a) The purpose of these tests is to demonstrate that the equipment and control systems have been installed and pre-commissioned correctly. Such tests will provide confidence that the plant is ready to receive product for full commissioning.
(b) Satisfactory completion of these tests will prove that the plant is substantially complete and in a condition to allow safe start-up with product.
(c) All test certificates required to support handover are listed in:FM_000). | [5 empty] | Document Store\07 Project Administration\07.02 Records / Logs\07.02.07 Quality
7.3) Health and Safety Considerations
(a) Prior to the commencement of the commissioning activities, all relevant construction/completion inspection sheets for the relevant area shall be completed and sign-off by the discipline (civil, mechanical, electrical) supervisor.
(b) All commissioning activities will be carried-out in accordance with the Jones Bros Health and Safety Processes. The Construction Phase Health and Safety plan will take precedence at all times.
(c) A system of visibly indicating the commissioning status of any area will be employed on this project. The arrangements for which are outlined below.
Visibility System
{insert site specific arrangements e.g. As the testing progresses, the area status will be updated through the three states: 1. Red Signage – Power source and services connected but safety systems not tested. 2. Yellow Signage – Dry tested and safety systems tested as functional. 3. Blue Signage – Available for operational use or in operation.}
SECTION 8 CHAP |  |  |  | AS-BUILT INFORMATION
Good as-built information is not only critical to the client for operation of the building, it also serves as a source of information on which future designs will be based.
{insert site specific arrangements for the generation of as-built information e.g. It is the responsibility of the commissioning engineer to record as-built information by marking-up the following key design documents as the commissioning progresses or to ensure that another party is performing this task, e.g. software subcontractor. 1. Pipe and instrumentation diagrams (P&IDs). 2. Control Philosophy and/or Functional Design Specification (FDS). Any change in the Control Philosophy or FDS should be agreed in advance with the Lead Design Engineer). It is also the responsibility of the commissioning engineer to return the amended documents, or ensure their return, to the Project Manager for updating and re-issue prior to the final handover of the project to the client. The site supervisors, subcontractors or other staff may mark up the schedules by agreement with the commissioning engineer.}
SECTION 9 CHAP |  |  |  | DEFECTS MANAGEMENT
(a) All defects identified through this process will be managed in accordance with the Jones Bros project close out process
PFC034 - Project Close Out(S)
(b) A defect register shall be maintained by the commissioning engineer and located in the project filing structure.
QA-f-029 - Notification of a Defect
SECTION 10 CHAP |  |  |  | RESTRICTIONS AND CONTRAINTS
(a) Restrictions and constraints shall be discussed at the Commissioning Team Meetings.
(b) Restrictions and constraints shall be considered when producing detailed method statements for commissioning. | [8 empty] | #REF!
(c) In the event that restrictions or constraints may prevent full commissioning and testing of the project to the design requirement, the Commissioning Engineer and Project Team should consider alternative methods of testing accordingly.
Project Specific Restrictions and Constraints
{insert project specific restrictions and constraints, as applicable}
SECTION 11 CHAP |  |  |  | TESTING AND DEMONSTRATION
(a) Where possible, individual items of plant shall be tested to prove correct operation.
(b) Tests will prove the plant to its full design limits (under a variety of conditions) if possible.
(c) It is not always possible to test the plant to its design limits due to loadings or demand not being present. In these circumstances, the Commissioning Team shall look at carrying-out ‘scaled’ tests to simulate full loading or demand.
(d) In the event that restrictions or constraints may prevent full commissioning and testing of the project to the design requirement, the Commissioning Engineer and Project Team should consider alternative methods of testing accordingly.
(e) Specific arrangements for testing and demonstration are outlined in the Completion Programme for this project.
(f) To support an effective aftercare process the Aftercare Supervisor will be invited to attend key testing and demonstrations.
Project Specific Requirements are outlined below
{insert project specific arrangements/ requirements, as applicable}
SECTION 12 CHAP |  |  |  | TRAINING
{Amend text below to reflect arrangements on the project -delete this text}
(a) {The Training Plan will be developed to outline the training to be offered for Client staff and end users, as appropriate, and stating the timescales involved with delivering the required training}.
(b) {The training will be managed by Jones Bros using in-house staff supported by subcontractors, to ensure that the relevant Client and End User personnel have sufficient information to operate the plant/ building/ asset safely}.
(c) {The training will cover process design parameters, health and safety requirements, and health and safety awareness}.
(d) {A Training Plan has been produced for this project and is located in the project filing structure
SECTION 13 CHAP |  |  |  | HANDOVER PROCESS
(a) The Project Manager is responsible for handover to the client and a specific list of requirements is defined in the construction procedures.
(b) The Handover process will be undertaken in accordance with:(CON_PR_000).
PFC034 - Project Close Out(S)
(c) A Handover meeting will be arranged with the Client team as earlier as possible to define key requirements of Jones Bros and the Client Team throughout this critical phase. (Regular meetings maybe required through this phase to support staged handover).
(d) An agenda will be agreed to ensure that the Handover Day achieves Client and Contractors objectives (CON_FM_000).
(e) {Define any Client or End User specified requirements that will require amendment to or deviations from the Jones Bros Standard Process}
SECTION 14 CHAP |  |  |  | AFTERCARE ARRANGEMENTS
[5 empty] | Name |  | E-mail |  | Tel No.
(a) The Aftercare Supervisor on this project is |  |  |  |  | (Insert name) |  | {insert email} |  | {insert tel no.}
(b) The process of aftercare will be managed in accordance with the Jones Bros process
PFC034 - Project Close Out(S)
(c) {Define any Client or End User specified requirements that will require amendment to or deviations from the Jones Bros Standard Process}
SECTION 15 CHAP |  |  |  | RECORD REFERENCING MATRIX
Explanatory Notes:-
To support the effective management of projects and remove the potential for duplication of information and effort, all records referred to in this plan are filed in the Jones Bros Project Filing Structure whilst the records are continuing to be updated and the project is live. The following matrix supports the navigation and archiving of project records. It enables project teams and third parties (as applicable) to easily navigate the Project Filing Structure.
NOTE: OPERATIONAL CONTROL PROCEDURES PENDING WHICH WILL DEFINE FORMS
Plan Section Ref. | Record Description | [5 empty] | BMS Format |  | Project Filing Location
2.1 | Project Appointment Matrix | [5 empty] | PROJECT ROLES & RESPONSIBILITES |  | PROJECT ROLES & RESPONSIBILITES
2.1 | Specific Appointment Letters
2.3 | Progress Reports
4.1 | Schedule of Process units (if not listed in plan)
4.1 | Schedule of Supporting Services (if not listed in plan)
4.3 | Schedule of Interfaces (if not listed in plan)
4.4 | Completion Programme
6.2 | Task Specific Risk Assessments
6.2 | Method Statements
6.2 | Permits
7.1 | Schedule of Factory Acceptance Tests (FATs) (if not listed in plan)
7.2 | On Site Testing Documentation
8 | As-Built Records
9 | Snagging and Defects Register | [7 empty] | QA-f-029 - Notification of a Defect
12 | Training Plan (Commissioning Phase)
13 | Completion Certificate
13 | List of Outstanding Works
14 | Aftercare Fault or Query Report
14 | Aftercare Fault Tracking Schedule
SECTION 16 CHAP |  |  |  | FURTHER GUIDANCE
Further guidance on Quality matters is available from: |  |  |  |  | Tony Murphy, Internal Projects and Quality Manager Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW Office: Telephone 01824 703661 Ext 143 Mobile: 07768 375714
Further guidance on technical matters and temporary works is available from Name here
Note on C39: Click title to navigate to section
Note on C44: Click title to navigate to section
Note on C49: Click title to navigate to section
Note on C51: Click title to navigate to section
Note on C57: Click title to navigate to section
Note on C61: Click title to navigate to section
Note on C65: Click title to navigate to section
Note on C70: Click title to navigate to section
Note on C72: Click title to navigate to section
Note on C74: Click title to navigate to section
Note on C76: Click title to navigate to section
Note on C78: Click title to navigate to section
Note on C80: Click title to navigate to section
Note on C82: Click title to navigate to section
Note on C84: Click title to navigate to section
Note on C86: Click title to navigate to section
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content

## TMP
TRAFFIC MANAGEMENT PLAN (TMP)
Project Name: |  | A494 River Dee Bridge Deck over-slabbing Contingency Scheme
Project Number: |  | 21-NM-CHR-003
Project Details
Project Description: |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) have commissioned a project to develop a major maintenance intervention should a critical defect be identified within the A494 River Dee Bridge structure and enable this to be implemented with minimal impact on traffic conditions. The proposed design intervention comprises of removing a depth of existing road surfacing and replacing with a new thin reinforced concrete over-slab with combined waterproof and wearing membrane (hence forth referred to as the ‘over-slabbing works’). Enabling works are required to parts of the central reserve and to the Riverside Way Junction to facilitate contraflow traffic management arrangements during construction. The enabling works consist of construction 2Nr crossovers through the central reserve west of the existing bridge and works to widen the Riverside Way Junction.
Project Location: |  |  | Enter your project location here
Plan Approvals
Written by: |  | Name: | 0 |  |  | Signature: | 0 |  | Date: | 0
Approved by: |  | Name: | 0 |  |  | Signature: | 0 |  | Date: | 0
Explanatory Notes:-
Origination: Tender phase origination resides with the Project Manager. Construction Phase update will be the responsibility of the Site Manager.
Approval: Tender phase approval resides with the Contracts Manager or Regional Director. Construction Phase approval will be the responsibility of the Project Manager.
Revision: The plan will be revised to reflect changes that have been made to the product, project or contract, work practices, service provision or Quality Assurance procedures. Where changes are made to the plan an assessment of the impacts of the changes will be carried out and recorded in the Version Control section below.
Version Control
Description of changes |  |  |  | Date | Revision | Page No. | Comments
Explanatory Notes:-
This Project Management Plan will be added to, reviewed and updated as the project develops, further design work is completed, information from subcontractors starting work becomes available, unforeseen circumstances or variations to planned circumstances arise or where the operations management team deem it is necessary.
If sections are deemed not applicable DO NOT DELETE. Replace text with not applicable on this project.
CONTENT
Section Ref |  | Content | [6 empty] | Comments
Introduction
1.0 |  | SCHEME PROPOSAL
| 1.1 | Responsibilities
| 1.2 | Scope of works
| 1.3 | Proposal
2.0 |  | DISPLAY/COMMUNICATION OF INFORMATION
2d,e,f |  | Traffic Management Drawings, Plans, Photos
3.0 |  | SPEED LIMITS
4.0 |  | RE-FUELLING
5.0 |  | DELIVERIES
6.0 |  | INTERNAL TRAFFIC HAZARDS
7.0 |  | PEDESTRIAN TRAFFIC
8.0 |  | PUBLIC INTERFACE
9.0 |  | EMERGENCY ARRANGEMENTS
10.0 |  | HIGHWAYS TEMPORARY TRAFFIC MANAGEMENT
11.0 |  | RECORD REFERENCING MATRIX
12.0 |  | FURTHER GUIDANCE
Explanatory Notes:-
in this template Plan, guidance and sample content is included where deemed necessary. This is indicated by the inclusion of yellow boxes with text in brackets { }. On completing this plan all sample and guidance text should be deleted or overwritten as required.
Introduction TMP
(a) This Traffic Management Plan (TMP) is a controlled document that outlines the arrangements Jones Bros propose to implement on this project. It sets out the project specific arrangements to control and manage the hazards and risks involved with the movement of construction plant and delivery vehicles around the site, the interface between site plant, vehicles and pedestrians.
SECTION 1 TMP |  |  |  | SCHEME PROPOSAL
1.1) Responsibilities TMP
(a) Agreed responsibilities for key roles are outlined in the BMS Manual. Specific duties and responsibilities are also identified in associated plans and process maps held in the Jones Bros BMS and, where appropriate, referenced through this plan.
(b) A copy of the appointments is displayed on the project’s health and safety notice board and in the Project Appointment Matrix of this document:
{PROJECT ROLES & RESPONSIBILITES}.
(c) Specific responsibilities for this project have been defined and are allocated in this document and in the and in relevant specialist letters as appropriate.
{PROJECT ROLES & RESPONSIBILITES}.
(d) All appointments on the matrix and standalone specialist letters are signed by the respective individuals which is deemed as acceptance and understanding of the responsibilities therein.
(e) Appointments will be reviewed and updated throughout the project, reflecting any changes or movement in the project as required. Changes in appointments will be administered through a Project Appointment Addendum form (CON_FM_000).
Role |  | Name |  |  | Company |  | Address |  | E-mail | Telephone
Client |  | {insert name} |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) |  | Insert Address |  | {insert email} | {insert tel no.}
Project Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Site Manager |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Traffic Management Coordinator |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
Traffic Management Supervisor |  | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW |  | {insert email} | {insert tel no.}
{insert additional}
1.2) Scope of Works TMP
The A494 River Dee Bridge Deck Over-Slabbing Contingency Scheme is a major maintenance intervention that involves the replacement of the existing road surface with a new reinforced concrete over-slab and combined waterproof and wearing membrane. The works will be contained within the existing footprint of the bridges surface structure and above the existing concrete deck slab. Below deck debris netting will be installed and the top 75mm of the bridge deck, existing kerbs and movement joints removed and disposed off-site. Concrete deck repairs will be carried out and new structural mesh will also be installed across the entire bridge deck. The combined waterproof and wearing membrane shall also be applied to the hard verge and central reserve.
1.3) Proposal
We propose to implement {insert information relating to traffic management} that will enable us to {insert benefits to the project, including health and safety improvements and additional information as needed}
SECTION 2 TMP |  |  |  | DISPLAY/COMMUNICATION OF INFORMATION |  |  |  |  | PFC056 - Site Set Up and Maintenance - Health and Safety
a) The arrangements for construction plant, vehicle and pedestrian management will be communicated through… {insert information}.
(b) When further specific information needs to be communicated, additional tool box talks and notifications will be given to the relevant site personnel.
(c) The TMP site layout drawing(s) will be displayed |  |  |  | {insert location/ arrangements}
(d) Site access (cars and vans): See example below Wind farm construction is expected to occur over an 18 -month period commencing in 2020. Phase 1F felling works and a degree of initial site mobilisation and works will be undertaken using the ‘Alternative Access’ onto the A70. Traffic during construction is expected to comprise the following: • Timber Extraction HGVs (Covered in Phase 1 Felling TMP (ARCUS)); • Staff and construction personnel cars/vans; • Construction equipment and materials by HGV; and • Wind turbine components by Abnormal Load Vehicle (ALV). Wind turbine components will be delivered to King George V Dock in Glasgow and will be transported overland to the site. Other materials and equipment will originate from a variety of locations but are expected to travel to the site via the M74 corridor. Access to site for vehicles will be along public roads. We are permitted to use the A70 Access for 8 months from project commencement until the Glespin Bridge has been fully constructed and we can gain access to site from the B7078 Access route. Both routes are single track with passing places from the access points shown on the drawing below. All staff and visitors travelling to site will be warned of the single track roads and advised to slow down when using these roads. Particular care is to be taken when travelling from the B7078 access along the Glentaggart Road as the road is currently used by residents and poses the risk of pedestrians, children and pets travelling this area on foot. During construction, vehicle movements will generally be restricted to between the hours of 07:00-19:00 on Monday to Friday and 07:00-16:00 on Saturday. In exceptional circumstances it may be necessary for vehicle movements to occur outside of the above times, however the Principal Contractor will avoid this occurrence as far as reasonably possible .
(e) Site access - Compound Arrangement All site personnel will park at the main compound and will be transported up to the main work area in site vehicles must be 4x4 (see site access plan below). The compound will be set up in the area shown above. The compound will be secured using post and rail fencing, the fencing will be set back from the access track and water filled barriers will be used at the site entrance to minimise the risk of collision into the fencing and provide added visibility of segregation. Pedestrian segregation post and rail fencing will be implemented round the boundary of all cabins, providing safe access to each and segregating footways from traffic/parking. Any openings will have an additional post and rail fence at the entrance to the footpath to avoid slips/trips and falls into the parking areas. All site personnel and visitors should follow the reverse parking procedure and adequate signage will be displayed on the fencing to enforce this. When travelling in and around pedestrian areas such as the compound / borrow pit or other areas where work is being carried out by men on foot the PPIZ procedures should be followed. These procedures will be briefed to all at their site induction and displayed on site notice boards. Site traffic must also reduce their speed and proceed with extra caution when passing areas where pedestrians are on foot. Orange flashing beacons or hazard lights should be used by all site traffic. All plant should be fitted with a green beacon to inform if the seatbelt is being used. All plant operatives should be trained and competent and must wear their seatbelts at all times, checks will be carried out by site management at various points throughout the project to ensure seatbelts are being worn. A refuelling station will be cordoned off in one section of the compound to ensure that there is no other plant, vehicles or container units in the vicinity of the refuelling station. This is to avoid adding potential crush zones to the refuelling process and to keep everyone out of the refuelling area except the one trained and competent person carrying out the activity. A plant / fitters area will be constructed so that plant repairs can be undertaken in a cordoned off area on a concrete pad with a spill kit unit in the area.
(f) Access to work area All site staff and visitors will park at the site compound. From there they will be taken to the work area using site vehicles (site foreman & engineers trucks). This should minimise the use of the public road for trips to and from the work area throughout the day. All plant will be kept on site overnight in the storage area, this will reduce the use of public roads for moving plant and machinery. All re-fuelling will be undertaken in at the work area in a designated refuelling area using a towable fuel bowser, this will eliminate the need for any item of plant to need to travel to the compound from the work area. g) Access to WTG foundation pours The only vehicles permitted on the crane pad during the concrete pours will be the 2x concrete pumps, concrete delivery wagons and the concrete testing technician. All other vehicles will be transported to the crane pad and dropped off / picked up. A one way system will be implemented and coned / barriered off. A banksman will be used when reversing wagons into position onto the concrete pump. Pedestrian segregation will be implemented on the access ramp to the base and a banksman will be used when transporting materials down the ramp.
SECTION 3 TMP |  |  |  | SPEED LIMITS
a) The site speed limit for this project is |  |  |  | 15mph
(b) When within the compound, borrow pit, batching plant or any other area where pedestrians are working, vehicle speeds must be reduced and extra caution taken.
SECTION 4 TMP |  |  |  | RE-FUELLING |  |  | PFC067 - Project Plant Equipment and Labour Planning Management
a) All re-fuelling activities must be undertaken away from potential sources of ignition with all items of machinery switched off and only when items of plant have cooled down.
b) The re-fuelling of vehicles, mobile plant and large static plant must only be undertaken at designated re-fuelling points utilising fixed installation or proprietary fuel bowsers with no pedestrians within the vicinity whilst the vehicles are being positioned for re-fuelling.
c) A minimum safe working distance of 3m must be maintained from members of the general public when re-fuelling or decanting fuel.
d) All re-fuelling duties must be undertaken in association with the use of drip trays and/or plant nappies.
e) Where multiple re-fuelling locations are required on site, these must be specifically designated and segregated from normal site operations. Where this is not possible due to space restrictions, a mobile re-fuelling area must be designated utilising appropriate signage.
f) Spill kits are to be made readily available and stored in designated locations alongside re-fuelling locations. Spill kit response procedures will be in accordance with the Pollution Control Plan.
EN-f-015 - Pollution Control Plan
g) All refuelling to be carried out in in accordance with an appropriate risk assessment and method statement.
h) All tanks will be bunded by means of a double skin or placed within a bund capable of holding 110% of the maximum capacity of the tank.
(i) {insert additional information with regards to refuelling as required}
SECTION 5 TMP |  |  |  | DELIVERIES |  |  | PFC067 - Project Plant Equipment and Labour Planning Management
HS-p-040 - Delivery Drivers Site Safety Procedures
HS-p-042 - Plant & People Interface Zone
(a) All deliveries to site will be co-ordinated |  |  |  | {insert relevant delivery information}
(b) Deliveries will only be accepted between the hours of |  |  |  |  | {insert delivery permitted times}
(c) Any vehicles used for routine delivery of materials to site where permitted shall be fitted with a reversing alarm and provisions for all round vision.
(d) All reversing delivery vehicles must be under the control of a trained banksman, irrespective of alarms or visual aids fitted.
(e) All delivery vehicles must activate warning beacons and/or hazard warning lights where fitted on site/ through site gates.
(f) The prescribed delivery routes are as follows:
SECTION 6 TMP |  |  |  | INTERNAL TRAFFIC HAZARDS |  |  |  | HS-p-037 - Site Traffic and Pedestrian Management
(a) {insert site specific traffic hazards as appropriate and how these are to be managed}
SECTION 7 TMP |  |  |  | SITE PEDESTRIAN TRAFFIC |  |  |  | HS-p-037 - Site Traffic and Pedestrian Management
(a) The location of pedestrian routes are detailed |  |  |  | {insert location}
(b) Clear identifiable pedestrian walkways will be located |  |  |  |  | {insert location}
(c) The use of segregation methods including pedestrian barriers will be implemented to segregate site personnel from plant operations.
(d) Priority is to be given to members of the public accessing or passing through. This will be briefed to all site operatives during the site induction and updated as part of the programme of daily briefings.
(e) Information relating to alterations or deviations in pedestrian access routes for site personnel will be clearly signposted and briefed during the induction and updated as part of the programme of daily briefings.
SECTION 8 TMP |  |  |  | PUBLIC INTERFACE |  |  | HS-p-037 - Site Traffic and Pedestrian Management
HS-p-014 - Protecting the Public
Measures in place to protect the public from site vehicles and plant are as follows:
(a) {insert site specific measurements in place to ensure public safety}
(b) {insert site specific measurements in place to ensure public safety}
(c) {insert site specific measurements in place to ensure public safety}
(d) {insert site specific measurements in place to ensure public safety}
(e) {insert site specific measurements in place to ensure public safety}
(f) {insert site specific measurements in place to ensure public safety}
(g) {insert site specific measurements in place to ensure public safety}
SECTION 9 TMP |  |  |  | EMERGENCY ARRANGEMENTS |  |  |  |  | HS-f-023 Basic Emergency Procedures Template
HS-f-093 - Wind Farm Emergency Response Plan Template
HS-f-095 - Emergency Procedure Flow Charts
In the event of an emergency, procedures must be implemented as identified within the Construction Phase Health & Safety Plan, including:
(a) Prior to the start of construction activities, local emergency services are to be informed of the proposed works and any imposed access restrictions.
(b) In the event of an emergency the site manager must be informed as soon as reasonably practical.
(c) If required the appropriate emergency services are to be contacted and provided with all necessary information required to attend site.
(d) In the event of emergency first aid measures required, they are to be implemented under the control of a competent first aider.
(e) Upon arrival to site of the emergency services they will be directed to the scene of an incident by the appointed site representative.
(f) {insert additional emergency arrangements are required}
SECTION 10 TMP |  |  |  | HIGHWAYS TEMPORARY TRAFFIC MANAGEMENT
{insert information as applicable}
SECTION 11 TMP |  |  |  | RECORD REFERENCING MATRIX
Explanatory Notes:-
To support the effective management of projects and remove the potential for duplication of information and effort, all records referred to in this plan are filed in the Jones Bros Project Filing Structure whilst the records are continuing to be updated and the project is live. The following matrix supports the navigation and archiving of project records. It enables project teams and third parties (as applicable) to easily navigate the Project Filing Structure.
Traffic Management Plan Section Reference |  | Record Description |  |  |  | BMS Format |  | Project Filing Location
1.1 |  | Project Appointment Matrix |  |  |  | PROJECT ROLES & RESPONSIBILITES |  | 07 Project Administration\07.07 Health and Safety\07.07.02 Construction Phase Health and Safety Plan
SECTION 12 TMP |  |  |  | FURTHER GUIDANCE
Further guidance on Traffic Management matters is available from: |  |  |  |  | the HSE Team on 01824 703661 or E-mail hseqt@jones-bros.com
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content
Back to Content

## Quality Test & Inspection Plan (hidden)
Setting Up a Project Inspection Plan [PIP]: (Template).
Reference |  |  | QMP000 | [21 empty] | 2019-05-01
PROJECT NAME: | [8 empty] | PROJECT REFERENCE:
PREPARED BY: | [8 empty] | DATE:
Does your Project need to include any of the following activities? | Preliminaries Custom Form Category 008 |  | Site Clearance Custom Form Category 009 |  | Fencing Custom Form Category 010 |  | Vehicle Restraint Systems Custom Form Category 011 |  | Drainage (Pipework, Chambers & Gullies) Custom Form Category 012 |  | Drainage ( Land Drains, Fin Drains, Narrow Filter Drains & Combi Drains) Custom Form Category 012 |  | Drainage (Cleaning of Drainage Systems) Custom Form Category 012 |  | Earthworks (Cuttings) Custom Form Category 013 |  | Earthworks (Filling) Custom Form Category 013 |  | Earthworks (Stabilisation) Custom Form Category 013 |  | Road Pavements; General Custom Form Category 014 |  | Road Pavements: Unbound, Custom Form Category 015 |  | Road Pavements: Cement & other Hydraulically Bound Custom Form Category 016 |  | Road Pavements; Bituminous Material Custom Form Category 017 |  | Pavements; Concrete Material Custom Form Category 018 |  | Kerbs Custom Form Category 019 |  | Footways and Paved Areas Custom Form Category 019 |  | Traffic Signs; Signs, Foundations, Road Bollards & Marker Posts, Markings & Studs, Delineators Custom Form Category 020 |  | Traffic Signs; Danger Lamps, Beacons, Temporary Signs, Signals, Detector Loops, Crossings Custom Form Category 020 |  | Street Lighting Columns, Brackets, CCTV Masts, Custom Form Category 021 |  | Electrical Work for Road lighting and Traffic Signs, Custom Form Category 022 |  | Piling, Custom Form Category 023 |  | Embedded Retaining Walls, Custom Form Category 023 |  | Piling and Embedded Retaining Walls, Testing & Support Fluids Custom Form Category 023 |  | Structural Concrete Insitu Concrete Placement Custom Form Category 024 |  | Structural Steelwork Custom Form Category 025 |  | Protection of Structural Steelwork Against Corrosion Custom Form Category 026 |  | Waterproofing of Concrete Structures Custom Form Category 027 |  | Bridge Expansion Joints & Sealing of Gaps Custom Form Category 028 |  | Brickwork, Blockwork & Masonry Custom Form Category 029 |  | Special Structures Custom Form Category 030 |  | Miscellaneous Mortar Beds, Ancillary Concrete, No Fines Concrete & Granolithic Concrete Custom Form Category 031 |  | Miscellaneous Plastic Coatings to Fence & Gatework, Thermoplastic Node Markers Custom Form Category 031 |  | Landscape & Ecology Weed Control, Rabbit & Deer Control Custom Form Category 032 |  | Landscape & Ecology Ground Preparation, Grass Seeding & Planting Custom Form Category 032 |  | Landscape & Ecology Maintenance & Watering Custom Form Category 032 |  | Landscape & Ecology Management of Water Bodies & Special Measures Custom Form Category 032
| Yes: Include QMP100 | No: No Further Action | Yes: Include QMP200 | No: No Further Action | Yes: Include QMP300 | No: No Further Action | Yes: Include QMP400 | No: No Further Action | Yes: Include QMP500 | No: No Further Action | Yes: Include QMP501 | No: No Further Action | Yes: Include QMP502 | No: No Further Action | Yes: Include QMP600 | No: No Further Action | Yes: Include QMP601 | No: No Further Action | Yes: Include QMP602 | No: No Further Action | Yes: Include QMP700 | No: No Further Action | Yes: Include QMP800 | No: No Further Action | Yes: Include QMP801 | No: No Further Action | Yes: Include QMP900 | No: No Further Action | Yes: Include QMP1000 | No: No Further Action | Yes: Include QMP1100 | No: No Further Action | Yes: Include QMP1101 | No: No Further Action | Yes: Include QMP1200 | No: No Further Action | Yes: Include QMP1201 | No: No Further Action | Yes: Include QMP1300 | No: No Further Action | Yes: Include QMP1400 | No: No Further Action | Yes: Include QMP1600 | No: No Further Action | Yes: Include QMP1601 | No: No Further Action | Yes: Include QMP1602 | No: No Further Action | Yes: Include QMP1700 | No: No Further Action | Yes: Include QMP1800 | No: No Further Action | Yes: Include QMP1900 | No: No Further Action | Yes: Include QMP2000 | No: No Further Action | Yes: Include QMP2300 | No: No Further Action | Yes: Include QMP2400 | No: No Further Action | Yes: Include QMP2500 | No: No Further Action | Yes: Include QMP2600 | No: No Further Action | Yes: Include QMP2600 | No: No Further Action | Yes: Include QMP3000 | No: No Further Action | Yes: Include QMP3001 | No: No Further Action | Yes: Include QMP3002 | No: No Further Action | Yes: Include QMP3003 | No: No Further Action
Quality Management Plan Link
Insert Specification Link
Review Quality Management Plan & Select Checklists Required for your Project; Checklists are all available on mobile devices. | QA-a-101 |  | QA-a-201 |  | QA-a-301 |  | QA-a-401 |  | QA-a-501 |  | QA-a-513 |  | QA-a-523 |  | QA-a-601 |  | QA-a-601 |  | QA-a-609 |  | QA-a-701 |  | QA-a-801 |  | QA-a-811 |  | QA-a-901 |  | QA-a-1001 |  | QA-a-1101 |  | QA-a-1107 |  | QA-a-1201 |  | QA-a-1213 |  | QA-a-1301 |  | QA-a-1401 |  | QA-a-1601 |  | QA-a-1611 |  | QA-a-1621 |  | QA-a-1701 |  | QA-a-1801 |  | QA-a-1901 |  | QA-a-2001 |  | QA-a-2301 |  | QA-a-2401 |  | QA-a-2501 |  | QA-a-2601 |  | QA-a-2604 |  | QA-a-3001 |  | QA-a-3007 |  | QA-a-3020 |  | QA-a-3030
| QA-a-102 |  | QA-a-202 |  | QA-a-302 |  | QA-a-402 |  | QA-a-502 |  | QA-a-514 |  | QA-a-524 |  | QA-a-603 |  | QA-a-602 |  | QA-a-610 |  | QA-a-702 |  | QA-a-802 |  | QA-a-812 |  | QA-a-902 |  | QA-a-1002 |  | QA-a-1102 |  | QA-a-1108 |  | QA-a-1202 |  | QA-a-1214 |  | QA-a-1302 |  | QA-a-1402 |  | QA-a-1602 |  | QA-a-1612 |  | QA-a-1622 |  | QA-a-1702 |  | QA-a-1802 |  | QA-a-1902 |  | QA-a-2002 |  | QA-a-2302 |  | QA-a-2402 |  | QA-a-2502 |  | QA-a-2602 |  | QA-a-2605 |  | QA-a-3002 |  | QA-a-3008 |  | QA-a-3021 |  | QA-a-3031
| QA-a-103 |  | QA-a-203 |  | QA-a-303 |  | QA-a-403 |  | QA-a-503 |  | QA-a-515 |  | QA-a-525 |  | QA-a-604 |  | QA-a-605 |  | QA-a-620 |  | QA-a-703 |  | QA-a-803 |  | QA-a-813 |  | QA-a-903 |  | QA-a-1003 |  | QA-a-1103 |  | QA-a-1109 |  | QA-a-1203 |  | QA-a-1215 |  | QA-a-1303 |  | QA-a-1403 |  | QA-a-1603 |  | QA-a-1613 |  | QA-a-1623 |  | QA-a-1703 |  | QA-a-1803 |  | QA-a-1903 |  | QA-a-2003 |  | QA-a-2303 |  | QA-a-2403 |  | QA-a-2503 |  | QA-a-2603 |  | QA-a-2606 |  | QA-a-3003 |  | QA-a-3009 |  | QA-a-3022 |  | QA-a-3032
| QA-a-104 |  | QA-a-204 |  | QA-a-304 |  | QA-a-404 |  | QA-a-504 |  | QA-a-516 |  | QA-a-526 |  | QA-a-607 |  | QA-a-606 |  | QA-a-621 |  | QA-a-704 |  | QA-a-804 |  | QA-a-814 |  | QA-a-904 |  | QA-a-1004 |  | QA-a-1104 |  | QA-a-1110 |  | QA-a-1204 |  | QA-a-1216 |  | QA-a-1304 |  | QA-a-1404 |  | QA-a-1604 |  | QA-a-1614 |  | QA-a-1624 |  | QA-a-1704 |  | QA-a-1804 |  | QA-a-1904 |  | QA-a-2004 |  | QA-a-2304 |  | QA-a-2404 |  | QA-a-2504 |  | QA-a-2607 |  | QA-a-2611 |  | QA-a-3004 |  | QA-a-3010 |  | QA-a-3023 |  | QA-a-3033
| QA-a-105 |  | QA-a-205 |  |  |  | QA-a-405 |  | QA-a-505 |  | QA-a-517 |  | QA-a-527 |  | QA-a-611 |  | QA-a-607 |  |  |  | QA-a-705 |  | QA-a-805 |  |  |  | QA-a-905 |  | QA-a-1005 |  | QA-a-1105 |  | QA-a-1111 |  | QA-a-1205 |  | QA-a-1217 |  | QA-a-1305 |  | QA-a-1405 |  | QA-a-1605 |  | QA-a-1615 |  | QA-a-1625 |  | QA-a-1705 |  | QA-a-1805 |  | QA-a-1905 |  | QA-a-2005 |  | QA-a-2305 |  | QA-a-2405 |  | QA-a-2505 |  | QA-a-2608 |  | QA-a-2612 |  | QA-a-3005 |  | QA-a-3011 |  | QA-a-3024
| QA-a-106 |  | QA-a-206 |  |  |  | QA-a-406 |  | QA-a-506 |  | QA-a-518 |  | QA-a-528 |  | QA-a-612 |  | QA-a-608 |  |  |  | QA-a-706 |  | QA-a-806 |  |  |  | QA-a-906 |  | QA-a-1006 |  | QA-a-1106 |  | QA-a-1112 |  | QA-a-1206 |  | QA-a-1218 |  | QA-a-1306 |  | QA-a-1406 |  | QA-a-1606 |  | QA-a-1616 |  | QA-a-1626 |  | QA-a-1706 |  | QA-a-1806 |  | QA-a-1906 |  | QA-a-2006 |  | QA-a-2306 |  | QA-a-2406 |  | QA-a-2506 |  | QA-a-2609 |  | QA-a-2613 |  | QA-a-3006 |  | QA-a-3012 |  | QA-a-3025
| QA-a-107 |  | QA-a-207 |  |  |  | QA-a-407 |  | QA-a-507 |  | QA-a-519 |  | QA-a-529 |  | QA-a-614 |  | QA-a-611 |  |  |  | QA-a-707 |  | QA-a-807 |  |  |  | QA-a-907 |  | QA-a-1007 |  |  |  | QA-a-1113 |  | QA-a-1207 |  | QA-a-1219 |  | QA-a-1307 |  | QA-a-1407 |  | QA-a-1607 |  | QA-a-1617 |  | QA-a-1627 |  | QA-a-1707 |  |  |  | QA-a-1907 | [5 empty] | QA-a-2407 |  | QA-a-2507 |  | QA-a-2610 | [5 empty] | QA-a-3013 |  | QA-a-3026
| QA-a-108 |  | QA-a-208 |  |  |  | QA-a-408 |  | QA-a-508 |  | QA-a-520 |  | QA-a-530 |  | QA-a-615 |  | QA-a-612 |  |  |  | QA-a-708 |  | QA-a-808 |  |  |  | QA-a-908 |  | QA-a-1008 |  |  |  | QA-a-1114 |  | QA-a-1208 |  | QA-a-1220 |  | QA-a-1308 |  | QA-a-1408 |  | QA-a-1608 |  | QA-a-1618 |  | QA-a-1628 |  | QA-a-1708 |  |  |  | QA-a-1908 | [5 empty] | QA-a-2408 |  | QA-a-2508 |  | QA-a-2614 | [5 empty] | QA-a-3014 |  | QA-a-3027
| QA-a-109 |  | QA-a-209 |  |  |  | QA-a-409 |  | QA-a-509 |  | QA-a-521 |  |  |  | QA-a-618 |  | QA-a-613 | [5 empty] | QA-a-809 |  |  |  | QA-a-909 |  | QA-a-1009 |  |  |  | QA-a-1115 |  | QA-a-1209 |  | QA-a-1221 |  |  |  | QA-a-1409 |  | QA-a-1609 |  | QA-a-1619 |  | QA-a-1629 |  | QA-a-1709 |  |  |  | QA-a-1909 | [5 empty] | QA-a-2409 |  | QA-a-2509 | [7 empty] | QA-a-3015 |  | QA-a-3028
| QA-a-110 |  | QA-a-210 |  |  |  | QA-a-410 |  | QA-a-510 |  | QA-a-522 |  |  |  | QA-a-619 |  | QA-a-614 | [5 empty] | QA-a-810 |  |  |  | QA-a-910 |  | QA-a-1010 |  |  |  | QA-a-1116 |  | QA-a-1210 |  | QA-a-1222 |  |  |  | QA-a-1410 |  | QA-a-1610 |  | QA-a-1620 |  | QA-a-1630 |  | QA-a-1710 |  |  |  | QA-a-1910 | [5 empty] | QA-a-2410 |  | QA-a-2510 | [7 empty] | QA-a-3016 |  | QA-a-3029
| QA-a-111 | [7 empty] | QA-a-511 | [7 empty] | QA-a-616 | [9 empty] | QA-a-911 | [5 empty] | QA-a-1117 |  | QA-a-1211 |  | QA-a-1223 |  |  |  | QA-a-1411 | [5 empty] | QA-a-1631 | [13 empty] | QA-a-2511 | [7 empty] | QA-a-3017
| QA-a-112 | [7 empty] | QA-a-512 | [7 empty] | QA-a-617 | [9 empty] | QA-a-912 | [5 empty] | QA-a-1118 |  | QA-a-1212 |  | QA-a-1224 |  |  |  | QA-a-1412 | [5 empty] | QA-a-1632 | [13 empty] | QA-a-2512 | [7 empty] | QA-a-3018
[17 empty] | QA-a-618 | [9 empty] | QA-a-913 | [13 empty] | QA-a-1413 | [27 empty] | QA-a-3019
[17 empty] | QA-a-619 | [9 empty] | QA-a-914 | [13 empty] | QA-a-1414
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=175978&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176038&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176043&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176045&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176054&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176062&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176065&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176072&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176093&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176164&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176222&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176227&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=177609&Latest=true
https://uni
onsquare.jones-bros.com:444/DMS/view_document.aspx?ID=177454&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176515&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=176516&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=179472&Latest=true
https
://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=180293&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=182051&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=186330&Latest=true
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=190580&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=190979&Latest=true
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=194615&Latest=true
S
S
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=196945&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=196945&Latest=true
S
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=201112&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=201159&Latest=true
S
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=204695&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=204709&Latest=true
S
S
S
S
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=209218&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=209402&Latest=true
S
S
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=210747&Latest=true
S
S
S
S
S
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=213047&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=214340&Latest=true
https://unionsquare.jones-bros.com:444/DMS/view_document.aspx?ID=214353&Latest=true
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S
S

## PROJECT ROLES & RESPONSIBILITES
PROJECT ROLES & RESPONSIBILITES
Project Name: | A494 River Dee Bridge Deck over-slabbing Contingency Scheme
Project Number: | 21-NM-CHR-003
Project Details
Project Description: |  | The North and Mid Wales Trunk Road Agent (NMWTRA) have commissioned a project to develop a major maintenance intervention should a critical defect be identified within the A494 River Dee Bridge structure and enable this to be implemented with minimal impact on traffic conditions. The proposed design intervention comprises of removing a depth of existing road surfacing and replacing with a new thin reinforced concrete over-slab with combined waterproof and wearing membrane (hence forth referred to as the ‘over-slabbing works’). Enabling works are required to parts of the central reserve and to the Riverside Way Junction to facilitate contraflow traffic management arrangements during construction. The enabling works consist of construction 2Nr crossovers through the central reserve west of the existing bridge and works to widen the Riverside Way Junction.
Project Location: |  | Enter your project location here
Plan Approvals
Written by: | Name: | 0 |  |  | Signature: | 0 | Date: | 0
Approved by: | Name: | 0 |  |  | Signature: | 0 | Date: | 0
Explanatory Notes:-
Origination: Tender phase origination resides with the Project Manager. Construction Phase update will be the responsibility of the Site Manager.
Approval: Tender phase approval resides with the Contracts Manager or Regional Director. Construction Phase approval will be the responsibility of the Project Manager.
(Revision: The plan will be revised to reflect changes that have been made to the product, project or contract, work practices, service provision or Quality Assurance procedures. Where changes are made to the plan an assessment of the impacts of the changes will be carried out and recorded in the Version Control section below.
Version Control
Description of changes |  |  | Date | Revision | Page No. | Comments
Explanatory Notes:-
This Project Management Plan will be added to, reviewed and updated as the project develops, further design work is completed, information from subcontractors starting work becomes available, unforeseen circumstances or variations to planned circumstances arise or where the operations management team deem it is necessary.
If sections are deemed not applicable DO NOT DELETE. Replace text with not applicable on this project.
1.1) Project Organisation and Resource
(a) Agreed responsibilities and Specific duties for key roles are outlined in the Jones Bros Business Management system under 03 -Knowledge area - 03.21 - HR - 03.21.01 Job Role Descriptions. Responsibilities are also identified in associated Process Flow Charts (PFC) held in the Jones Bros BMS 03 - Knowledge area - 03.03 Process Flow Charts and, where appropriate, referenced throughout this plan.
(b) Communication and display of appointments: |  |  | A copy of the appointments is to be displayed on the project’s health and safety notice board and in the project filing structure located in the site reception.
(c) All appointments on the matrix are to be signed for by each individual as acceptance and understanding of the issued roles and responsibilities for the project.
(d) Appointments will be reviewed and updated throughout the project, reflecting any changes or movement in the project as required.
Role | Name |  |  | Company |  | Address | E-mail | Telephone
Client | {insert name} |  |  | The North and Mid Wales Trunk Road Agent (NMWTRA) |  | Insert Address | {insert email} | {insert tel no.}
Client Contract Admin | {insert name} |  |  | {insert company} |  | {insert address} | {insert email} | {insert tel no.}
Principal Contractor | Jones Bros |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Workforce Planning Manager | Alan Manuel |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | alan.manuel@jones-bros.com | 07384834594
IT Infrastructure Section Manager | Gerallt Ellis |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | gerallt@jones-bros.com | 07584 705103
IT Systems Section Manager | Colin Jones |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | colin.jones@jones-bros.com
Jones Bros Internal Auditor | Ellis Ashton |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | ellisa@jones-bros.com | 07384 835329
Principal Designer | (Insert name) |  |  | Insert Company Name |  | Insert Address | {insert email} | {insert tel no.}
Designer | (Insert name) |  |  | Insert Company Name |  | Insert Address | {insert email} | {insert tel no.}
Architect | {insert name} |  |  | {insert company} |  | {insert address} | {insert email} | {insert tel no.}
Structural Engineer | {insert name} |  |  | {insert company} |  | {insert address} | {insert email} | {insert tel no.}
Mechanical Consultant | {insert name} |  |  | {insert company} |  | {insert address} | {insert email} | {insert tel no.}
Electrical Consultant | (Insert name) |  |  | Insert Company Name |  | Insert Address | {insert email} | {insert tel no.}
Contract Director | Hefin Lloyd-Davies |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | hefin@jones-bros.com | 07887 722560
Contracts Manager | Daniel Robat Williams |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | robat@jones-bros.com | 07787 100752
Project Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Site Agent | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Senior Works Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Works Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Foreman 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Foreman 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Foreman 3 | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Site Engineer 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Site Engineer 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Site Engineer 3 | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Commercial Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Quantity Surveyor | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Senior Health & Safety Manager | Michael Jolley |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | michaeljo@jones-bros.com | 07795 648184
Environment Manager | Sam Higgitt |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | samh@jones-bros.com | 07766 747133
Design Manager | Dylan Parry |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | dylan.parry@jones-bros.com | 07918 797076
Designated Individual | {insert name} |  |  | 0 |  | {insert address} | {insert email} | {insert tel no.}
PC Temporary Work Co-Ordinator | {insert name} |  |  | 0 |  | {insert address} | {insert email} | {insert tel no.}
Temporary Works Co-ordinator | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Temporary Works Supervisor | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | {insert address} | {insert email} | {insert tel no.}
Temporary Works Designer | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Temporary Works Design Checker | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Quality & Business Improvement Manager | Jonathan Dennehy |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | Jonathan.Dennehy@jones-bros.com | 07443265165
Quality Controller (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Document Controller (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Material Buyer | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Plant Administrator (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
CSR Co-ordinator | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
CSR Administrator (Site Based) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Commissioning Manager | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Commissioning Engineer | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Aftercare Supervisor | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Fire Officer | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
First Aider 1 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
First Aider 2 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
First Aider 3 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
First Aider 4 | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Traffic Management Coordinator | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Traffic Management Supervisor | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Daily/Weekly HSE Checks | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
| Daily Delete or add as required (Mandatory must be completed) HS-a-043 - Excavations: Daily Check (Mandatory) HS-a-018 - H&S - Work Stopped for Day: Check (Mandatory) EN-a-001 - Environment Inspection: Daily Check (Mandatory) EN-a-002 - Environment Daily Generator Fuel Recording (Mandatory) |  |  |  |  | Weekly Delete or add as required (Mandatory must be completed) HS-a-002 - Safe Place of Work: Weekly Check (Mandatory)
Available When Required Checks HS-a-023 - Ladder Inspection Record HS-a-029 - Hand-Arm and Whole-Body Vibration Assessment and Monitoring HS-a-033 - Temporary Works Foundation Check HS-a-034 - Falsework Structure Check HS-a-035 - Falsework Timber HS-a-036 - Work Equipment Inspection Report HS-a-050 - HS - Point of Works Risk Assessment HS-a-062 - Mobile Scaffold - Daily Inspection HS-a-045 - Fall Arrest Equipment Pre-use Checks HS-a-048 - HSE Noise Monitoring Record HS-a-015 - Scaffolds: Weekly Check HS-a-019 - Roof Work: Weekly Check HS-a-008 - Noise Weekly Checklist EN-a-003 - Environment - Daily - Watercourse Monitoring Record (Site Specific) EN-a-004 - Environment - Daily Air Quality Monitoring Record (Site Specific) QC-a-001 - Quality Control - Instrument Check QC-a-002 - Quality Control - Machine Control Check
Daily/Weekly HSE Checks | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
| Daily Delete or add as required (Mandatory must be completed) HS-a-043 - Excavations: Daily Check (Mandatory) HS-a-018 - H&S - Work Stopped for Day: Check (Mandatory) EN-a-001 - Environment Inspection: Daily Check (Mandatory) EN-a-002 - Environment Daily Generator Fuel Recording (Mandatory) |  |  |  |  | Weekly Delete or add as required (Mandatory must be completed) HS-a-002 - Safe Place of Work: Weekly Check (Mandatory)
Available When Required Checks HS-a-023 - Ladder Inspection Record HS-a-029 - Hand-Arm and Whole-Body Vibration Assessment and Monitoring HS-a-033 - Temporary Works Foundation Check HS-a-034 - Falsework Structure Check HS-a-035 - Falsework Timber HS-a-036 - Work Equipment Inspection Report HS-a-050 - HS - Point of Works Risk Assessment HS-a-062 - Mobile Scaffold - Daily Inspection HS-a-045 - Fall Arrest Equipment Pre-use Checks HS-a-048 - HSE Noise Monitoring Record HS-a-015 - Scaffolds: Weekly Check HS-a-019 - Roof Work: Weekly Check HS-a-008 - Noise Weekly Checklist EN-a-003 - Environment - Daily - Watercourse Monitoring Record (Site Specific) EN-a-004 - Environment - Daily Air Quality Monitoring Record (Site Specific) QC-a-001 - Quality Control - Instrument Check QC-a-002 - Quality Control - Machine Control Check
Daily/Weekly HSE Checks | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
| Daily Delete or add as required (Mandatory must be completed) HS-a-043 - Excavations: Daily Check (Mandatory) HS-a-018 - H&S - Work Stopped for Day: Check (Mandatory) EN-a-001 - Environment Inspection: Daily Check (Mandatory) EN-a-002 - Environment Daily Generator Fuel Recording (Mandatory) |  |  |  |  | Weekly Delete or add as required (Mandatory must be completed) HS-a-002 - Safe Place of Work: Weekly Check (Mandatory)
Available When Required Checks HS-a-023 - Ladder Inspection Record HS-a-029 - Hand-Arm and Whole-Body Vibration Assessment and Monitoring HS-a-033 - Temporary Works Foundation Check HS-a-034 - Falsework Structure Check HS-a-035 - Falsework Timber HS-a-036 - Work Equipment Inspection Report HS-a-050 - HS - Point of Works Risk Assessment HS-a-062 - Mobile Scaffold - Daily Inspection HS-a-045 - Fall Arrest Equipment Pre-use Checks HS-a-048 - HSE Noise Monitoring Record HS-a-015 - Scaffolds: Weekly Check HS-a-019 - Roof Work: Weekly Check HS-a-008 - Noise Weekly Checklist EN-a-003 - Environment - Daily - Watercourse Monitoring Record (Site Specific) EN-a-004 - Environment - Daily Air Quality Monitoring Record (Site Specific) QC-a-001 - Quality Control - Instrument Check QC-a-002 - Quality Control - Machine Control Check
Project Energy Management Champion (Only if project is valued at over £1 million and/or over 20 weeks in duration) | (Insert name) |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd Ty Glyn, Canol Y Dre, Ruthin, Denbighshire LL15 1QW | {insert email} | {insert tel no.}
Other | {insert name} |  |  | Jones Bros. Ruthin (Civil Engineering) Co. Ltd |  | {insert address} | {insert email} | {insert tel no.}
Responsibilities
Contracts Manager | The Contracts manager responsible for: ·Ensuring that those persons, to whom functions are delegated, have the capacity to carry them out. ·To take charge of the drafting and updating of the Construction Phase Plan and all supporting documents. ·Ensuring that the assessment of risks is integrated within the day-to-day functions of Jones Bros (JB). ·Pre-plan contracts in order to establish appropriate working methods, material purchases and sequence of operation to minimise any potential hazard or pollution. ·Participate in the detailed review of accident and incident investigation and implement appropriate action to prevent recurrence. ·Co-ordinate the health, safety and environmental monitoring and act upon the information and reports arising from it. ·Collate information from the Health, Safety & environmental meetings and refer to the Managing Director any matters that require that level of authority. ·Take appropriate disciplinary action under established disciplinary procedures with regard to any employee not complying with their duties and responsibilities and safe working practices as laid down in policy and procedures. ·To implement systems to ensure that all activities operate in accordance with statutory regulations and with the safety policy including the production of relevant risk assessments and method statements and refrain from condoning any activity which is in breach of those requirements. ·Appoint only competent contractors who have made adequate allowances for matters of safety, health and environmental provisions. ·Ensure that any measurements and review of contractor performance takes account of their compliance with appropriate Safety, health and environmental provisions. ·To ensure those facilities are established to assess all risks faced by or created by employees and to determine and record a strategy to overcome those risks. ·Ensure that on all projects to which CDM applies, that procedures are adopted to only allow projects to start after a suitable Construction Phase Plan has been produced.
Site Agent / Engineer | The site agent / engineer is responsible for: ·To ensure that all activities operate in accordance with statutory requirements and with the Health and Safety Policy and the Health and Safety procedures. ·To ensure that all subordinate staff have sufficient safety training to enable them to conduct their work without undue risks to their own or other people’s safety and health. ·To ensure that all subordinate staff have sufficient environmental training / information to enable them to conduct their work without undue pollution to the environment ·To assist the contracts manager in updating of the Construction phase plan. ·To secure from each sub-contractor a method statement and risk assessments providing details of the way in which any hazardous aspects of the work is to be executed. ·To ensure that access routes are planned. Deliveries are programmed to ensure the company requirements with regard to storage, clearing up, tidiness etc. ··· Ensure that storage areas are prepared and that materials are ordered in quantities which will not create difficulties. ·To seek advice on any matters of safety and health upon which there is uncertainty.
Site Manager | The site Manager is responsible for: ·To ensure that all subordinate staff have sufficient safety training to enable them to conduct their work without undue risks to their own or other people’s safety and health and have sufficient environmental training / information to enable them to conduct their work without undue pollution to the environment ·To assist the construction manager in updating of the Construction phase plan. ·To ensure that all personnel, whether operatives, sub-contractors or legitimate visitors are inducted onto the site they visit and made aware of the specific risks associated with the site. ·To ensure that all risks faced by JB personnel, sub-contractors and others have been adequately assessed, that the necessary precautions have been established and that they are being implemented. ·Ensure and maintain in good order, adequate protective clothing, hard hats, reflective waistcoats, safety boots etc. for all employees PPE MUST BE WORN ON ALL SITES. If the job requires, additional PPE is supplied and used. ·To ensure adequate and suitable welfare facilities are available and are maintained in a good order. ·Encourage site tidiness and high standards of housekeeping to reduce the risk of accidents and wastage of materials. ·Ensure any statutory notices are displayed ·To ensure all accidents whether or not they give rise to injury, pollution or property damage is reported in accordance with the established procedures. ·To ensure that all operations are inspected on a regular basis and to act on all proper reports submitted either orally or in writing.
Employees & Subcontractors | All Employees and sub contractors are responsible for: ·To know the detail of the policy and where appropriate the health and Safety plan which will affect them. ·To work in accordance with the policy, the method statements, and where appropriate, the health and safety plan. ·To attend all briefings in respect of matters of safety health and environment and act upon the information given. ·To report to the appropriate line manager if there is any reason that instructions on safety and health cannot be followed. ·To report all accidents whether or not they result in injury, pollution or property damage and to complete the accident/incident report form. ·To report to line management any matter which is considered a risk to the safety and health of anyone who may be affected by the site activity. ·Make full and proper use of any safety equipment, machinery guards, and to operate all equipment in accordance with instructions. ·To refrain from interfering with anything provided for their safety and health. ·To use any issued equipment and to refrain from improvising ·To refrain from indulging in horseplay ·To report immediately any defect in any equipment ·To set a personal example.

## Validation (hidden)
Please Specify: | Please Specify:
Daily | Required
Weekly | Not Required
Forthnightly
Monthly
Quarterly
Annually