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1. SummaryThe planned works include a light washing and full repainting of the Usk River Footbridge structure and concrete abutments using pressurised clean water. Then applying paint by roller or brush to the existing painted areas. Paint will not enter the watercourse.

The works will require a MEWP (Mobile Elevating Working Platform) and specialist rope access to the masts which span over the Usk River (Outside the line of the bridge deck) and to the outer sides of the bridge deck. 

But does not include painting of the bank seats or abutments. 

Painting is confined to the masts of the bridge and the outriggers / cable supports at bridge deck level.






2. Scope of works
Sequence of works: 

1) Establishment of secure site compound on the west bank of the river adjacent to the bridge. The compound is to extent to the riverbank and encompasses the access to the bridge. 

2) Close of the east end of the bridge to public access. The closure will remain in force during times when works are being undertaken on or over the bridge deck. The bridge will be reopened outside of working hours when the bridge is clear of any equipment which may provide a hazard to bridge users. Working hours are expected to be 09:30 until 3pm Monday to Friday but may vary slightly in order to complete a specific task.

3) Prior to any works being carried out safety arrangements for retrieval of personnel from the masts or below deck level will be put in place. 

4) Access to the masts extending over the river and bridge deck will be accessed via the stay cables extending from the bridge deck. Ropes will be installed from the cables between the mast heads to allow access down to the mast to allow cleaning. Access to the outriggers and sides of the deck will be provided by the use of rope access from the deck of the bridge. 

5) Light cleaning will be carried out using pressurised water provided by jet wash' apparatus. The water is to be provided by a standpipe connected to the mains water supply inside the compound.

6) Paint will be applied by roller or brush, all tools and cans to be tethered to prevent spillage or dropping.

7) On completion of the cleaning / painting, all apparatus installed on the bridge will be removed. The compound will be dismantled and any damage/wear to the highway street furniture or finishes be made good. Estimated works duration and working times:- The estimated time period for the works will between 12 and 14 weeks. Working times will vary each day, depending on the progress made, but it is expected that the bridge will be reopened each evening after and each morning before work takes place requiring closure of the bridge. 
There will be a contingency in place for extending the contract time period or the working hours in order to ensure the works are completed within the required timescale. Plant, machinery required.- 
If any plant is required it will remain on riverbank or bridge deck. All vehicles and heavy equipment will remain within the compound. Generators powering the water pressuriser units will remain inside the compound and the units themselves limited to the compound and bridge deck. Extension to the masts and outside the deck will be provided using flexible hoses. The quantity of deposits removed from the bridge during the cleaning process is considered negligible. Any accidental paint spillage will be notified and actioned accordingly.

3. Access and working areas· The attached drawing (NCC 3759-001 Site Location Plan) shows the location of the bridge and area of the proposed secure compound. 

· The vehicle movements are likely to be:-

· 1) Delivery of equipment for site setup throughout the first 3-5 days of the project.


·  2) Daily arrival and departure from site of site personnel. 

· 3) Deployment of equipment required for cleaning at the start of each working period and removal of equipment from bridge deck to allow for reopening of bridge during nonworking hours. 


· Delivery of paint and Hand tools

· Paint will not be stored on site unless in fully secured antivandal containers.


· All equipment is to be stored at the end of each working period in a secure container within the compound or removed from site. 

· Any equipment not inside the container will be isolated and made secure. There are no expected risks to navigation during the contract period. 


· For any unforeseen incidents which may affect navigation will be reported to the appropriate authorities (See Section 5).

4. Environmental mitigation
Measure to minimise impacts on the marine environment:- 

1) Both NCC and all contractors are aware that the bridge sits within the River Usk/ Afon Wysg SAC and above a protected habitat. 
Sightings of any creatures or plant life will be reported immediately to the NCC ecologist Matthew Harris for direction as to the way forward. Work will cease until specific direction is given.
2)The impact of pollution will be limited by the use of only mains water being used in the cleaning process. 
3) Spill response kits are to be provided to all equipment which may leak oils, fuels or other substances which have the capacity to cause pollution to the river and surrounding environment. 
4) Plant traffic close to the riverbank and on the bridge-deck will be minimised. 
5) Access and egress routes are limited by the layout of the bridge. 
6) Storage of materials (fuel, chemicals, construction waste) will be in accordance with the contractor's environmental policy and any relevant environmental legislation. By signing this method statement, we understand that we will be agreeing to adhere to the following restrictions. 

✓ All equipment, temporary structures, access tracks, waste and/or debris associated with the works will be removed on completion of the works. 
✓ Bunding, storage facilities and spill kits will be employed to contain and prevent the release of fuel, oils and chemicals associated with the plant, refuelling and construction equipment into the marine environment. 
✓ Plant, vehicles and machinery will not be refuelled on the foreshore. 
✓ Coatings/ paint and treatments will be suitable for use in the marine environment and are used in accordance with best environmental practice. 
✓ All equipment, materials, machinery and PPE used will be in a clean condition prior to their arrival on site, and upon removal from site, to minimise risk of introducing nonnative species into the marine environment. 
✓ In the event of removal of any sensitive species or habitat designated by NRW under Schedule 7 of the Environment (Wales) Act 2016, no further removals will occur at that location or within 20m of that location. 

Bespoke mitigations:- 

. No chemicals to be used in the cleaning process. No equipment or plant containing oils or fuels to be placed on the bridge deck or suspended over the mast sections over the river. 

• No washing of non-organic materials from the bridge will take place during the cleaning/ painting process.





5. Additional Information· Additional information: 

Consents/permissions required from the following:- 

1) The National Maritime Operations Centre (nmoccontrollerQhmcq.gov.uk) is to be made aware of the works prior to commencement. 
2) Agreement of the responsible local navigation authority or the Harbour Authority/Commissioners/Council. 
3) Sufficient measures are put in place to ensure the safety of personnel and objects suspended from the bridge over the waterway, and that there remains sufficient clearance below the works for vessels passing underneath. 

· Emergency procedures:- 

· Emergency procedures to be provided as part of the contractors pre-works health and safety plan prior to commencement of site works. 

· Any accidental spillage or contamination will be reported to all appropriate authorities.

· Contact details:-

·  NCC contact: John Kimberley - Senior Structural Engineer (Assets) Mob:07388625424 email.-john.kimberley@newport.gov.uk 

· Contractor office/ contacts: MAE Solutions Mobile – 07584 570538
· Landline - 02922 360364

· The attached drawing NCC 3759-001 Site Location Plan



6. Customer details

Signature:       [image: A signature on a white background  Description automatically generated]DATE 27.02.2025


Full name:  John Kimberley

Organisation name (where appropriate): Newport City Council

Contact e mail: john.kimberley@newport.gov.uk

Contact phone number: 07388625424
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