## Sheet1
ORML 1938
Summary of updates made to the Morlais site-wide Navigational Risk Assessment following receipt of comments from MCA, RYA, TH and NRW.
ID | Source | Comment | Issue 1 | Revised
1 | MCA | -That there is no precedence in the UK to control/ restrict navigation through an offshore renewable energy area. This is something we can’t support. -We would like to point out that ATBAs, PAs, No Anchoring Area etc.. are IMO Routeing Measures adopted at an international level after submitting a proposal to IMOs NCSR sub-committee and Experts Group on Ships Routeing. | -‘’Restrict Navigation through the Gold and Green MDZ Zones” and “MDZ designation as No Fishing Zone” -Table 26: Suggested Additional Mitigation Measures that the project proposes to enforce the above restriction through Area To Be Avoided (ATBA) or Precautionary Areas (PA). | Appropriate alignment and spacing of devices Restrict Navigation through the Gold and Green MDZ Zones. The MCA has statutory obligations to provide Search and Rescue services in and around OREIs in UK waters. Device layout designs must be designed to ensure clear lines of sight and navigation allow safe transit by rescue craft and those vessels that decide to transit through them including during poor visibility, high sea states and at night.[3] In order to minimise risks to surface vessels transiting through an OREI, structures (turbines, substations, etc,) should be aligned and in straight rows or columns. Multiple lines of orientation provide alternative options for passage planning and for vessels to counter the environmental effects on handling i.e. sea state, tides, currents, weather, visibility etc. Developers should plan for at least two lines of orientation unless they can clearly demonstrate that fewer is acceptable. The MCA document ‘Offshore Renewable Energy Installation: Requirements, Advice and Guidance for Search and Rescue and Emergency Response’ outlines the SAR requirements. See also 15:‘Undertake Device / Array Specific Risk Assessments’. It was noted during consultation with recreational stakeholders that 'if surface devices are spaced adequately then sailing could occur between them, although this would not be recommended at night'. For example; via designation of site as an Area To Be Avoided (ATBA) or Precautionary Area (PA). In the UK, all vessels have freedom to transit through OREIs, subject to any applied safety zones, and their own risk assessments and passage plans, which should take account of factors such as vessel size, manoeuvrability, environmental factors and competency of the Master and crew. MGN 372 (or subsequent update) provides further guidance on navigation in and around OREIs. An ATBA is an area within defined limits that should be avoided by all ships or certain classes of ship, in which navigation is particularly hazardous or in which it is exceptionally important to avoid casualties. In general, ATBAs should be established only in places where: inadequate survey or insufficient provision of aids to navigation may lead to danger of stranding; where local knowledge is considered essential for safe passage; where there is the possibility that unacceptable damage to the environment could result from a casualty; or where there may be hazards to a vital aid to navigation . PA’s are defined as areas within defined limits where ships must navigate with particular caution and within which the direction of flow of traffic may be recommended.
2 | MCA | -Continuous monitoring by marine coordination centre is considered as an additional mitigation measure. However, we note that there is no further information about this. Table 26 captures how monitoring will be done, we would like the document to capture additional details like whether the MCC will be located offshore or inshore, whether it will be manned 24/7 what alert system will be used for monitoring of devices and how break outs will be addressed. | -Continuous Monitoring by Marine Coordination Centre Appropriate ATBA | Continuous Monitoring by Marine Coordination Centre Implementation of a vessel traffic coordination system Appropriate While remote monitoring of individual devices is assumed as an embedded risk control factor (Table 23 #12), additional monitoring may be appropriate on a site wide basis, and should be determined in site specific assessments. This will allow a sitewide overview of all deployed devices and give an appropriate means for OREI operators to notify, and provide evidence of, the infringement of safety zones or ATBA.
3 | MCA | Table 22 includes SCADA and GPS monitoring as embedded risk controls however the description section is empty. We need more clarity regarding the monitoring of devices being deployed within the site, an action plan in case of breakouts including monitoring and alert systems, response times, actions etc.. | nil | Addition to the now named Table 23 : - The individual developers will have remote systems able to monitor and control function of their devices.
4 | RYA | -A key point for us both on the wider NRA and the device-specific submission is the right of navigation through OREI, which is a well-established principle in UK waters that was developed in consultation with early project developers. From a safety perspective, allowing smaller boats to pass through offshore renewables developments helps to mitigate the navigational squeeze caused by reduced sea room, and enables recreational boaters to avoid conflicts with commercial shipping. For this particular project, with the nearby rocky lee shore, this is of particular relevance. -We also remain concerned regarding the monitoring of equipment failure / breakout and ensuring timely notification to local sailing clubs and boats on passage of any resulting additional hazards, whether due to unlit installations or equipment off station. Clarity both about the technical aspects of determining if equipment is off station and the resulting proposed monitoring, response and recovery would be welcomed. |  | See above revisions
Additional changes to Issue 2 by Marico
5 | Marico |  |  | Executive summary: Summary appended to the ES summarising the revisions made, including that the changes had resulted in a rescore.
6 | Marico | Table 27: Suggested Additional Risk Control Measures |  | Check device surveys To ensure devices remain at the stated charted depth. Changes to charted depth arising from tidal turbines should be surveyed and marked on navigational charts.
7 | Marico | Table 27: Suggested Additional Risk Control Measures |  | Guard vessel to monitor passing traffic To prevent a vessel contacting a device / partially constructed device during construction / installation. To keep watch and warn vessels that may be in danger, for example, to prevent a collision as a result of third-party avoidance.
8 | Marico | Table 27: Suggested Additional Risk Control Measures |  | Establish no anchoring areas No anchoring areas to be established around nearshore cable route.
9 | Marico | Table 27: Suggested Additional Risk Control Measures | MDZ designation as No Fishing Zone To prevent fishing gear snagging on underwater devices and their associated infrastructure. | Enhanced cable protection MDZ designation as No Fishing Zone If burial is not possible, for example due to underwater features and/or seabed ground conditions export cables should be suitably protected such as by rocks or other such suitable mattress placements to mitigate the risks to the cable and vessels. The MCA would be willing to accept up to 5% reduction in surrounding charted depths referenced to Chart Datum, unless developers are able to demonstrate evidence that any identified risks to any vessel type are satisfactorily mitigated. To prevent fishing gear snagging on underwater devices and their associated infrastructure.
10 | Marico | Table 27: Suggested Additional Risk Control Measures |  | Implementation of Safety Zones Safety zones of appropriate configuration, extent and application; typically: 500m during construction, extension, maintenance or decommissioning.
11 | Marico | Table 27: Suggested Additional Risk Control Measures |  | Temporary navigation aids as required by Trinity House Temporary marking, lighting and buoyage should be utilised during construction phase in accordance with Trinity House requirements.
12 | Marico | Table 27: Suggested Additional Risk Control Measures | Undertake Device / Array Specific Risk Assessments to include NavAids and Marker Buoys. Appropriate alignment and spacing of devices | The Further site-specific assessments should be undertaken to build on previous assessments and assess the proposed locations of individual turbine devices, substations, platforms and any other structure within the tidal array. This assessment should include the potential impacts the proposed location may have on navigation and SAR activities and should be undertaken in liaison with the MCA. Additionally, this assessment should consider the tow / delivery of devices to and from the site. MCA has statutory obligations to provide Search and Rescue (SAR) services in and around OREIs in UK waters. DeviceTurbine layout designs must be designed to ensure clear lines of sight and navigation allow safe transit through OREIs by rescue craftSAR helicopters operating at low altitude in bad weather, and those vessels (including rescue craft) that decide to transit through them including during poor visibility, high sea states and at night.[3] . Developers should therefore carry out further site-specific assessment to build on previous assessments to assess the proposed locations of individual turbine devices, substations, platforms and any other structure within the wind farm or tidal/wave array. This assessment should include the potential impacts the proposed location may have on navigation and SAR activities. Risk assessments for proposed layouts should build on earlier work conducted as part of the Navigation Risk Assessment and the mitigations identified as part of that process. Where possible, this original assessment should be referenced to confirm where information or the assessment remains the same or can be further refined due to the later stages of project development