## AMP8 Tracker
Core information/Submission | [7 empty] | Duly Made |  | NRW RFI/Schedule 5 request |  |  |  |  | DCWW Response |  |  | Issuing |  | Financial - Incoming |  |  | Legal |  | Financial - Refunds |  |  |  | Financial - Total
Submission # | Driver & Batch number | Site Name | FE Permit Number | Storm Permit Number | Date Submitted | PAN # | Allocated NRW Officer | Duly Made? | Duly Made Decision Date | Further info required? | What is the Request? (limit to 100 words) | RFI Request Date | RFI Deadline | Request Status | DCWW Comment | Date of DCWW Comment | DCWW Officer | Variation Issued? | Issued Date | Variation Type | Initial fee paid | Futher Assessment fee paid | Schedule 5 sent (date) | Schedule 5 response (date) | REFUND Date | REFUND 10% fee retained | REFUND 100% fee retained | REFUND 10% fee retained (£) | Net Fee
17 | UMON 3 - Batch 2 | Llechryd SPS | N/A | BG0024901 | 2026-02-26 | PAN-031939 | Olu | Y | 2026-03-11 | N | This permit was not varied for UMON3/4 in AMP7, so we are unable to process this application for MCERTS requirements to be added to the Storm to Environment EDM Monitoring Point. We will not be able to proceed with this permit application at this time and we will have to return this application. | 2026-03-11 | 2026-03-25 | Closed | The permit number in the submission sheet should have been BP0251301 which is for the Storm and Emergency Overflow at Llechryd SPS. This permit was varied in for UMON3/4 in AMP7. All other details in the submission sheet and the site plan should be correct as they are relating to the SPS. | 2026-03-11 | Claire Grainger |  |  | Minor (Network) | 888 | 0 | [5 empty] | 0 | 888
45 | [27 empty] | 0 | 0
46 | [27 empty] | 0 | 0
47 | [27 empty] | 0 | 0
48 | [27 empty] | 0 | 0
49 | [27 empty] | 0 | 0
50 | [27 empty] | 0 | 0
51 | [27 empty] | 0 | 0
52 | [27 empty] | 0 | 0
53 | [27 empty] | 0 | 0
54 | [27 empty] | 0 | 0
55 | [27 empty] | 0 | 0
56 | [27 empty] | 0 | 0
57 | [27 empty] | 0 | 0
58 | [27 empty] | 0 | 0
59 | [27 empty] | 0 | 0
60 | [27 empty] | 0 | 0
61 | [27 empty] | 0 | 0
62 | [27 empty] | 0 | 0
63 | [27 empty] | 0 | 0
64 | [27 empty] | 0 | 0
65 | [27 empty] | 0 | 0
66 | [27 empty] | 0 | 0
67 | [27 empty] | 0 | 0
68 | [27 empty] | 0 | 0
69 | [27 empty] | 0 | 0
70 | [27 empty] | 0 | 0
71 | [27 empty] | 0 | 0
72 | [27 empty] | 0 | 0
73 | [27 empty] | 0 | 0
74 | [27 empty] | 0 | 0
75 | [27 empty] | 0 | 0
76 | [27 empty] | 0 | 0
77 | [27 empty] | 0 | 0
78 | [27 empty] | 0 | 0
79 | [27 empty] | 0 | 0
80 | [27 empty] | 0 | 0
81 | [27 empty] | 0 | 0
82 | [27 empty] | 0 | 0
83 | [27 empty] | 0 | 0
84 | [27 empty] | 0 | 0
85 | [27 empty] | 0 | 0
86 | [27 empty] | 0 | 0
87 | [27 empty] | 0 | 0
88 | [27 empty] | 0 | 0
89 | [27 empty] | 0 | 0
90 | [27 empty] | 0 | 0
91 | [27 empty] | 0 | 0
92 | [27 empty] | 0 | 0
93 | [27 empty] | 0 | 0
94 | [27 empty] | 0 | 0
95 | [27 empty] | 0 | 0
96 | [27 empty] | 0 | 0
97 | [27 empty] | 0 | 0
98 | [27 empty] | 0 | 0
99 | [27 empty] | 0 | 0
100 | [27 empty] | 0 | 0
101 | [27 empty] | 0 | 0
102 | [27 empty] | 0 | 0
103 | [27 empty] | 0 | 0
104 | [27 empty] | 0 | 0
105 | [27 empty] | 0 | 0
106 | [27 empty] | 0 | 0
107 | [27 empty] | 0 | 0
108 | [27 empty] | 0 | 0
109 | [27 empty] | 0 | 0
110 | [27 empty] | 0 | 0
111 | [27 empty] | 0 | 0
112 | [27 empty] | 0 | 0
113 | [27 empty] | 0 | 0
114 | [27 empty] | 0 | 0
115 | [27 empty] | 0 | 0
116 | [27 empty] | 0 | 0
117 | [27 empty] | 0 | 0
118 | [27 empty] | 0 | 0
119 | [27 empty] | 0 | 0
120 | [27 empty] | 0 | 0
121 | [27 empty] | 0 | 0
122 | [27 empty] | 0 | 0
123 | [27 empty] | 0 | 0
124 | [27 empty] | 0 | 0
125 | [27 empty] | 0 | 0
126 | [27 empty] | 0 | 0
127 | [27 empty] | 0 | 0
128 | [27 empty] | 0 | 0
129 | [27 empty] | 0 | 0
130 | [27 empty] | 0 | 0
131 | [27 empty] | 0 | 0
132 | [27 empty] | 0 | 0
133 | [27 empty] | 0 | 0
134 | [27 empty] | 0 | 0
135 | [27 empty] | 0 | 0
136 | [27 empty] | 0 | 0
137 | [27 empty] | 0 | 0
138 | [27 empty] | 0 | 0
139 | [27 empty] | 0 | 0
140 | [27 empty] | 0 | 0
141 | [27 empty] | 0 | 0
142 | [27 empty] | 0 | 0
143 | [27 empty] | 0 | 0
144 | [27 empty] | 0 | 0
145 | [27 empty] | 0 | 0
146 | [27 empty] | 0 | 0
147 | [27 empty] | 0 | 0
148 | [27 empty] | 0 | 0
149 | [27 empty] | 0 | 0
150 | [27 empty] | 0 | 0
151 | [27 empty] | 0 | 0
152 | [27 empty] | 0 | 0
153 | [27 empty] | 0 | 0
154 | [27 empty] | 0 | 0
155 | [27 empty] | 0 | 0
156 | [27 empty] | 0 | 0
157 | [27 empty] | 0 | 0
158 | [27 empty] | 0 | 0
159 | [27 empty] | 0 | 0
160 | [27 empty] | 0 | 0
161 | [27 empty] | 0 | 0
162 | [27 empty] | 0 | 0
163 | [27 empty] | 0 | 0
164 | [27 empty] | 0 | 0
165 | [27 empty] | 0 | 0
166 | [27 empty] | 0 | 0
167 | [27 empty] | 0 | 0
168 | [27 empty] | 0 | 0
169 | [27 empty] | 0 | 0
170 | [27 empty] | 0 | 0
171 | [27 empty] | 0 | 0
172 | [27 empty] | 0 | 0
173 | [27 empty] | 0 | 0
174 | [27 empty] | 0 | 0
175 | [27 empty] | 0 | 0
176 | [27 empty] | 0 | 0
177 | [27 empty] | 0 | 0
178 | [27 empty] | 0 | 0
179 | [27 empty] | 0 | 0
180 | [27 empty] | 0 | 0
181 | [27 empty] | 0 | 0
182 | [27 empty] | 0 | 0
183 | [27 empty] | 0 | 0
184 | [27 empty] | 0 | 0
185 | [27 empty] | 0 | 0
186 | [27 empty] | 0 | 0
187 | [27 empty] | 0 | 0
188 | [27 empty] | 0 | 0
189 | [27 empty] | 0 | 0
190 | [27 empty] | 0 | 0
191 | [27 empty] | 0 | 0
192 | [27 empty] | 0 | 0
193 | [27 empty] | 0 | 0
194 | [27 empty] | 0 | 0
195 | [27 empty] | 0 | 0
196 | [27 empty] | 0 | 0
197 | [27 empty] | 0 | 0
198 | [27 empty] | 0 | 0
199 | [27 empty] | 0 | 0
200 | [27 empty] | 0 | 0
201 | [27 empty] | 0 | 0
202 | [27 empty] | 0 | 0
203 | [27 empty] | 0 | 0
204 | [27 empty] | 0 | 0
205 | [27 empty] | 0 | 0
206 | [27 empty] | 0 | 0
207 | [27 empty] | 0 | 0
208 | [27 empty] | 0 | 0
209 | [27 empty] | 0 | 0
210 | [27 empty] | 0 | 0
211 | [27 empty] | 0 | 0
212 | [27 empty] | 0 | 0
213 | [27 empty] | 0 | 0
214 | [27 empty] | 0 | 0
215 | [27 empty] | 0 | 0
216 | [27 empty] | 0 | 0
217 | [27 empty] | 0 | 0
218 | [27 empty] | 0 | 0
219 | [27 empty] | 0 | 0
220 | [27 empty] | 0 | 0
221 | [27 empty] | 0 | 0
222 | [27 empty] | 0 | 0
223 | [27 empty] | 0 | 0
224 | [27 empty] | 0 | 0
225 | [27 empty] | 0 | 0
226 | [27 empty] | 0 | 0
227 | [27 empty] | 0 | 0
228 | [27 empty] | 0 | 0
229 | [27 empty] | 0 | 0
230 | [27 empty] | 0 | 0
231 | [27 empty] | 0 | 0
232 | [27 empty] | 0 | 0
233 | [27 empty] | 0 | 0
234 | [27 empty] | 0 | 0
235 | [27 empty] | 0 | 0
236 | [27 empty] | 0 | 0
237 | [27 empty] | 0 | 0
238 | [27 empty] | 0 | 0
239 | [27 empty] | 0 | 0
240 | [27 empty] | 0 | 0
241 | [27 empty] | 0 | 0
242 | [27 empty] | 0 | 0
243 | [27 empty] | 0 | 0
244 | [27 empty] | 0 | 0
245 | [27 empty] | 0 | 0
246 | [27 empty] | 0 | 0
247 | [27 empty] | 0 | 0
248 | [27 empty] | 0 | 0
249 | [27 empty] | 0 | 0
250 | [27 empty] | 0 | 0
251 | [27 empty] | 0 | 0
252 | [27 empty] | 0 | 0
253 | [27 empty] | 0 | 0
254 | [27 empty] | 0 | 0
255 | [27 empty] | 0 | 0
256 | [27 empty] | 0 | 0
257 | [27 empty] | 0 | 0
258 | [27 empty] | 0 | 0
259 | [27 empty] | 0 | 0
260 | [27 empty] | 0 | 0
261 | [27 empty] | 0 | 0
262 | [27 empty] | 0 | 0
263 | [27 empty] | 0 | 0
264 | [27 empty] | 0 | 0
265 | [27 empty] | 0 | 0
266 | [27 empty] | 0 | 0
267 | [27 empty] | 0 | 0
268 | [27 empty] | 0 | 0
269 | [27 empty] | 0 | 0
270 | [27 empty] | 0 | 0
271 | [27 empty] | 0 | 0
272 | [27 empty] | 0 | 0
273 | [27 empty] | 0 | 0
274 | [27 empty] | 0 | 0
275 | [27 empty] | 0 | 0
276 | [27 empty] | 0 | 0
277 | [27 empty] | 0 | 0
278 | [27 empty] | 0 | 0
279 | [27 empty] | 0 | 0
280 | [27 empty] | 0 | 0
281 | [27 empty] | 0 | 0
282 | [27 empty] | 0 | 0
283 | [27 empty] | 0 | 0
284 | [27 empty] | 0 | 0
285 | [27 empty] | 0 | 0
286 | [27 empty] | 0 | 0
287 | [27 empty] | 0 | 0
288 | [27 empty] | 0 | 0
289 | [27 empty] | 0 | 0
290 | [27 empty] | 0 | 0
291 | [27 empty] | 0 | 0
292 | [27 empty] | 0 | 0
293 | [27 empty] | 0 | 0
294 | [27 empty] | 0 | 0
295 | [27 empty] | 0 | 0
296 | [27 empty] | 0 | 0
297 | [27 empty] | 0 | 0
298 | [27 empty] | 0 | 0
299 | [27 empty] | 0 | 0
300 | [27 empty] | 0 | 0
301 | [27 empty] | 0 | 0
302 | [27 empty] | 0 | 0
303 | [27 empty] | 0 | 0
304 | [27 empty] | 0 | 0
305 | [27 empty] | 0 | 0
306 | [27 empty] | 0 | 0
307 | [27 empty] | 0 | 0
308 | [27 empty] | 0 | 0
309 | [27 empty] | 0 | 0
310 | [27 empty] | 0 | 0
311 | [27 empty] | 0 | 0
312 | [27 empty] | 0 | 0
313 | [27 empty] | 0 | 0
314 | [27 empty] | 0 | 0
315 | [27 empty] | 0 | 0
316 | [27 empty] | 0 | 0
317 | [27 empty] | 0 | 0
318 | [27 empty] | 0 | 0
319 | [27 empty] | 0 | 0
320 | [27 empty] | 0 | 0
321 | [27 empty] | 0 | 0
322 | [27 empty] | 0 | 0
323 | [27 empty] | 0 | 0
324 | [27 empty] | 0 | 0
325 | [27 empty] | 0 | 0
326 | [27 empty] | 0 | 0
327 | [27 empty] | 0 | 0
328 | [27 empty] | 0 | 0
329 | [27 empty] | 0 | 0
330 | [27 empty] | 0 | 0
331 | [27 empty] | 0 | 0
332 | [27 empty] | 0 | 0
333 | [27 empty] | 0 | 0
334 | [27 empty] | 0 | 0
335 | [27 empty] | 0 | 0
336 | [27 empty] | 0 | 0
337 | [27 empty] | 0 | 0
338 | [27 empty] | 0 | 0
339 | [27 empty] | 0 | 0
340 | [27 empty] | 0 | 0
341 | [27 empty] | 0 | 0
342 | [27 empty] | 0 | 0
343 | [27 empty] | 0 | 0
344 | [27 empty] | 0 | 0
345 | [27 empty] | 0 | 0
346 | [27 empty] | 0 | 0
347 | [27 empty] | 0 | 0
348 | [27 empty] | 0 | 0
349 | [27 empty] | 0 | 0
350 | [27 empty] | 0 | 0
351 | [27 empty] | 0 | 0
352 | [27 empty] | 0 | 0
353 | [27 empty] | 0 | 0
354 | [27 empty] | 0 | 0
355 | [27 empty] | 0 | 0
356 | [27 empty] | 0 | 0
357 | [27 empty] | 0 | 0
358 | [27 empty] | 0 | 0
359 | [27 empty] | 0 | 0
360 | [27 empty] | 0 | 0
361 | [27 empty] | 0 | 0
362 | [27 empty] | 0 | 0
363 | [27 empty] | 0 | 0
364 | [27 empty] | 0 | 0
365 | [27 empty] | 0 | 0
366 | [27 empty] | 0 | 0
367 | [27 empty] | 0 | 0
368 | [27 empty] | 0 | 0
369 | [27 empty] | 0 | 0
370 | [27 empty] | 0 | 0
371 | [27 empty] | 0 | 0
372 | [27 empty] | 0 | 0
373 | [27 empty] | 0 | 0
374 | [27 empty] | 0 | 0
375 | [27 empty] | 0 | 0
376 | [27 empty] | 0 | 0
377 | [27 empty] | 0 | 0
378 | [27 empty] | 0 | 0
379 | [27 empty] | 0 | 0
380 | [27 empty] | 0 | 0
381 | [27 empty] | 0 | 0
382 | [27 empty] | 0 | 0
383 | [27 empty] | 0 | 0
384 | [27 empty] | 0 | 0
385 | [27 empty] | 0 | 0
386 | [27 empty] | 0 | 0
387 | [27 empty] | 0 | 0
388 | [27 empty] | 0 | 0
389 | [27 empty] | 0 | 0
390 | [27 empty] | 0 | 0
391 | [27 empty] | 0 | 0
392 | [27 empty] | 0 | 0
393 | [27 empty] | 0 | 0
394 | [27 empty] | 0 | 0
395 | [27 empty] | 0 | 0
396 | [27 empty] | 0 | 0
397 | [27 empty] | 0 | 0
398 | [27 empty] | 0 | 0
399 | [27 empty] | 0 | 0
400 | [27 empty] | 0 | 0
401 | [27 empty] | 0 | 0
402 | [27 empty] | 0 | 0
403 | [27 empty] | 0 | 0
404 | [27 empty] | 0 | 0
405 | [27 empty] | 0 | 0
406 | [27 empty] | 0 | 0
407 | [27 empty] | 0 | 0
408 | [27 empty] | 0 | 0
409 | [27 empty] | 0 | 0
410 | [27 empty] | 0 | 0
411 | [27 empty] | 0 | 0
412 | [27 empty] | 0 | 0
413 | [27 empty] | 0 | 0
414 | [27 empty] | 0 | 0
415 | [27 empty] | 0 | 0
416 | [27 empty] | 0 | 0
417 | [27 empty] | 0 | 0
418 | [27 empty] | 0 | 0
419 | [27 empty] | 0 | 0
420 | [27 empty] | 0 | 0
421 | [27 empty] | 0 | 0
422 | [27 empty] | 0 | 0
423 | [27 empty] | 0 | 0
424 | [27 empty] | 0 | 0
425 | [27 empty] | 0 | 0
426 | [27 empty] | 0 | 0
427 | [27 empty] | 0 | 0
428 | [27 empty] | 0 | 0
429 | [27 empty] | 0 | 0
430 | [27 empty] | 0 | 0
431 | [27 empty] | 0 | 0
432 | [27 empty] | 0 | 0
433 | [27 empty] | 0 | 0
434 | [27 empty] | 0 | 0
435 | [27 empty] | 0 | 0
436 | [27 empty] | 0 | 0
437 | [27 empty] | 0 | 0
438 | [27 empty] | 0 | 0
439 | [27 empty] | 0 | 0
440 | [27 empty] | 0 | 0
441 | [27 empty] | 0 | 0
442 | [27 empty] | 0 | 0
443 | [27 empty] | 0 | 0
444 | [27 empty] | 0 | 0
445 | [27 empty] | 0 | 0
446 | [27 empty] | 0 | 0
447 | [27 empty] | 0 | 0
448 | [27 empty] | 0 | 0
449 | [27 empty] | 0 | 0
450 | [27 empty] | 0 | 0
451 | [27 empty] | 0 | 0
452 | [27 empty] | 0 | 0
453 | [27 empty] | 0 | 0
454 | [27 empty] | 0 | 0
455 | [27 empty] | 0 | 0
456 | [27 empty] | 0 | 0
457 | [27 empty] | 0 | 0
458 | [27 empty] | 0 | 0
459 | [27 empty] | 0 | 0
460 | [27 empty] | 0 | 0
461 | [27 empty] | 0 | 0
462 | [27 empty] | 0 | 0
463 | [27 empty] | 0 | 0
464 | [27 empty] | 0 | 0
465 | [27 empty] | 0 | 0
466 | [27 empty] | 0 | 0
467 | [27 empty] | 0 | 0
468 | [27 empty] | 0 | 0
469 | [27 empty] | 0 | 0
470 | [27 empty] | 0 | 0
471 | [27 empty] | 0 | 0
472 | [27 empty] | 0 | 0
473 | [27 empty] | 0 | 0
474 | [27 empty] | 0 | 0
475 | [27 empty] | 0 | 0
476 | [27 empty] | 0 | 0
477 | [27 empty] | 0 | 0
478 | [27 empty] | 0 | 0
479 | [27 empty] | 0 | 0
480 | [27 empty] | 0 | 0
481 | [27 empty] | 0 | 0
482 | [27 empty] | 0 | 0
483 | [27 empty] | 0 | 0
484 | [27 empty] | 0 | 0
485 | [27 empty] | 0 | 0
486 | [27 empty] | 0 | 0
487 | [27 empty] | 0 | 0
488 | [27 empty] | 0 | 0
489 | [27 empty] | 0 | 0
490 | [27 empty] | 0 | 0
491 | [27 empty] | 0 | 0
492 | [27 empty] | 0 | 0
493 | [27 empty] | 0 | 0
494 | [27 empty] | 0 | 0
495 | [27 empty] | 0 | 0
496 | [27 empty] | 0 | 0
497 | [27 empty] | 0 | 0
498 | [27 empty] | 0 | 0
499 | [27 empty] | 0 | 0
500 | [27 empty] | 0 | 0
501 | [27 empty] | 0 | 0
502 | [27 empty] | 0 | 0
503 | [27 empty] | 0 | 0
504 | [27 empty] | 0 | 0
505 | [27 empty] | 0 | 0
506 | [27 empty] | 0 | 0
507 | [27 empty] | 0 | 0
508 | [27 empty] | 0 | 0
509 | [27 empty] | 0 | 0
510 | [27 empty] | 0 | 0
511 | [27 empty] | 0 | 0
512 | [27 empty] | 0 | 0
513 | [27 empty] | 0 | 0
514 | [27 empty] | 0 | 0
515 | [27 empty] | 0 | 0
516 | [27 empty] | 0 | 0
517 | [27 empty] | 0 | 0
518 | [27 empty] | 0 | 0
519 | [27 empty] | 0 | 0
520 | [27 empty] | 0 | 0
521 | [27 empty] | 0 | 0
522 | [27 empty] | 0 | 0
523 | [27 empty] | 0 | 0
524 | [27 empty] | 0 | 0
525 | [27 empty] | 0 | 0
526 | [27 empty] | 0 | 0
527 | [27 empty] | 0 | 0
528 | [27 empty] | 0 | 0
529 | [27 empty] | 0 | 0
530 | [27 empty] | 0 | 0
531 | [27 empty] | 0 | 0
532 | [27 empty] | 0 | 0
533 | [27 empty] | 0 | 0
534 | [27 empty] | 0 | 0
535 | [27 empty] | 0 | 0
536 | [27 empty] | 0 | 0
537 | [27 empty] | 0 | 0
538 | [27 empty] | 0 | 0
539 | [27 empty] | 0 | 0
540 | [27 empty] | 0 | 0
541 | [27 empty] | 0 | 0
542 | [27 empty] | 0 | 0
543 | [27 empty] | 0 | 0
544 | [27 empty] | 0 | 0
545 | [27 empty] | 0 | 0
546 | [27 empty] | 0 | 0
547 | [27 empty] | 0 | 0
548 | [27 empty] | 0 | 0
549 | [27 empty] | 0 | 0
550 | [27 empty] | 0 | 0
551 | [27 empty] | 0 | 0
552 | [27 empty] | 0 | 0
553 | [27 empty] | 0 | 0
554 | [27 empty] | 0 | 0
555 | [27 empty] | 0 | 0
556 | [27 empty] | 0 | 0
557 | [27 empty] | 0 | 0
558 | [27 empty] | 0 | 0
559 | [27 empty] | 0 | 0
560 | [27 empty] | 0 | 0
561 | [27 empty] | 0 | 0
562 | [27 empty] | 0 | 0
563 | [27 empty] | 0 | 0
564 | [27 empty] | 0 | 0
565 | [27 empty] | 0 | 0
566 | [27 empty] | 0 | 0
567 | [27 empty] | 0 | 0
568 | [27 empty] | 0 | 0
569 | [27 empty] | 0 | 0
570 | [27 empty] | 0 | 0
571 | [27 empty] | 0 | 0
572 | [27 empty] | 0 | 0
573 | [27 empty] | 0 | 0
574 | [27 empty] | 0 | 0
575 | [27 empty] | 0 | 0
576 | [27 empty] | 0 | 0
577 | [27 empty] | 0 | 0
578 | [27 empty] | 0 | 0
579 | [27 empty] | 0 | 0
580 | [27 empty] | 0 | 0
581 | [27 empty] | 0 | 0
582 | [27 empty] | 0 | 0
583 | [27 empty] | 0 | 0
584 | [27 empty] | 0 | 0
585 | [27 empty] | 0 | 0
586 | [27 empty] | 0 | 0
587 | [27 empty] | 0 | 0
588 | [27 empty] | 0 | 0
589 | [27 empty] | 0 | 0
590 | [27 empty] | 0 | 0
591 | [27 empty] | 0 | 0
592 | [27 empty] | 0 | 0
593 | [27 empty] | 0 | 0
594 | [27 empty] | 0 | 0
595 | [27 empty] | 0 | 0
596 | [27 empty] | 0 | 0
597 | [27 empty] | 0 | 0
598 | [27 empty] | 0 | 0
599 | [27 empty] | 0 | 0
600 | [27 empty] | 0 | 0
601 | [27 empty] | 0 | 0
602 | [27 empty] | 0 | 0
603 | [27 empty] | 0 | 0
604 | [27 empty] | 0 | 0
605 | [27 empty] | 0 | 0
606 | [27 empty] | 0 | 0
607 | [27 empty] | 0 | 0
608 | [27 empty] | 0 | 0
609 | [27 empty] | 0 | 0
610 | [27 empty] | 0 | 0
611 | [27 empty] | 0 | 0
612 | [27 empty] | 0 | 0
613 | [27 empty] | 0 | 0
614 | [27 empty] | 0 | 0
615 | [27 empty] | 0 | 0
616 | [27 empty] | 0 | 0
617 | [27 empty] | 0 | 0
618 | [27 empty] | 0 | 0
619 | [27 empty] | 0 | 0
620 | [27 empty] | 0 | 0
621 | [27 empty] | 0 | 0
622 | [27 empty] | 0 | 0
623 | [27 empty] | 0 | 0
624 | [27 empty] | 0 | 0
625 | [27 empty] | 0 | 0
626 | [27 empty] | 0 | 0
627 | [27 empty] | 0 | 0
628 | [27 empty] | 0 | 0
629 | [27 empty] | 0 | 0
630 | [27 empty] | 0 | 0
631 | [27 empty] | 0 | 0
632 | [27 empty] | 0 | 0
633 | [27 empty] | 0 | 0
634 | [27 empty] | 0 | 0
635 | [27 empty] | 0 | 0
636 | [27 empty] | 0 | 0
637 | [27 empty] | 0 | 0
638 | [27 empty] | 0 | 0
639 | [27 empty] | 0 | 0
640 | [27 empty] | 0 | 0
641 | [27 empty] | 0 | 0
642 | [27 empty] | 0 | 0
643 | [27 empty] | 0 | 0
644 | [27 empty] | 0 | 0
645 | [27 empty] | 0 | 0
646 | [27 empty] | 0 | 0
647 | [27 empty] | 0 | 0
648 | [27 empty] | 0 | 0
649 | [27 empty] | 0 | 0
650 | [27 empty] | 0 | 0
651 | [27 empty] | 0 | 0
652 | [27 empty] | 0 | 0
653 | [27 empty] | 0 | 0
654 | [27 empty] | 0 | 0
655 | [27 empty] | 0 | 0
656 | [27 empty] | 0 | 0
657 | [27 empty] | 0 | 0
658 | [27 empty] | 0 | 0
659 | [27 empty] | 0 | 0
660 | [27 empty] | 0 | 0
661 | [27 empty] | 0 | 0
662 | [27 empty] | 0 | 0
663 | [27 empty] | 0 | 0
664 | [27 empty] | 0 | 0
665 | [27 empty] | 0 | 0
666 | [27 empty] | 0 | 0
667 | [27 empty] | 0 | 0
668 | [27 empty] | 0 | 0
669 | [27 empty] | 0 | 0
670 | [27 empty] | 0 | 0
671 | [27 empty] | 0 | 0
672 | [27 empty] | 0 | 0
673 | [27 empty] | 0 | 0
674 | [27 empty] | 0 | 0
675 | [27 empty] | 0 | 0
676 | [27 empty] | 0 | 0
677 | [27 empty] | 0 | 0
678 | [27 empty] | 0 | 0
679 | [27 empty] | 0 | 0
680 | [27 empty] | 0 | 0
681 | [27 empty] | 0 | 0
682 | [27 empty] | 0 | 0
683 | [27 empty] | 0 | 0
684 | [27 empty] | 0 | 0
685 | [27 empty] | 0 | 0
686 | [27 empty] | 0 | 0
687 | [27 empty] | 0 | 0
688 | [27 empty] | 0 | 0
689 | [27 empty] | 0 | 0
690 | [27 empty] | 0 | 0
691 | [27 empty] | 0 | 0
692 | [27 empty] | 0 | 0
693 | [27 empty] | 0 | 0
694 | [27 empty] | 0 | 0
695 | [27 empty] | 0 | 0
696 | [27 empty] | 0 | 0
697 | [27 empty] | 0 | 0
698 | [27 empty] | 0 | 0
699 | [27 empty] | 0 | 0
700 | [27 empty] | 0 | 0
701 | [27 empty] | 0 | 0
702 | [27 empty] | 0 | 0
703 | [27 empty] | 0 | 0
704 | [27 empty] | 0 | 0
705 | [27 empty] | 0 | 0
706 | [27 empty] | 0 | 0
707 | [27 empty] | 0 | 0
708 | [27 empty] | 0 | 0
709 | [27 empty] | 0 | 0
710 | [27 empty] | 0 | 0
711 | [27 empty] | 0 | 0
712 | [27 empty] | 0 | 0
713 | [27 empty] | 0 | 0
714 | [27 empty] | 0 | 0
715 | [27 empty] | 0 | 0
716 | [27 empty] | 0 | 0
717 | [27 empty] | 0 | 0
718 | [27 empty] | 0 | 0
719 | [27 empty] | 0 | 0
720 | [27 empty] | 0 | 0
721 | [27 empty] | 0 | 0
722 | [27 empty] | 0 | 0
723 | [27 empty] | 0 | 0
724 | [27 empty] | 0 | 0
725 | [27 empty] | 0 | 0
726 | [27 empty] | 0 | 0
727 | [27 empty] | 0 | 0
728 | [27 empty] | 0 | 0
729 | [27 empty] | 0 | 0
730 | [27 empty] | 0 | 0
731 | [27 empty] | 0 | 0
732 | [27 empty] | 0 | 0
733 | [27 empty] | 0 | 0
734 | [27 empty] | 0 | 0
735 | [27 empty] | 0 | 0
736 | [27 empty] | 0 | 0
737 | [27 empty] | 0 | 0
738 | [27 empty] | 0 | 0
739 | [27 empty] | 0 | 0
740 | [27 empty] | 0 | 0
741 | [27 empty] | 0 | 0
742 | [27 empty] | 0 | 0
743 | [27 empty] | 0 | 0
744 | [27 empty] | 0 | 0
745 | [27 empty] | 0 | 0
746 | [27 empty] | 0 | 0
747 | [27 empty] | 0 | 0
748 | [27 empty] | 0 | 0
749 | [27 empty] | 0 | 0
750 | [27 empty] | 0 | 0
751 | [27 empty] | 0 | 0
752 | [27 empty] | 0 | 0
753 | [27 empty] | 0 | 0
754 | [27 empty] | 0 | 0
755 | [27 empty] | 0 | 0
756 | [27 empty] | 0 | 0
757 | [27 empty] | 0 | 0
758 | [27 empty] | 0 | 0
759 | [27 empty] | 0 | 0
760 | [27 empty] | 0 | 0
761 | [27 empty] | 0 | 0
762 | [27 empty] | 0 | 0
763 | [27 empty] | 0 | 0
764 | [27 empty] | 0 | 0
765 | [27 empty] | 0 | 0
766 | [27 empty] | 0 | 0
767 | [27 empty] | 0 | 0
768 | [27 empty] | 0 | 0
769 | [27 empty] | 0 | 0
770 | [27 empty] | 0 | 0
771 | [27 empty] | 0 | 0
772 | [27 empty] | 0 | 0
773 | [27 empty] | 0 | 0
774 | [27 empty] | 0 | 0
775 | [27 empty] | 0 | 0
776 | [27 empty] | 0 | 0
777 | [27 empty] | 0 | 0
778 | [27 empty] | 0 | 0
779 | [27 empty] | 0 | 0
780 | [27 empty] | 0 | 0
781 | [27 empty] | 0 | 0
782 | [27 empty] | 0 | 0
783 | [27 empty] | 0 | 0
784 | [27 empty] | 0 | 0
785 | [27 empty] | 0 | 0
786 | [27 empty] | 0 | 0
787 | [27 empty] | 0 | 0
788 | [27 empty] | 0 | 0
789 | [27 empty] | 0 | 0
790 | [27 empty] | 0 | 0
791 | [27 empty] | 0 | 0
792 | [27 empty] | 0 | 0
793 | [27 empty] | 0 | 0
794 | [27 empty] | 0 | 0
795 | [27 empty] | 0 | 0
796 | [27 empty] | 0 | 0
797 | [27 empty] | 0 | 0
798 | [27 empty] | 0 | 0
799 | [27 empty] | 0 | 0
800 | [27 empty] | 0 | 0
801 | [27 empty] | 0 | 0
802 | [27 empty] | 0 | 0
803 | [27 empty] | 0 | 0
804 | [27 empty] | 0 | 0
805 | [27 empty] | 0 | 0
806 | [27 empty] | 0 | 0
807 | [27 empty] | 0 | 0
808 | [27 empty] | 0 | 0
809 | [27 empty] | 0 | 0
810 | [27 empty] | 0 | 0
811 | [27 empty] | 0 | 0
812 | [27 empty] | 0 | 0
813 | [27 empty] | 0 | 0
814 | [27 empty] | 0 | 0
815 | [27 empty] | 0 | 0
816 | [27 empty] | 0 | 0
817 | [27 empty] | 0 | 0
818 | [27 empty] | 0 | 0
819 | [27 empty] | 0 | 0
820 | [27 empty] | 0 | 0
821 | [27 empty] | 0 | 0
822 | [27 empty] | 0 | 0
823 | [27 empty] | 0 | 0
824 | [27 empty] | 0 | 0
825 | [27 empty] | 0 | 0
826 | [27 empty] | 0 | 0
827 | [27 empty] | 0 | 0
828 | [27 empty] | 0 | 0
829 | [27 empty] | 0 | 0
830 | [27 empty] | 0 | 0
831 | [27 empty] | 0 | 0
832 | [27 empty] | 0 | 0
833 | [27 empty] | 0 | 0
834 | [27 empty] | 0 | 0
835 | [27 empty] | 0 | 0
836 | [27 empty] | 0 | 0
837 | [27 empty] | 0 | 0
838 | [27 empty] | 0 | 0
839 | [27 empty] | 0 | 0
840 | [27 empty] | 0 | 0
841 | [27 empty] | 0 | 0
842 | [27 empty] | 0 | 0
843 | [27 empty] | 0 | 0
844 | [27 empty] | 0 | 0
845 | [27 empty] | 0 | 0
846 | [27 empty] | 0 | 0
847 | [27 empty] | 0 | 0
848 | [27 empty] | 0 | 0
849 | [27 empty] | 0 | 0
850 | [27 empty] | 0 | 0
851 | [27 empty] | 0 | 0
852 | [27 empty] | 0 | 0
853 | [27 empty] | 0 | 0
854 | [27 empty] | 0 | 0
855 | [27 empty] | 0 | 0
856 | [27 empty] | 0 | 0
857 | [27 empty] | 0 | 0
858 | [27 empty] | 0 | 0
859 | [27 empty] | 0 | 0
860 | [27 empty] | 0 | 0
861 | [27 empty] | 0 | 0
862 | [27 empty] | 0 | 0
863 | [27 empty] | 0 | 0
864 | [27 empty] | 0 | 0
865 | [27 empty] | 0 | 0
866 | [27 empty] | 0 | 0
867 | [27 empty] | 0 | 0
868 | [27 empty] | 0 | 0
869 | [27 empty] | 0 | 0
870 | [27 empty] | 0 | 0
871 | [27 empty] | 0 | 0
872 | [27 empty] | 0 | 0
873 | [27 empty] | 0 | 0
874 | [27 empty] | 0 | 0
875 | [27 empty] | 0 | 0
876 | [27 empty] | 0 | 0
877 | [27 empty] | 0 | 0
878 | [27 empty] | 0 | 0
879 | [27 empty] | 0 | 0
880 | [27 empty] | 0 | 0
881 | [27 empty] | 0 | 0
882 | [27 empty] | 0 | 0
883 | [27 empty] | 0 | 0
884 | [27 empty] | 0 | 0
885 | [27 empty] | 0 | 0
886 | [27 empty] | 0 | 0
887 | [27 empty] | 0 | 0
888 | [27 empty] | 0 | 0
889 | [27 empty] | 0 | 0
890 | [27 empty] | 0 | 0
891 | [27 empty] | 0 | 0
892 | [27 empty] | 0 | 0
893 | [27 empty] | 0 | 0
894 | [27 empty] | 0 | 0
895 | [27 empty] | 0 | 0
896 | [27 empty] | 0 | 0
897 | [27 empty] | 0 | 0
898 | [27 empty] | 0 | 0
899 | [27 empty] | 0 | 0
900 | [27 empty] | 0 | 0
901 | [27 empty] | 0 | 0
902 | [27 empty] | 0 | 0
903 | [27 empty] | 0 | 0
904 | [27 empty] | 0 | 0
905 | [27 empty] | 0 | 0
906 | [27 empty] | 0 | 0
907 | [27 empty] | 0 | 0
908 | [27 empty] | 0 | 0
909 | [27 empty] | 0 | 0
910 | [27 empty] | 0 | 0
911 | [27 empty] | 0 | 0
912 | [27 empty] | 0 | 0
913 | [27 empty] | 0 | 0
914 | [27 empty] | 0 | 0
915 | [27 empty] | 0 | 0
916 | [27 empty] | 0 | 0
917 | [27 empty] | 0 | 0
918 | [27 empty] | 0 | 0
919 | [27 empty] | 0 | 0
920 | [27 empty] | 0 | 0
921 | [27 empty] | 0 | 0
922 | [27 empty] | 0 | 0
923 | [27 empty] | 0 | 0
924 | [27 empty] | 0 | 0
925 | [27 empty] | 0 | 0
926 | [27 empty] | 0 | 0
927 | [27 empty] | 0 | 0
928 | [27 empty] | 0 | 0
929 | [27 empty] | 0 | 0
930 | [27 empty] | 0 | 0
931 | [27 empty] | 0 | 0
932 | [27 empty] | 0 | 0
933 | [27 empty] | 0 | 0
934 | [27 empty] | 0 | 0
935 | [27 empty] | 0 | 0
936 | [27 empty] | 0 | 0
937 | [27 empty] | 0 | 0
938 | [27 empty] | 0 | 0
939 | [27 empty] | 0 | 0
940 | [27 empty] | 0 | 0
941 | [27 empty] | 0 | 0
942 | [27 empty] | 0 | 0
943 | [27 empty] | 0 | 0
944 | [27 empty] | 0 | 0
945 | [27 empty] | 0 | 0
946 | [27 empty] | 0 | 0
947 | [27 empty] | 0 | 0
948 | [27 empty] | 0 | 0
949 | [27 empty] | 0 | 0
950 | [27 empty] | 0 | 0
951 | [27 empty] | 0 | 0
952 | [27 empty] | 0 | 0
953 | [27 empty] | 0 | 0
954 | [27 empty] | 0 | 0
955 | [27 empty] | 0 | 0
956 | [27 empty] | 0 | 0
957 | [27 empty] | 0 | 0
958 | [27 empty] | 0 | 0
959 | [27 empty] | 0 | 0
960 | [27 empty] | 0 | 0
961 | [27 empty] | 0 | 0
962 | [27 empty] | 0 | 0
963 | [27 empty] | 0 | 0
964 | [27 empty] | 0 | 0
965 | [27 empty] | 0 | 0
966 | [27 empty] | 0 | 0
967 | [27 empty] | 0 | 0
968 | [27 empty] | 0 | 0
969 | [27 empty] | 0 | 0
970 | [27 empty] | 0 | 0
971 | [27 empty] | 0 | 0
972 | [27 empty] | 0 | 0
973 | [27 empty] | 0 | 0
974 | [27 empty] | 0 | 0
975 | [27 empty] | 0 | 0
976 | [27 empty] | 0 | 0
977 | [27 empty] | 0 | 0
978 | [27 empty] | 0 | 0
979 | [27 empty] | 0 | 0
980 | [27 empty] | 0 | 0
981 | [27 empty] | 0 | 0
982 | [27 empty] | 0 | 0
983 | [27 empty] | 0 | 0
984 | [27 empty] | 0 | 0
985 | [27 empty] | 0 | 0
986 | [27 empty] | 0 | 0
987 | [27 empty] | 0 | 0
988 | [27 empty] | 0 | 0
989 | [27 empty] | 0 | 0
990 | [27 empty] | 0 | 0
991 | [27 empty] | 0 | 0
992 | [27 empty] | 0 | 0
993 | [27 empty] | 0 | 0
994 | [27 empty] | 0 | 0
995 | [27 empty] | 0 | 0
996 | [27 empty] | 0 | 0
997 | [27 empty] | 0 | 0
998 | [27 empty] | 0 | 0
999 | [27 empty] | 0 | 0
1000 | [27 empty] | 0 | 0
1001 | [27 empty] | 0 | 0
1002 | [27 empty] | 0 | 0
1003 | [27 empty] | 0 | 0
1004 | [27 empty] | 0 | 0
1005 | [27 empty] | 0 | 0
1006 | [27 empty] | 0 | 0
1007 | [27 empty] | 0 | 0
1008 | [27 empty] | 0 | 0
1009 | [27 empty] | 0 | 0
1010 | [27 empty] | 0 | 0
1011 | [27 empty] | 0 | 0
1012 | [27 empty] | 0 | 0
1013 | [27 empty] | 0 | 0
1014 | [27 empty] | 0 | 0
1015 | [27 empty] | 0 | 0
1016 | [27 empty] | 0 | 0
1017 | [27 empty] | 0 | 0
1018 | [27 empty] | 0 | 0
1019 | [27 empty] | 0 | 0
1020 | [27 empty] | 0 | 0
1021 | [27 empty] | 0 | 0
1022 | [27 empty] | 0 | 0
1023 | [27 empty] | 0 | 0
1024 | [27 empty] | 0 | 0
1025 | [27 empty] | 0 | 0
1026 | [27 empty] | 0 | 0
1027 | [27 empty] | 0 | 0
1028 | [27 empty] | 0 | 0
1029 | [27 empty] | 0 | 0
1030 | [27 empty] | 0 | 0
1031 | [27 empty] | 0 | 0
1032 | [27 empty] | 0 | 0
1033 | [27 empty] | 0 | 0
1034 | [27 empty] | 0 | 0
1035 | [27 empty] | 0 | 0
1036 | [27 empty] | 0 | 0
1037 | [27 empty] | 0 | 0
1038 | [27 empty] | 0 | 0
1039 | [27 empty] | 0 | 0
1040 | [27 empty] | 0 | 0
1041 | [27 empty] | 0 | 0
1042 | [27 empty] | 0 | 0
1043 | [27 empty] | 0 | 0
1044 | [27 empty] | 0 | 0
1045 | [27 empty] | 0 | 0
1046 | [27 empty] | 0 | 0
1047 | [27 empty] | 0 | 0
1048 | [27 empty] | 0 | 0
1049 | [27 empty] | 0 | 0
1050 | [27 empty] | 0 | 0
1051 | [27 empty] | 0 | 0
1052 | [27 empty] | 0 | 0
1053 | [27 empty] | 0 | 0
1054 | [27 empty] | 0 | 0
1055 | [27 empty] | 0 | 0
1056 | [27 empty] | 0 | 0
1057 | [27 empty] | 0 | 0
1058 | [27 empty] | 0 | 0
1059 | [27 empty] | 0 | 0
1060 | [27 empty] | 0 | 0
1061 | [27 empty] | 0 | 0
1062 | [27 empty] | 0 | 0
1063 | [27 empty] | 0 | 0
1064 | [27 empty] | 0 | 0
1065 | [27 empty] | 0 | 0
1066 | [27 empty] | 0 | 0
1067 | [27 empty] | 0 | 0
1068 | [27 empty] | 0 | 0
1069 | [27 empty] | 0 | 0
1070 | [27 empty] | 0 | 0
1071 | [27 empty] | 0 | 0
1072 | [27 empty] | 0 | 0
1073 | [27 empty] | 0 | 0
1074 | [27 empty] | 0 | 0
1075 | [27 empty] | 0 | 0
1076 | [27 empty] | 0 | 0
1077 | [27 empty] | 0 | 0
1078 | [27 empty] | 0 | 0
1079 | [27 empty] | 0 | 0
1080 | [27 empty] | 0 | 0
1081 | [27 empty] | 0 | 0
1082 | [27 empty] | 0 | 0
1083 | [27 empty] | 0 | 0
1084 | [27 empty] | 0 | 0
1085 | [27 empty] | 0 | 0
1086 | [27 empty] | 0 | 0
1087 | [27 empty] | 0 | 0
1088 | [27 empty] | 0 | 0
1089 | [27 empty] | 0 | 0
1090 | [27 empty] | 0 | 0
1091 | [27 empty] | 0 | 0
1092 | [27 empty] | 0 | 0
1093 | [27 empty] | 0 | 0
1094 | [27 empty] | 0 | 0
1095 | [27 empty] | 0 | 0
1096 | [27 empty] | 0 | 0
1097 | [27 empty] | 0 | 0
1098 | [27 empty] | 0 | 0
1099 | [27 empty] | 0 | 0
1100 | [27 empty] | 0 | 0
1101 | [27 empty] | 0 | 0
1102 | [27 empty] | 0 | 0
1103 | [27 empty] | 0 | 0
1104 | [27 empty] | 0 | 0
1105 | [27 empty] | 0 | 0
1106 | [27 empty] | 0 | 0
1107 | [27 empty] | 0 | 0
1108 | [27 empty] | 0 | 0
1109 | [27 empty] | 0 | 0
1110 | [27 empty] | 0 | 0
1111 | [27 empty] | 0 | 0
1112 | [27 empty] | 0 | 0
1113 | [27 empty] | 0 | 0
1114 | [27 empty] | 0 | 0
1115 | [27 empty] | 0 | 0
1116 | [27 empty] | 0 | 0
1117 | [27 empty] | 0 | 0
1118 | [27 empty] | 0 | 0
1119 | [27 empty] | 0 | 0
1120 | [27 empty] | 0 | 0
1121 | [27 empty] | 0 | 0
1122 | [27 empty] | 0 | 0
1123 | [27 empty] | 0 | 0
1124 | [27 empty] | 0 | 0
1125 | [27 empty] | 0 | 0
1126 | [27 empty] | 0 | 0
1127 | [27 empty] | 0 | 0
1128 | [27 empty] | 0 | 0
1129 | [27 empty] | 0 | 0
1130 | [27 empty] | 0 | 0
1131 | [27 empty] | 0 | 0
1132 | [27 empty] | 0 | 0
1133 | [27 empty] | 0 | 0
1134 | [27 empty] | 0 | 0
1135 | [27 empty] | 0 | 0
1136 | [27 empty] | 0 | 0
1137 | [27 empty] | 0 | 0
1138 | [27 empty] | 0 | 0
1139 | [27 empty] | 0 | 0
1140 | [27 empty] | 0 | 0
1141 | [27 empty] | 0 | 0
1142 | [27 empty] | 0 | 0
1143 | [27 empty] | 0 | 0
1144 | [27 empty] | 0 | 0
1145 | [27 empty] | 0 | 0
1146 | [27 empty] | 0 | 0
1147 | [27 empty] | 0 | 0
1148 | [27 empty] | 0 | 0
1149 | [27 empty] | 0 | 0
1150 | [27 empty] | 0 | 0
1151 | [27 empty] | 0 | 0
1152 | [27 empty] | 0 | 0
1153 | [27 empty] | 0 | 0
1154 | [27 empty] | 0 | 0
1155 | [27 empty] | 0 | 0
1156 | [27 empty] | 0 | 0
1157 | [27 empty] | 0 | 0
1158 | [27 empty] | 0 | 0
1159 | [27 empty] | 0 | 0
1160 | [27 empty] | 0 | 0
1161 | [27 empty] | 0 | 0
1162 | [27 empty] | 0 | 0
1163 | [27 empty] | 0 | 0
1164 | [27 empty] | 0 | 0
1165 | [27 empty] | 0 | 0
1166 | [27 empty] | 0 | 0
1167 | [27 empty] | 0 | 0
1168 | [27 empty] | 0 | 0
1169 | [27 empty] | 0 | 0
1170 | [27 empty] | 0 | 0
1171 | [27 empty] | 0 | 0
1172 | [27 empty] | 0 | 0
1173 | [27 empty] | 0 | 0
1174 | [27 empty] | 0 | 0
1175 | [27 empty] | 0 | 0
1176 | [27 empty] | 0 | 0
1177 | [27 empty] | 0 | 0
1178 | [27 empty] | 0 | 0
1179 | [27 empty] | 0 | 0
1180 | [27 empty] | 0 | 0
1181 | [27 empty] | 0 | 0
1182 | [27 empty] | 0 | 0
1183 | [27 empty] | 0 | 0
1184 | [27 empty] | 0 | 0
1185 | [27 empty] | 0 | 0
1186 | [27 empty] | 0 | 0
1187 | [27 empty] | 0 | 0
1188 | [27 empty] | 0 | 0
1189 | [27 empty] | 0 | 0
1190 | [27 empty] | 0 | 0
1191 | [27 empty] | 0 | 0
1192 | [27 empty] | 0 | 0
1193 | [27 empty] | 0 | 0
1194 | [27 empty] | 0 | 0
1195 | [27 empty] | 0 | 0
1196 | [27 empty] | 0 | 0
1197 | [27 empty] | 0 | 0
1198 | [27 empty] | 0 | 0
1199 | [27 empty] | 0 | 0
1200 | [27 empty] | 0 | 0
1201 | [27 empty] | 0 | 0
1202 | [27 empty] | 0 | 0
1203 | [27 empty] | 0 | 0
1204 | [27 empty] | 0 | 0
1205 | [27 empty] | 0 | 0
1206 | [27 empty] | 0 | 0
1207 | [27 empty] | 0 | 0
1208 | [27 empty] | 0 | 0
1209 | [27 empty] | 0 | 0
1210 | [27 empty] | 0 | 0
1211 | [27 empty] | 0 | 0
1212 | [27 empty] | 0 | 0
1213 | [27 empty] | 0 | 0
1214 | [27 empty] | 0 | 0
1215 | [27 empty] | 0 | 0
1216 | [27 empty] | 0 | 0
1217 | [27 empty] | 0 | 0
1218 | [27 empty] | 0 | 0
1219 | [27 empty] | 0 | 0
1220 | [27 empty] | 0 | 0
1221 | [27 empty] | 0 | 0
1222 | [27 empty] | 0 | 0
1223 | [27 empty] | 0 | 0
1224 | [27 empty] | 0 | 0
1225 | [27 empty] | 0 | 0
1226 | [27 empty] | 0 | 0
1227 | [27 empty] | 0 | 0
1228 | [27 empty] | 0 | 0
1229 | [27 empty] | 0 | 0
1230 | [27 empty] | 0 | 0
1231 | [27 empty] | 0 | 0
1232 | [27 empty] | 0 | 0
1233 | [27 empty] | 0 | 0
1234 | [27 empty] | 0 | 0
1235 | [27 empty] | 0 | 0
1236 | [27 empty] | 0 | 0
1237 | [27 empty] | 0 | 0
1238 | [27 empty] | 0 | 0
1239 | [27 empty] | 0 | 0
1240 | [27 empty] | 0 | 0
1241 | [27 empty] | 0 | 0
1242 | [27 empty] | 0 | 0
1243 | [27 empty] | 0 | 0
1244 | [27 empty] | 0 | 0
1245 | [27 empty] | 0 | 0
1246 | [27 empty] | 0 | 0
1247 | [27 empty] | 0 | 0
1248 | [27 empty] | 0 | 0
1249 | [27 empty] | 0 | 0
1250 | [27 empty] | 0 | 0
1251 | [27 empty] | 0 | 0
1252 | [27 empty] | 0 | 0
1253 | [27 empty] | 0 | 0
1254 | [27 empty] | 0 | 0
1255 | [27 empty] | 0 | 0
1256 | [27 empty] | 0 | 0
1257 | [27 empty] | 0 | 0
1258 | [27 empty] | 0 | 0
1259 | [27 empty] | 0 | 0
1260 | [27 empty] | 0 | 0
1261 | [27 empty] | 0 | 0
1262 | [27 empty] | 0 | 0
1263 | [27 empty] | 0 | 0
1264 | [27 empty] | 0 | 0
1265 | [27 empty] | 0 | 0
1266 | [27 empty] | 0 | 0
1267 | [27 empty] | 0 | 0
1268 | [27 empty] | 0 | 0
1269 | [27 empty] | 0 | 0
1270 | [27 empty] | 0 | 0
1271 | [27 empty] | 0 | 0
1272 | [27 empty] | 0 | 0
1273 | [27 empty] | 0 | 0
1274 | [27 empty] | 0 | 0
1275 | [27 empty] | 0 | 0
1276 | [27 empty] | 0 | 0
1277 | [27 empty] | 0 | 0
1278 | [27 empty] | 0 | 0
1279 | [27 empty] | 0 | 0
1280 | [27 empty] | 0 | 0
1281 | [27 empty] | 0 | 0
1282 | [27 empty] | 0 | 0
1283 | [27 empty] | 0 | 0
1284 | [27 empty] | 0 | 0
1285 | [27 empty] | 0 | 0
1286 | [27 empty] | 0 | 0
1287 | [27 empty] | 0 | 0
1288 | [27 empty] | 0 | 0
1289 | [27 empty] | 0 | 0
1290 | [27 empty] | 0 | 0
1291 | [27 empty] | 0 | 0
1292 | [27 empty] | 0 | 0
1293 | [27 empty] | 0 | 0
1294 | [27 empty] | 0 | 0
1295 | [27 empty] | 0 | 0
1296 | [27 empty] | 0 | 0
1297 | [27 empty] | 0 | 0
1298 | [27 empty] | 0 | 0
1299 | [27 empty] | 0 | 0
1300 | [27 empty] | 0 | 0
1301 | [27 empty] | 0 | 0
1302 | [27 empty] | 0 | 0
1303 | [27 empty] | 0 | 0
1304 | [27 empty] | 0 | 0
1305 | [27 empty] | 0 | 0
1306 | [27 empty] | 0 | 0
1307 | [27 empty] | 0 | 0
1308 | [27 empty] | 0 | 0
1309 | [27 empty] | 0 | 0
1310 | [27 empty] | 0 | 0
1311 | [27 empty] | 0 | 0
1312 | [27 empty] | 0 | 0
1313 | [27 empty] | 0 | 0
1314 | [27 empty] | 0 | 0
1315 | [27 empty] | 0 | 0
1316 | [27 empty] | 0 | 0
1317 | [27 empty] | 0 | 0
1318 | [27 empty] | 0 | 0
1319 | [27 empty] | 0 | 0
1320 | [27 empty] | 0 | 0
1321 | [27 empty] | 0 | 0
1322 | [27 empty] | 0 | 0
1323 | [27 empty] | 0 | 0
1324 | [27 empty] | 0 | 0
1325 | [27 empty] | 0 | 0
1326 | [27 empty] | 0 | 0
1327 | [27 empty] | 0 | 0
1328 | [27 empty] | 0 | 0
1329 | [27 empty] | 0 | 0
1330 | [27 empty] | 0 | 0
1331 | [27 empty] | 0 | 0
1332 | [27 empty] | 0 | 0
1333 | [27 empty] | 0 | 0
1334 | [27 empty] | 0 | 0
1335 | [27 empty] | 0 | 0
1336 | [27 empty] | 0 | 0
1337 | [27 empty] | 0 | 0
1338 | [27 empty] | 0 | 0
1339 | [27 empty] | 0 | 0
1340 | [27 empty] | 0 | 0
1341 | [27 empty] | 0 | 0
1342 | [27 empty] | 0 | 0
1343 | [27 empty] | 0 | 0
1344 | [27 empty] | 0 | 0
1345 | [27 empty] | 0 | 0
1346 | [27 empty] | 0 | 0
1347 | [27 empty] | 0 | 0
1348 | [27 empty] | 0 | 0
1349 | [27 empty] | 0 | 0
1350 | [27 empty] | 0 | 0
1351 | [27 empty] | 0 | 0
1352 | [27 empty] | 0 | 0
1353 | [27 empty] | 0 | 0
1354 | [27 empty] | 0 | 0
1355 | [27 empty] | 0 | 0
1356 | [27 empty] | 0 | 0
1357 | [27 empty] | 0 | 0
1358 | [27 empty] | 0 | 0
1359 | [27 empty] | 0 | 0
1360 | [27 empty] | 0 | 0
1361 | [27 empty] | 0 | 0
1362 | [27 empty] | 0 | 0
1363 | [27 empty] | 0 | 0
1364 | [27 empty] | 0 | 0
1365 | [27 empty] | 0 | 0
1366 | [27 empty] | 0 | 0
1367 | [27 empty] | 0 | 0
1368 | [27 empty] | 0 | 0
1369 | [27 empty] | 0 | 0
1370 | [27 empty] | 0 | 0
1371 | [27 empty] | 0 | 0
1372 | [27 empty] | 0 | 0
1373 | [27 empty] | 0 | 0
1374 | [27 empty] | 0 | 0
1375 | [27 empty] | 0 | 0
1376 | [27 empty] | 0 | 0
1377 | [27 empty] | 0 | 0
1378 | [27 empty] | 0 | 0
1379 | [27 empty] | 0 | 0
1380 | [27 empty] | 0 | 0
1381 | [27 empty] | 0 | 0
1382 | [27 empty] | 0 | 0
1383 | [27 empty] | 0 | 0
1384 | [27 empty] | 0 | 0
1385 | [27 empty] | 0 | 0
1386 | [27 empty] | 0 | 0
1387 | [27 empty] | 0 | 0
1388 | [27 empty] | 0 | 0
1389 | [27 empty] | 0 | 0
1390 | [27 empty] | 0 | 0
1391 | [27 empty] | 0 | 0
1392 | [27 empty] | 0 | 0
1393 | [27 empty] | 0 | 0
1394 | [27 empty] | 0 | 0
1395 | [27 empty] | 0 | 0
1396 | [27 empty] | 0 | 0
1397 | [27 empty] | 0 | 0
1398 | [27 empty] | 0 | 0
1399 | [27 empty] | 0 | 0
1400 | [27 empty] | 0 | 0
1401 | [27 empty] | 0 | 0
1402 | [27 empty] | 0 | 0
1403 | [27 empty] | 0 | 0
1404 | [27 empty] | 0 | 0
1405 | [27 empty] | 0 | 0
1406 | [27 empty] | 0 | 0
1407 | [27 empty] | 0 | 0
1408 | [27 empty] | 0 | 0
1409 | [27 empty] | 0 | 0
1410 | [27 empty] | 0 | 0
1411 | [27 empty] | 0 | 0
1412 | [27 empty] | 0 | 0
1413 | [27 empty] | 0 | 0
1414 | [27 empty] | 0 | 0
1415 | [27 empty] | 0 | 0
1416 | [27 empty] | 0 | 0
1417 | [27 empty] | 0 | 0
1418 | [27 empty] | 0 | 0
1419 | [27 empty] | 0 | 0
1420 | [27 empty] | 0 | 0
1421 | [27 empty] | 0 | 0
1422 | [27 empty] | 0 | 0
1423 | [27 empty] | 0 | 0
1424 | [27 empty] | 0 | 0
1425 | [27 empty] | 0 | 0
1426 | [27 empty] | 0 | 0
1427 | [27 empty] | 0 | 0
1428 | [27 empty] | 0 | 0
1429 | [27 empty] | 0 | 0
1430 | [27 empty] | 0 | 0
1431 | [27 empty] | 0 | 0
1432 | [27 empty] | 0 | 0
1433 | [27 empty] | 0 | 0
1434 | [27 empty] | 0 | 0
1435 | [27 empty] | 0 | 0
1436 | [27 empty] | 0 | 0
1437 | [27 empty] | 0 | 0
1438 | [27 empty] | 0 | 0
1439 | [27 empty] | 0 | 0
1440 | [27 empty] | 0 | 0
1441 | [27 empty] | 0 | 0
1442 | [27 empty] | 0 | 0
1443 | [27 empty] | 0 | 0
1444 | [27 empty] | 0 | 0
1445 | [27 empty] | 0 | 0
1446 | [27 empty] | 0 | 0
1447 | [27 empty] | 0 | 0
1448 | [27 empty] | 0 | 0
1449 | [27 empty] | 0 | 0
1450 | [27 empty] | 0 | 0
1451 | [27 empty] | 0 | 0
1452 | [27 empty] | 0 | 0
1453 | [27 empty] | 0 | 0
1454 | [27 empty] | 0 | 0
1455 | [27 empty] | 0 | 0
1456 | [27 empty] | 0 | 0
1457 | [27 empty] | 0 | 0
1458 | [27 empty] | 0 | 0
1459 | [27 empty] | 0 | 0
1460 | [27 empty] | 0 | 0
1461 | [27 empty] | 0 | 0
1462 | [27 empty] | 0 | 0
1463 | [27 empty] | 0 | 0
1464 | [27 empty] | 0 | 0
1465 | [27 empty] | 0 | 0
1466 | [27 empty] | 0 | 0
1467 | [27 empty] | 0 | 0
1468 | [27 empty] | 0 | 0
1469 | [27 empty] | 0 | 0
1470 | [27 empty] | 0 | 0
1471 | [27 empty] | 0 | 0
1472 | [27 empty] | 0 | 0
1473 | [27 empty] | 0 | 0
1474 | [27 empty] | 0 | 0
1475 | [27 empty] | 0 | 0
1476 | [27 empty] | 0 | 0
1477 | [27 empty] | 0 | 0
1478 | [27 empty] | 0 | 0
1479 | [27 empty] | 0 | 0
1480 | [27 empty] | 0 | 0
1481 | [27 empty] | 0 | 0
1482 | [27 empty] | 0 | 0
1483 | [27 empty] | 0 | 0
1484 | [27 empty] | 0 | 0
1485 | [27 empty] | 0 | 0
1486 | [27 empty] | 0 | 0
1487 | [27 empty] | 0 | 0
1488 | [27 empty] | 0 | 0
1489 | [27 empty] | 0 | 0
1490 | [27 empty] | 0 | 0
1491 | [27 empty] | 0 | 0
1492 | [27 empty] | 0 | 0
1493 | [27 empty] | 0 | 0
1494 | [27 empty] | 0 | 0
1495 | [27 empty] | 0 | 0
1496 | [27 empty] | 0 | 0
1497 | [27 empty] | 0 | 0
1498 | [27 empty] | 0 | 0
1499 | [27 empty] | 0 | 0
1500 | [27 empty] | 0 | 0
1501 | [27 empty] | 0 | 0
1502 | [27 empty] | 0 | 0
1503 | [27 empty] | 0 | 0
1504 | [27 empty] | 0 | 0
1505 | [27 empty] | 0 | 0
1506 | [27 empty] | 0 | 0
1507 | [27 empty] | 0 | 0
1508 | [27 empty] | 0 | 0
1509 | [27 empty] | 0 | 0
1510 | [27 empty] | 0 | 0
1511 | [27 empty] | 0 | 0
1512 | [27 empty] | 0 | 0
1513 | [27 empty] | 0 | 0
1514 | [27 empty] | 0 | 0
1515 | [27 empty] | 0 | 0
1516 | [27 empty] | 0 | 0
1517 | [27 empty] | 0 | 0
1518 | [27 empty] | 0 | 0
1519 | [27 empty] | 0 | 0
1520 | [27 empty] | 0 | 0
1521 | [27 empty] | 0 | 0
1522 | [27 empty] | 0 | 0
1523 | [27 empty] | 0 | 0
1524 | [27 empty] | 0 | 0
1525 | [27 empty] | 0 | 0
1526 | [27 empty] | 0 | 0
1527 | [27 empty] | 0 | 0
1528 | [27 empty] | 0 | 0
1529 | [27 empty] | 0 | 0
1530 | [27 empty] | 0 | 0
1531 | [27 empty] | 0 | 0
1532 | [27 empty] | 0 | 0
1533 | [27 empty] | 0 | 0
1534 | [27 empty] | 0 | 0
1535 | [27 empty] | 0 | 0
1536 | [27 empty] | 0 | 0
1537 | [27 empty] | 0 | 0
1538 | [27 empty] | 0 | 0
1539 | [27 empty] | 0 | 0
1540 | [27 empty] | 0 | 0
1541 | [27 empty] | 0 | 0
1542 | [27 empty] | 0 | 0
1543 | [27 empty] | 0 | 0
1544 | [27 empty] | 0 | 0
1545 | [27 empty] | 0 | 0
1546 | [27 empty] | 0 | 0
1547 | [27 empty] | 0 | 0
1548 | [27 empty] | 0 | 0
1549 | [27 empty] | 0 | 0
1550 | [27 empty] | 0 | 0
1551 | [27 empty] | 0 | 0
1552 | [27 empty] | 0 | 0
1553 | [27 empty] | 0 | 0
1554 | [27 empty] | 0 | 0
1555 | [27 empty] | 0 | 0
1556 | [27 empty] | 0 | 0
1557 | [27 empty] | 0 | 0
1558 | [27 empty] | 0 | 0
1559 | [27 empty] | 0 | 0
1560 | [27 empty] | 0 | 0
1561 | [27 empty] | 0 | 0
1562 | [27 empty] | 0 | 0
1563 | [27 empty] | 0 | 0
1564 | [27 empty] | 0 | 0
1565 | [27 empty] | 0 | 0
1566 | [27 empty] | 0 | 0
1567 | [27 empty] | 0 | 0
1568 | [27 empty] | 0 | 0
1569 | [27 empty] | 0 | 0
1570 | [27 empty] | 0 | 0
1571 | [27 empty] | 0 | 0
1572 | [27 empty] | 0 | 0
1573 | [27 empty] | 0 | 0
1574 | [27 empty] | 0 | 0
1575 | [27 empty] | 0 | 0
1576 | [27 empty] | 0 | 0
1577 | [27 empty] | 0 | 0
1578 | [27 empty] | 0 | 0
1579 | [27 empty] | 0 | 0
1580 | [27 empty] | 0 | 0
1581 | [27 empty] | 0 | 0
1582 | [27 empty] | 0 | 0
1583 | [27 empty] | 0 | 0
1584 | [27 empty] | 0 | 0
1585 | [27 empty] | 0 | 0
1586 | [27 empty] | 0 | 0
1587 | [27 empty] | 0 | 0
1588 | [27 empty] | 0 | 0
1589 | [27 empty] | 0 | 0
1590 | [27 empty] | 0 | 0
1591 | [27 empty] | 0 | 0
1592 | [27 empty] | 0 | 0
1593 | [27 empty] | 0 | 0
1594 | [27 empty] | 0 | 0
1595 | [27 empty] | 0 | 0
1596 | [27 empty] | 0 | 0
1597 | [27 empty] | 0 | 0
1598 | [27 empty] | 0 | 0
1599 | [27 empty] | 0 | 0
1600 | [27 empty] | 0 | 0
1601 | [27 empty] | 0 | 0
1602 | [27 empty] | 0 | 0
1603 | [27 empty] | 0 | 0
1604 | [27 empty] | 0 | 0
1605 | [27 empty] | 0 | 0
1606 | [27 empty] | 0 | 0
1607 | [27 empty] | 0 | 0
1608 | [27 empty] | 0 | 0
1609 | [27 empty] | 0 | 0
1610 | [27 empty] | 0 | 0
1611 | [27 empty] | 0 | 0
1612 | [27 empty] | 0 | 0
1613 | [27 empty] | 0 | 0
1614 | [27 empty] | 0 | 0
1615 | [27 empty] | 0 | 0
1616 | [27 empty] | 0 | 0
1617 | [27 empty] | 0 | 0
1618 | [27 empty] | 0 | 0
1619 | [27 empty] | 0 | 0
1620 | [27 empty] | 0 | 0
1621 | [27 empty] | 0 | 0
1622 | [27 empty] | 0 | 0
1623 | [27 empty] | 0 | 0
1624 | [27 empty] | 0 | 0
1625 | [27 empty] | 0 | 0
1626 | [27 empty] | 0 | 0
1627 | [27 empty] | 0 | 0
1628 | [27 empty] | 0 | 0
1629 | [27 empty] | 0 | 0
1630 | [27 empty] | 0 | 0
1631 | [27 empty] | 0 | 0
1632 | [27 empty] | 0 | 0
1633 | [27 empty] | 0 | 0
1634 | [27 empty] | 0 | 0
1635 | [27 empty] | 0 | 0
1636 | [27 empty] | 0 | 0
1637 | [27 empty] | 0 | 0
1638 | [27 empty] | 0 | 0
1639 | [27 empty] | 0 | 0
1640 | [27 empty] | 0 | 0
1641 | [27 empty] | 0 | 0
1642 | [27 empty] | 0 | 0
1643 | [27 empty] | 0 | 0
1644 | [27 empty] | 0 | 0
1645 | [27 empty] | 0 | 0
1646 | [27 empty] | 0 | 0
1647 | [27 empty] | 0 | 0
1648 | [27 empty] | 0 | 0
1649 | [27 empty] | 0 | 0
1650 | [27 empty] | 0 | 0
1651 | [27 empty] | 0 | 0
1652 | [27 empty] | 0 | 0
1653 | [27 empty] | 0 | 0
1654 | [27 empty] | 0 | 0
1655 | [27 empty] | 0 | 0
1656 | [27 empty] | 0 | 0
1657 | [27 empty] | 0 | 0
1658 | [27 empty] | 0 | 0
1659 | [27 empty] | 0 | 0
1660 | [27 empty] | 0 | 0
1661 | [27 empty] | 0 | 0
1662 | [27 empty] | 0 | 0
1663 | [27 empty] | 0 | 0
1664 | [27 empty] | 0 | 0
1665 | [27 empty] | 0 | 0
1666 | [27 empty] | 0 | 0
1667 | [27 empty] | 0 | 0
1668 | [27 empty] | 0 | 0
1669 | [27 empty] | 0 | 0
1670 | [27 empty] | 0 | 0
1671 | [27 empty] | 0 | 0
1672 | [27 empty] | 0 | 0
1673 | [27 empty] | 0 | 0
1674 | [27 empty] | 0 | 0
1675 | [27 empty] | 0 | 0
1676 | [27 empty] | 0 | 0
1677 | [27 empty] | 0 | 0
1678 | [27 empty] | 0 | 0
1679 | [27 empty] | 0 | 0
1680 | [27 empty] | 0 | 0
1681 | [27 empty] | 0 | 0
1682 | [27 empty] | 0 | 0
1683 | [27 empty] | 0 | 0
1684 | [27 empty] | 0 | 0
1685 | [27 empty] | 0 | 0
1686 | [27 empty] | 0 | 0
1687 | [27 empty] | 0 | 0
1688 | [27 empty] | 0 | 0
1689 | [27 empty] | 0 | 0
1690 | [27 empty] | 0 | 0
1691 | [27 empty] | 0 | 0
1692 | [27 empty] | 0 | 0
1693 | [27 empty] | 0 | 0
1694 | [27 empty] | 0 | 0
1695 | [27 empty] | 0 | 0
1696 | [27 empty] | 0 | 0
1697 | [27 empty] | 0 | 0
1698 | [27 empty] | 0 | 0
Note on L2: Dulson, Emma: If maps or other documents are used for the RFI - please add an extra tab at the bottom stating the site name/permit number. Please delete this once the RFI is closed.