## Sheet1
| HAFOD QUARRY LEACHATE MANAGEMENT ACTION PLAN | [5 empty] | Record Number: Hafod/LMAP/005
Date: April 2026
Page 1 of 1
Hafod Quarry Landfill Site - Leachate Management Action Plan |  | ORIGIN (highlight) |  | H&S: | Env: JH | B/C: | Ops: IC & DL
|  | REPONSIBILITY | I Craven / D Leonard
PROGRAMME DETAILS/SHORT TERM TARGETS |  | TARGET TIMEFRAME | PROGRESS & COMMENTS INCLUDING RESOURCES
1. Complete proposed permanent clay capping , circa 10,590m2, as per HAF 350 Proposed Capping Plan 2026. |  | Target - 31/07/26 Ongoing | Permanent clay capping on Cell 4 and Cells 5a/5b will be undertaken once tipping in Cell 5b is up to final levels. An area of 2500m2 is now ready and capping will commence on 15th April 2026. Restoration soils currently being deployed to last years capped areas.
2. Install further temporary LLDPE capping along outer northern flank and inner western flank of Cell 5b, as per HAF 350 Proposed Capping Plan 2026. |  | Target - 30/04/26 | An additional 4355m2 of LLDPE capping has been identified on northern flank of Cell 5b and will be installed as soon as ground conditions allow. An additional 3630m2 will then be able to be achieved.
3. Install fully automated pumping system (Leachate, Ground and Surface Water) in Cell 5c once Cell is fully engineered, to ensure extraction can commence as soon as tipping operations are approved. |  | Target - 31/03/26 Completed | All electric cabling, leachate control panel and pumps operational. Ground Water and Surface Water pumps and controls are fully installed and operational. Surface water ditches improved and lagoon increased in size.
4. Install a replacement leachate extraction chamber for LC3 in Cell 3. |  | Target - 31/03/26 Completed | A blockage was identified in LC3 which prevent it being ustilised as an extraction chamber. CQA Plan was submitted and a replacement chamber was drilled between 16th and 22nd March 2026. Chamber successfully drilled to target depth of 49m and pump will be installed week commencing 13th April.
5. Remove any siltation at the bottom of existing leachate infrastructure which may prevent compliance levels being achieved. |  | Target 31/05/2026 | Discussions held with specialist contractor to use hydraulic solids handling pump to attempt to remove silt from the bottom of affected chambers.
6. Monitor liquid level in gas wells to determine if this is having any effect on gas collection efficiencies. |  | Ongoing | Gas team continue to undertake regular dipping exercises across the site. Eductor system has been installed on two gas wells in Cell 5a and recharge rates monitored. Report has been produced and submitted to NRW in March 2026.
7. Revised Leachate Management Plan was submitted to NRW on 12th December 2025. As this Plan is fully adopted, produce 6 monthly LMAP's to update progress towards the stated aims. |  | Ongoing | Curently awaiting NRW comments on revised LMP. Incorporate any comments received and operate in accordance with this Plan. This LMAP is the second of those submitted in 2026.
8. Conduct a HRA review and propose new leachate compliance levels together with justification to increase levels from 2m head to (6m ?) head in Cells 1 to 4. |  | Target 31/05/26 | HRA Review is currently in draft form at the consultants and will be internally reviewed once received. We are aiming to get this submitted to NRW before the end of May 2026.
9. Install a new sealed access hatch onto the top of the Green Tank on Cell 1 to prevent any associated leachate pumping odours escaping along the perimeter of New Hall Lane. |  | 30/01/2026 Completed | Improvements made to sealing on access hatch and inspected during recent NRW Gas Audit.
10. Installation of automated pumping infrastructure within MP4b, to affect what are believed to be perched leachate levels within this chamber and MP4a. |  | Target - 31/03/26 | Pump installed in MP4b, new cabling put in to run from temporary generator. Controls will be installed week commencing 13th April 2026. Continue to monitor levels in MP4a for the next 3 months to see if pumping in MP4b has any affect on drawing levels down.
COMPLETION DATE: |  |  | SIGNED OFF:
Date updated: 10th April 2026
RECORD AUTHOR: Ian Craven