Wrexham Drainage Improvement Plan

Introduction

In response to the action issued by NRW (CAR_NRW0036261) for maintaining the site interceptor. The following plan takes into account the need to maintain and inspect the interceptor on a bye annual basis and ensure access is easy to achieve.

The plan involves the movement of the porta cabin office block from its current location to the lorry park. This will involve the installation of a concrete slab to take the weight of the cabin and provide safe access to those staff that normally use it.

Project team:

VN – Vince Norris - Project lead

Paul Phillips - Plant Manager

Mike Munro -Site Engineer

Alex Jones - Site Electrical Engineer

Action Plan

| Task | Current status | Responsible person | Target date for completion |
| --- | --- | --- | --- |
| - Find suitable contractor to complete the civils within the lorry park | Porta Cabin Ltd issued with purchase order to complete items 1 to 4,l RAM’s and risk assessments to be submitted to Tradebe prior to work commencing | VN | 20/02/2020 |
| - Engage a contractor to move the portacabin from its current location to its new location | As above | VN | 20/03/2020 |
| - Find suitable contractor to Install new utilities to the porta cabin | As above | VN & AJ | 20/03/2020 |
| - Move the Porta cabin to its new location | As above | VN | 01/06/2020 |
| - Carry out full clean out and inspection of the interceptor |  | VN & MM | 05/06/2020 |
| - Carry out full drainage survey on the surface water and foul drainage system on site |  | VN | 15/06/2020 |
| - Update drawings and submit to NRW |  | VN | 01/07/2020 |
| - Update PPM system to ensure bi-annual inspections of the interceptor /drains are complete |  | MM | 01/07/2020 |