## Title Sheet
Signposting of Morlais response_MCA
Applicant: Menter Môn Morlais Limited
Morlais Document No.: | Status: | Version No.: | Date:
MOR-MCO-DOC-003 | Final | 1 | 2021-06-09
© 2021 Menter Môn | This document is issued and controlled by: |  |  | Menter Môn
Morlais, Menter Môn. Registered Address: Llangefni Town Hall, Anglesey, Wales, LL77 7LR, UK
Unauthorised copies of this document are NOT to be made
Company registration No: | 3160233 | Requests for additional copies shall be made to Morlais Project

## MCA 2
Reference | Document | Section | MCA Comment 2 | Morlais Response
1 |  |  | Thank you for the opportunity to comment on the second Marine Licence consultation and supporting information for the proposed Morlais Tidal Array project to construct and operate the tidal devices west of Anglesey. | With reference to the MCA’s letter to NRW dated 20th April 2021.
2 |  |  | On 10 December 2019 I wrote to you with our response to the fist marine licence consultation, in italics below. Following the Transport and Works Act inquiry, I have provided an update on our position below in red.
3 |  | NRA | We are satisfied the NRA has been conducted accordance with the published guidelines of the Methodology for Assessing Navigational Risk, however the completed MGN Checklist has not been provided.
4 |  |  | The MCA is content the NRA was conducted in accordance with MCA published guidance, however it is important to note that this refers to the process undertaken and does not necessarily guarantee acceptance of the NRA results. It is the risk scores and the conclusion that the risk will be tolerable that has been challenged by other stakeholders regarding the safety of navigation and safety of recreational users. The MGN Checklist was provided in the NRA Addendum. | We are pleased to see that the MCA are content the NRA has been conducted in accordance with the MCA published guidance and it is confirmed that the checklist has been provided. It is acknowledged that other stakeholders are challenging the scores and conclusions. At present, because of the flexibility inherent within the PDE and phased approach we understand that it is the MCAs position that it is not possible to confirm that the conclusions reflect the final project that will be constructed. We understand from our discussions with the MCA that the MCA consider the NRA addendum and conclusions are adequate for the current stage of the consent process and that they expect the commitment for future array specific NRA’s to be secured through the ML Conditions. It is these array specific NRA’s which will allow for a definitive conclusion to be reached as they will be based on the actual devices proposed to be deployed. We note that the MCA have not raised an objection to the project. The MCA agree with us that all appropriate details and risk controls can be determined through array specific NRAs. There is precedent for this approach at other wind and test sites around the UK.
5 |  |  | We are satisfied that appropriate traffic data has been collected in accordance with MGN543, which includes six months’ worth of AIS data. Out of 46 hazards identified for collisions, contacts, groundings and snagging during the construction and operation phases, 26 hazards were assessed as having a risk score higher than 4 (‘low risk’). Therefore, these 26 hazards would require additional mitigation for the risk to be tolerable and As Low As Reasonably Practicable (ALARP). However, it is unclear on the terminology in the document on which mitigation measures are recommended. There is a ‘Suggested risk control’ section where mitigation is recommended however for the remainder of the document they are referred to as ‘possible mitigation’. In order to agree that risks are deemed to be ALARP, it needs to be made clearer exactly which risk control measures are recommended for implementation.
6 |  |  | MCA is content with Table 13-1 of the NRA Addendum provides for ‘Suggested Additional Risk Controls’, however not all are agreed. MCA agrees the following risk controls are necessary to reduce risks to As Low As Reasonably Practicable, as per Table 13-1 and I have provided a comment to each: | With regard to the MCA comments on the Suggested Additional Risk Controls, the project can confirm that we will comply with the MCA’s requests and those conditions secured through the marine licence as detailed. We believe that all other items highlighted have been dealt with to the MCA’s satisfaction and we continue to have a very good ongoing dialogue with the MCA.
7 |  | Risk Control | MCA Comment
8 |  | 1 Continuous Monitoring by Marine Co-ordination Centre. | To be secured as a condition in the marine licence.
9 |  | 4 Appropriate alignment and spacing of devices. | Each array will require layout approval from MCA and Trinity House which must include micrositing limits and ID marking. To be secured as a condition in the marine licence.
10 |  | 5 Check device surveys. | To be secured as a condition in the marine licence, including frequency of surveys.
11 |  | 6 Guard vessel to monitor passing traffic during construction. | To be secured as a condition in the marine licence.
12 |  | 8 Enhanced cable protection. | To be secured as a condition in the marine licence.
13 |  | 9 Implementation of Safety Zones during construction. | This will require an application through BEIS or Welsh Ministers.
14 |  | 10 Temporary navigation aids as required by Trinity House. | To be secured as a condition in the marine licence.
15 |  | 11 Undertake Device / Array Specific Risk Assessments to include NavAids and Marker Buoys. | MCA requests updates to the site-wide NRA every two years and array-specific NRAs for each array. Both to be secured as separate conditions in the marine licence.
16 |  | 12 Provision of life saving equipment on fixed structures and floating devices. | Further details must be discussed with MCA for each array and be included in the array-specific NRAs.
17 |  | 13 Minimise use of marker buoys in zones of minimum UKC. | To be agreed by Trinity House
18 |  |  | In addition, any device moored to the seabed must have mooring arrangements that meet the guidance document published by MCA and HSE “Regulatory expectations on moorings for floating wind and marine devices” which includes Third Party Verification by an independent competent person or body to ensure the mooring arrangements are suitable.
19 |  |  | MCA does not agree the following additional risk controls are necessary:
20 |  | Risk Control | MCA Comment
21 |  | 2 Restrict Navigation through the Gold and Green MDZ Zones [through either an Area To Be Avoided or a Precautionary Area]. | These are IMO-adopted routeing measures and will require formal application through UK Safety of Navigation Committee and agreement at IMO. This process can be lengthy and whilst MCA does not believe an ATBA is appropriate however we would be willing to discuss the appropriateness of a Precautionary Area.
22 |  | 3 MDZ designation as a No Fishing Zone | When test arrays are in place fishermen are unlikely to fish in the area and provided the necessary notifications are issued and the MDZ is charted in nautical charts and publications fishermen will be aware of the hazards.
23 |  | 7 Establish no anchoring areas [around nearshore cable route] | Export cables do not normally attract ‘no anchoring areas’ - the cable will be charted by the UKHO and mariners are already advised not to anchor within 0.25nm of a cable.
24 |  |  | We would recommend that a section is included on interactive boundaries, particularly to assess the northern and eastern boundaries to provide evidence for the risk control measures.
25 |  |  | A separate Interactive Boundaries Assessment was provided. | Agreed
26 |  |  | The type of device(s) to be installed is not yet known and the report suggests that it would be a mixture of surface floating, mid-water suspension and bottom mounted. Feedback has been gathered from stakeholders (ferry companies, CoS, RYA and RNLI) on under-keel clearance requirements, however we would recommend that under-keel clearance calculations are made to corroborate this evidence. Further guidance is available from the MCA’s Under Keel Clearance paper.
27 |  |  | The site was divided into coloured zones which accounted for under keel clearance, specifically the purple zone (20m UKC) and blue zone (8m UKC). | Agreed
28 |  | NRA Additional Mitigation | We have the following comments on the list of 15 Additional Mitigation measures in Table 11-1 for reducing the inherent risk to ALARP:
29 |  |  | • “Restrict Navigation through the Morlais Zone” via an Area To Be Avoided or Precautionary Area. These are IMO routeing measures and will need a formal proposal to MCA and UK Safety of Navigation committee for approval.
30 |  |  | • “Exclusion of fishing within the Morlais Zone”. It is not clear how this is to be implemented. Whilst this risk control aims to prevent snagging of fishing gear, it relates to the risks associated with fishing activity rather than to surface navigation.
31 |  |  | • “Establish no anchoring areas” around the nearshore cable route. This will need a formal proposal to MCA for approval.
32 |  |  | • “Enhanced cable protection” where burial is not possible. It can be argued this is an embedded risk control since it is already a requirement to protect unburied cables.
33 |  |  | • “Construction vessels to be marked in accordance with COLREG”. It can be argued this is an embedded risk control since the Collision Regulations are an established set of regulations for shipping activity and all vessels, when not jacked up, must already exhibit signals in accordance with COLREG.
34 |  |  | • When any construction vessel is jacked up, it must exhibit signals in accordance with the UK Standard Marking Schedule for Offshore Installations.
35 |  |  | As above.
36 |  | Environmental Statement (Shipping & Navigation Chapter) | The ES does not make any proposals on risk controls, rather it uses the ‘possible mitigation’ terminology and it is therefore unclear what is being proposed.
37 |  |  | The list of mitigation measures in the ES differs from that in the NRA:
38 |  |  | • Within the NRA it suggests: “Devices >20m below CD to be deployed within Zones 1,2 and 8”. The ES only suggests this for zone 1, not 2 or 8 so we request justification from Mentor Mon/Marine Space.
39 |  |  | MCA understands that Figure 1 in the NRA Addendum is the final proposed zonal layout of the site. | Agreed this is the proposal.
40 |  |  | • “Re-design eastern boundary”. There should be an interactive boundary assessment on the inshore sea space to be able to discount reducing the eastern boundary as commercially unviable.
41 |  |  | An Interactive Boundary Assessment was conducted which led to the expansion of the blue zone. | Agreed
42 |  |  | • It is not clear how much sea room there will be (RYA recommend 4 cables) east of the eastern boundary. However, we note that “Only deploy devices that allow at least 8 m UKC along eastern boundary” as an additional risk control has been included which we would suggest requires an under-keel clearance calculation to support it.
43 |  |  | An Interactive Boundary Assessment was conducted which led to the revised zonal layout. | Agreed this was part of the process.
44 |  |  | It appears there are discrepancies between the NRA and Shipping & Navigation Chapter in the ES. Where the advice contained within the NRA has not been taken forward by the applicant into the ES there should be appropriate justification
45 |  | Risk Matrix | We note there are inconsistencies between the risk matrices in the NRA and ES. The NRA lists each hazard, scores them and lists possible risk control measures. The ES however, does not use the NRA hazard list, instead some of the NRA hazards have been included along with combined hazards which are described as ‘Impacts’ e.g. “Potential Impacts to Commercial Vessels”. These have then been scored. This makes it quite confusing and difficult to read and understand. The result is that the risk control measures do not correspond. For instance, the NRA lists seven risk controls for the Grounding of a Recreational Vessel, whereas the ES identifies just one risk control measure.
46 |  |  | We request the applicant provides a risk control log of embedded and additional mitigation measures to confirm what is proposed for the project. Without this we are unable to agree that the risk scores are at an ALARP level.
47 |  |  | Table 13-1 of the NRA Addendum provides for the applicant’s draft marine licence conditions (Document Reference: MMC011 MOR-ESI-DOC-0001). I provided comments to NRW on these in my email dated 13/4/21. | Acknowledged
48 |  | Cable Routes | Export cable routes, cable burial protection index and cable protections are issues that are yet to be fully developed. However due cognisance needs to address cable burial and protection, particularly close to shore where impacts on navigable water depth may become significant. Any consented cable protection works must ensure existing and future safe navigation is not compromised. The MCA would accept a maximum of 5% reduction in surrounding depth referenced to Chart Datum. Existing charted anchorage areas should be avoided.
49 |  |  | To be secured as a condition in the marine licence. | We are content if NRW choose to proceed in this way.
50 |  | Safety Zones | Construction and operational safety zones will only be granted subject to a detailed justification with significant evidence from the construction and operational phases in addition to the baseline NRA required supporting the case.
51 |  |  | No change to MCA position. | Acknowledged
52 |  | Mooring Arrangements | Third Party Verification of the mooring arrangements for all floating devices will be required prior to construction to provide assurance against loss of station. Ideally this will be a condition of the marine licence. Guidance on regulatory expectations on mooring arrangements can be found on our website: https://www.gov.uk/guidance/offshore-renewable-energy-installations-impact-on-shipping
53 |  |  | To be secured as a condition in the marine licence. | We are content if NRW choose to proceed in this way.
54 |  | Emergency Response | Stakeholders raised a concern about access to Holyhead as a safe haven however it is not clear where this has been addressed in the NRA and ES.
55 |  |  | Further consultation will be required with the MCA to discuss emergency response requirements in accordance with MGN543 Annex 5, including the completion of a SAR Checklist.
56 |  |  | The requirement for an ERCoP will be secured through condition 13 below for the marine licence. | We are content if NRW choose to proceed in this way.
57 |  | Bathymetric Survey Data | MGN 543 Annex 2 Paragraph 6 requires that hydrographic surveys should fulfil the requirements of the International Hydrographic Organisation (IHO) Order 1a standard, with the final data supplied as a digital full density data set, and survey report to the UKHO and MCA for updating of nautical charts and publications. This should include the site and its immediate environs extending to 500m outside of the development area and a cable route survey post-construction.
58 |  |  | No change to MCA position. | Agreed
59 |  | Turbine Layout Plan | The turbine layout plan will require discussion and approval of the MCA and Trinity House prior to construction commencing. This is to ensure risks to navigation safety and search and rescue operations are minimised.
60 |  |  | No change to MCA position. | Agreed
61 |  | Marine Licence Conditions | The following list of licence conditions and advisories are requested:
62 |  |  | No change on our position for the below conditions and advisories, provided our comments to the applicant’s Draft Marine Licence Conditions are also addressed. | We are content if NRW choose to proceed in this way.
63 |  | Conditions | 1. The Licencee must ensure appropriate steps are taken to minimise damage to the shoreline resulting from the works and that navigational aids and/or the topography are returned to the original profile, or as close as reasonably practicable, following the completion of the works.
64 |  |  | 2. The Licencee must issue local notification to marine users, including fisherman’s organisations, neighbouring port authorities, HM Coastguard, UKHO and other local stakeholders, to ensure that they are made fully aware of the activity at least 14 days prior to the commencement of the authorised project.
65 |  |  | 3. The Licencee must ensure that HM Coastguard, in this case nmoccontroller@hmcg.gov.uk, The National Maritime Operations Centre is made aware of the works prior to commencement.
66 |  |  | 4. The Licencee must notify the UK Hydrographic Office of the completion of the authroised project within 14 days to permit the updating of nautical charts and publications.
67 |  |  | 5. The Licencee must ensure that 'the works' do not encroach on any recognised anchorage, either charted or noted in nautical publications, within the proposed consent area.
68 |  |  | 6. Any consented cable/pipeline protection works must ensure existing and future safe navigation is not compromised. The MCA would accept a maximum of 5% reduction in surrounding depth referenced to Chart Datum but under no circumstances should depth reductions compromise safe navigation.
69 |  |  | 7. A Third Party Verification of the mooring arrangements for all floating devices must be undertaken prior to construction to ensure the mooring design is suitable for the location.
70 |  |  | 8. As per the requirements of MCA’s MGN 543 and supplementary updates, the Licencee must complete periodic hydrographic surveys of the consented area or subsections thereof, to the IHO Order 1a survey standard. On completion of these surveys the results and a corresponding report of survey must be supplied to the UKHO, with notification to the MCA Hydrography Manager.
71 |  |  | 9. The Licencee should ensure suitable bunding, storage facilities are employed to prevent the release of fuel oils, lubricating fluids associated with the plant and equipment into the marine environment.
72 |  |  | 10.In case of damage to, or destruction or decay of, the authorised project seaward of MHWS or any part thereof, excluding the exposure of cables, the undertaker shall as soon as reasonably practicable and no later than 24 hours following the undertaker becoming aware of any such damage, destruction or decay, notify MCA, Trinity House, the Kingfisher Information Service of Seafish and the UKHO.
73 |  |  | 11. No part of the authorised project may commence until the NRW, in consultation with the MCA, has confirmed in writing that a detailed cable laying plan has been satisfactorily conducted incorporating a burial risk assessment encompassing the identification of any cable protection that exceeds 5% of navigable depth referenced to chart datum and, in the event that any area of cable protection exceeding 5% of navigable depth is identified, details of any steps (to be determined following consultation with the MCA and Trinity House) to be taken to ensure existing and future safe navigation is not compromised or such similar assessment to ascertain suitable burial depths and cable laying techniques, including cable protection. This plan must include proposals for monitoring offshore cables including cable protection during the operational lifetime of the authorised scheme which includes a risk-based approach to the management of unburied or shallow buried cables.
74 |  |  | 12. In case of exposure of cables on or above the seabed, the undertaker must within three days following identification of a potential cable exposure, notify mariners by issuing a notice to mariners and by informing Kingfisher Information Service of the location and extent of exposure. Copies of all notices must be provided to the MCA, Trinity House, and the UKHO within 5 days.
75 |  |  | 13. No part of the authorised project may commence until the NRW, in consultation with the MCA, has confirmed in writing that the undertaker has taken into account and, so far as is applicable to that stage of the project, adequately addressed all MCA recommendations as appropriate to the authorised project contained within MGN543 Offshore Renewable Energy Installations (OREIs) – Guidance on UK Navigational Practice, Safety and Emergency Response Issues and its annexes.
76 |  |  | 14. Post construction monitoring must include vessel traffic monitoring by Automatic Identification System for a duration of three consecutive years following the completion of construction of authorised project, unless otherwise agreed in writing by the NRW. An appropriate report must be submitted to the NRW, Trinity House and the MCA at the end of each year of the three-year period.
77 |  | Advisories | 1. No radio beacon or radar beacon operating in the Marine frequency bands shall be installed or used on the works without prior written approval by OFCOM.
78 |  |  | 2. Any jack up barges / vessels utilised during the works/laying of the cable, when jacked up, should exhibit signals in accordance with the UK Standard Marking Schedule for Offshore Installations.
79 |  |  | 3. If in the opinion of the Secretary of State the assistance of a Government Department, including the broadcast of navigational warnings, is required in connection with the works or to deal with any emergency arising from the failure to mark and light the works as required by the consent or to maintain the works in good order or from the drifting or wreck of the works, the owner of the works shall be liable for any expense incurred in securing such assistance.
80 |  | Conclusion | The nature of the proposed Morlais Tidal Demonstration project in that it is a test site for tidal arrays means we must approach our marine licence response differently to other offshore renewable energy installations that are not test sites. The marine licence from this consultation will allow for the site to be established but future arrays to be installed will be subject to further marine licence applications for individual array deployments. The MCA still has concerns regarding the safety of recreational users and expects the same stakeholder concerns will be submitted to yourselves in this marine licence consultation.
81 |  |  | We understand from Mentor Mon that their intention is to stagger future array deployments therefore the above comments are not made on the assumption that the whole site will have a maximum number of consented/licenced arrays and turbines installed in the first round of construction activity. It is made on the provision that array deployment will be staggered therefore future discussions with the applicant will be necessary for the subsequent marine licence applications to ensure appropriate risk controls are agreed which will hopefully meet the concerns of all stakeholders. MCA believes it may be possible to satisfy navigation stakeholder concerns and that the risks can be either acceptable or tolerable (if ALARP) as the site develops.